## Milestones (hidden)
CovPhyTopTest Plan - Verification Milestones
The following lists CovPhyTop verification milestones.
Release | Milestone Metric | Test Completion |  |  |  | Coverage |  | Due Date
No | Details | P1 % | P2 % | P3 % | P4 % | Code % | Functional % | WW
0.1 | TB Environment creation 1. UVM ENV 2. RAL model 3. Score Board 4. Cover Groups 5. Assertions | 0 | 0 | 0 | 0 | 0 | 0
0.3 | TB Environment Fixes, register access and connectivity tests | 10 | 0 | 0 | 0 | 20 | 20
0.5 | Random/various configuration tests and Interrupts | 60 | 30 | 20 | 10 | 50 | 50
0.8 | E2E, Performance and Error Test | 90 | 70 | 50 | 30 | 75 | 75
0.9 | Random Regression Failure Fixes (RTL Freeze) | 100 | 90 | 80 | 70 | 90 | 90
1 | Random Regression Failure Fixes (ECO) | 100 | 100 | 100 | 100 | 100 | 100

## Overview
Static tools | Dynamic tools | Collage tool | Coretools
|  | 5.8 | P-2019.06-SP5
CLP / 19.10-s300 | xcelium/19.03-s003
VCLP / P-2019.06-SP2-1 | vcsmx/P-2019.06-SP2-3
NoC
NSPS
PMXTOR
CXT
IDI
CMI
AXI SLV
AHB SLV
CMIS SLV
S
Y
N
C
U
N
I
T
req
ack
req
ack
req
ack
ack
req
QC
I/f
rst_<pd>
host clk/rst/pwr controls
host clk/rst/pwr controls
global reset and gclocks
pwr controls
clocks
ClkGen
UFI
req
ack
APB SLV
ns_soc_ip.v

## Tasks N Owners
JIRA | Task | Owner | NS or collage/corekit flow | Planned(APR) | Dependencies | Timeline
VCLP | VCLP IDI | John S | corekit/Collage flow |  | RTL, SW, UPF | WW20
| VCLP CMI | John S | corekit/Collage flow |  | RTL, SW, UPF | WW20
| VCLP RBC+RBM | John S | corekit/Collage flow |  | RTL, SW, UPF | WW20
| VCLP for UFI | John S | corekit/Collage flow |  | RTL, SW, UPF | WW20
| Nocweaver cfg VCLP and debug | John S | corekit/Collage flow | 1000+ cfgs | RTL, SW, UPF | WW20
Dynamic sim with Xcelium | Xcelium +UPF IDI | Nikesh | corekit/Collage flow | Autowake | RTL, SW, UPF | WW21
| Xcelium+UPF CMI | Sreeram | corekit/Collage flow | Autowake | RTL, SW, UPF | WW21
| Xcelium+UPF RBC+RBM | John+Sreeram | corekit/Collage flow | Autowake | RTL, SW, UPF | WW21
| Xcelium+UPF UFI | Nikesh | corekit/Collage flow | Autowake | RTL, SW, UPF | WW21
| Nocweaver cfg bring up(Xcelium) and debug | Nikesh+sreeram | corekit/Collage flow | 1000+ cfgs | RTL, SW, UPF | WW22
Dynamic sim with VCSNLP | VCSNLP+UPF IDI | Aswin | corekit/Collage flow | Autowake | RTL, SW, UPF | WW21
| VCSNLP+UPF CMI | Aswin+Sreeram | corekit/Collage flow | Autowake | RTL, SW, UPF | WW21
| VCSNLP+UPF RBC+RBM | John+sreeram | corekit/Collage flow | Autowake | RTL, SW, UPF | WW22
| VCSNLP+UPF UFI | Aswin | corekit/Collage flow | Autowake | RTL, SW, UPF | WW22
| Nocweaver cfg bring up(VCSNLP) and debug | Aswin+John S+sreeram | corekit/Collage flow | 1000 +cfgs | RTL, SW, UPF | WW23
Nemesis | nemesis/Gen X changes | Aswin/Nikesh | corekit/Collage flow |  | IDI | WW19
[5 empty] | CMI | WW19
[5 empty] | UFI | WW20
[5 empty] | RBC+RBM | WW20
Retention |  | John S
Save and restore
Regressions | Lp regressions | Aswin |  |  | VCSNLP(AMBA) | WW22
|  | John/Sreeram/Nikesh |  |  | IDI | WW19
|  | John/Sreeram/Nikesh |  |  | CMI | WW19
|  | John/Sreeram/Nikesh |  |  | UFI | WW19
|  | Aswin/Nikesh |  |  | All with nemesis and nocweaver changes | WW23
| External sanity sims with Collage flow | Aswin |  |  | IDI | WW23
[5 empty] | CMI | WW23
[5 empty] | UFI | WW23
[5 empty] | RBC+RBM | WW23
Pending BUGS |  | John S/Sreeram/Nikesh

## Power Gating - Static
LP | Voltage Domain | Power Domain | Components | Cell Type |  |  | Hier/Flat | NS/Collage | Tools/Version | Rule Checks | Waivers | Random Tests | BuildBot
|  |  |  | Isolation | Level Shifter | Retention
Static LP | Multi Voltage | Autowake or AON | AMBA | YES | YES | NO | Both | Both | CLP / 19.10-s300 | Applies UPF standard rule checks | waive_lp -add FLT-ISO_STRATEGY_MISSING_psw_ack -comment "psw_ack waive" -tag "ISO_STRATEGY_MISSING" -filter {(Source:PinName =~ "*psw_ack*")} | 1000 cfgs | http://sccj017606.sc.intel.com:8120/builders/trunk-lp
|  |  | UFI | YES | YES | TODO | Both | Both | VCLP / P-2019.06-SP2-1 | /p/hdk/rtl/proj_tools/vc_methodology_lp/master/2.00.09.20ww03/fe | add rule filter f_clamp -rule 1801_ISO_CLAMP_VALUE_CONFLICT -AND -message "*specifying clamp value '0' conflicts with the propagated tied value '1' at lowconn of element*" | 1000 cfgs
|  |  | IDI | YES | YES | TODO | Both | Both |  |  | LogicSinkUnconnected == "True"
|  |  | CMI | YES | YES | TODO | Both | Both
|  |  | RBC_RBM | YES | YES | TODO | Both | Both |  |  | LS Strategies required??
|  |  | IDI2CMI | YES | YES | TODO | Both | Both
|  |  | CCC/ICCC | YES | YES | TODO | Both | Both
|  |  | RING Slaves | YES | YES | TODO | Both | Both

## Power Gating - Dynamic
LP | Component | Instance Type | PD Type | PD Dependency | Assertions check | Accept/Deny for power down request check | Sleep ACK check | Retention/ Save_Restore | LP Test Description | DV Infra Required | Protocol Checker Enabled | Functional/ End2End Checkers | Directed | Random | BuildBot
Dynamic LP | IDI Master Bridge | Host | Autowake or AON | Share with Host (reason: credits) | #1 Coherency Connect: Autowake CCCs or ICCCs. #2 Transaction: Autowake slave, path to slave, and return path. #3 Autowake self on access or host CC connect | Deny if requests are currently outstanding. Deny if host has coh_conn and is connected. If bridge is source of coh_conn, disconnect before Accept. If Accept, may still get requests from host and from NoC (Host or bridge sending snoops will be the ones to DENY). | Ack when credits to NoC are returned. |  | Power down all the switchable PDs (excluding Host n Bridge) and send transactions from host. Check autowake power targets on request and response path by doing data integrity check. A) an auto power down when no transactions for a while (not sure, how long ?) . B) Power down request. 1. Send sleep_req when no/outstanding transactions 2. Send transactions betweeen sleep_req and sleep_ack 3. Send transactions after sleep_ack immeditely and after some delay 4. Send multi sleep_reqs even after sleep_ack. C) Powering up 1. By send power up request and/or send transactions. | 1.) Masters need to part of QREQ/QDENY handshake in order to prevent shutdown while they are issuing requests. (IDI and CMI, but not UFI) 2.) Masters need a warm reset that cleans up their credits back to reset state. (IDI and CMI, but not UFI) 3.) Power off of masters must be temporary if end_of_test=0. (IDI+CMI+UFI) 4.) Probably need a way to induce transactors to go idle to increase chance of successful power down. (IDI+CMI+UFI) 5.) Need test when coherency_connect is done by bridge (no pins). Bridge should disconnect on its own. (IDI+UFI) | YES | YES
|  | CCC or ICCC | Autowake or AON | Share with CCC or ICCC (reason: credits, no autowake from ccc) | Same as above | Same as above | Same as above |  | Same as above |  | YES | YES
| IDI Slave Bridge | Host | Autowake or AON | Share with Host (reason: credits) | #1: Autowake U2C REQ or U2C RSP target, path to target, and response path | Deny if requests are currently outstanding. If Accept, may still get packets (relies on master bridges or host to Deny). | Ack when credits to NoC are returned |  | Power down and check wakes up when there is a power up request or transaction on path. Auto power down when there is no tranactions/power up request for a while |  | YES | YES
|  | CCC or ICCC | Autowake or AON | Share with CCC or ICCC (reason:credits) | Same as above | Same as above | Same as above |  | Same as above |  | YES | YES
|  | MBOX | Autowake or AON | Share with MBOX | Same as above | Same as above | Same as above |  | Same as above |  | YES | YES
|  | IDI2CMI/IDI2AXI | Autowake or AON | Share with IDI2CMI or IDI2AXI (reason: credits) | Only need U2C RSP logic | Same as above, but relies on master bridges only. | Same as above |  | Same as above |  | YES | YES
| UFI |  | Autowake or AON | None | #1 Coherency Connect: Autowake CCCs or ICCCs. #2 Transaction: Autowake slave, path to slave, and return path. #3 Autowake self on access or host CC connect | Deny if requests are outstanding. Deny if host has coh_conn and is connected. Before Accept, bridge coh_conn must disconnect. Before Accept, UFI link must shut down. May still get U2C Req from NoC after Accept. Once Accept is sent, should not reconnect link. | Ack when credits to NoC are returned |  | Power down all the switchable PDs (excluding Host) and send transactions from host. Check master bridge autowake and then wakes up power targets on request and response path by doing data integrity check. A) an auto power down when no transactions for a while (not sure, how long ?) . B) Power down request. 1. Send sleep_req when no/outstanding transactions 2. Send transactions betweeen sleep_req and sleep_ack 3. Send transactions after sleep_ack immeditely and after some delay 4. Send multi sleep_reqs even after sleep_ack. C) Powering up 1. By send power up request and/or send transactions. |  | YES | YES
| CMI Master Bridge | Host | Autowake or AON | Share with host (reason: credits, ISM does not go to reset) | #1 Autowake request target, path to target, and return paths (including possible forwarding return path) #2 Self autowake | Deny if outstanding transactions. Once Accept is sent, ISM handshake may start or traffic may arrive from host. PMU would have to ask Host if power down was okay, and get DENY from the host. | Ack when credits to NoC are returned |  | Power down all the switchable PDs (excluding Host n Bridge) and send transactions from host. Check autowake power targets on request and response path by doing data integrity check. A) an auto power down when no transactions for a while (not sure, how long ?) . B) Power down request. 1. Send sleep_req when no/outstanding transactions 2. Send transactions betweeen sleep_req and sleep_ack 3. Send transactions after sleep_ack immeditely and after some delay 4. Send multi sleep_reqs even after sleep_ack. C) Powering up 1. By send power up request and/or send transactions. |  | YES | YES
|  | CCC/ICCC | Autowake or AON | Share with CCC or ICCC (reason: credits, ISM does not go to reset, no autowake in ccc) | Same as above | Same as above | Same as above |  | Same as above |  | YES | YES
|  | IDI2CMI | Autowake or AON | Share with IDI2CMI (reason: credits, ISM does not go to reset, no autowake from IDI2CMI) | Same as above | Same as above | Same as above |  | Same as above |  | YES | YES
| CMI Slave Bridge | Host | Autowake or AON | Share with host (reason: credits, ISM does not go to reset) | None | None | Ack when credits to NoC are returned |  | Power down and check wakes up when there is a power up request or transaction on path. Auto power down when there is no tranactions/power up request for a while |  | YES | YES
| IDI2CMI |  | Autowake or AON | Share with SB and MB (reason: credits, ISM does not go to reset) | None | None | None |  | Same as above |  | YES | YES
| IDI2AXI |  | Autowake or AON | Share with SB and MB (reason: credits, ISM does not go to reset) | None | None | None |  | Same as above |  | YES | YES
| CCC/ICCC |  | Autowake or AON | Share with MB. Share with IDIS. (see bridge requirements) | None | Deny if coherency connected. Deny if ICCC cache is not flushed/disabled. | None |  | Same as above |  | YES | YES
| RBC | Normal | Autowake or AON | Share with RBM (reason: see RBM) | None | Deny if requests are oustanding or if interfaces don't allow shutdown |  |  | Send transaction/power up request from any master and Check autowake RBC and self wake RBM and wakes up power targets on request and response path by doing data integrity check. A) an auto power down when no transactions for a while (not sure, how long ?) . B) Power down request. 1. Send sleep_req when no/outstanding transactions 2. Send transactions betweeen sleep_req and sleep_ack 3. Send transactions after sleep_ack immeditely and after some delay 4. Send multi sleep_reqs even after sleep_ack. C) Powering up 1. By sending power up request and/or send transactions. | RBC_RBM and IOSFSB on same power domain | YES | YES
| RBM | Normal | Autowake or AON | Share with RBC (reason: no autowake from RBC) | #1 Auto-wake targets and paths to and from. #2 Self-autowake | Deny if outstanding transactions. | Ack when credits to NoC are returned |  | Same as above |  | YES | YES
| Ring Slaves | Any | Autowake or AON | Share with Ring (ring is always in same power domain) | Autowake ring master, RBC/RBM, and path to RBC/RBM. | None | Ack when credit are returned | YES | Same as above |  | YES | YES
| BIST Controller |  | Don't Care | None | Autowake all BistGen/BistCheck and all routes tested by BIST flows. | Deny if BIST sequence is in progress. Deny if BIST controller is set up to run BIST periodically | None |  | Send transaction/power up request from any master and Check autowake power targets on request and response path by doing data integrity check. A) an auto power down when no transactions for a while (not sure, how long ?) . B) Power down request. 1. Send sleep_req when no/outstanding transactions 2. Send transactions betweeen sleep_req and sleep_ack 3. Send transactions after sleep_ack immeditely and after some delay 4. Send multi sleep_reqs even after sleep_ack. C) Powering up 1. By sending power up request and/or send transactions. |  | YES | YES

## Status
Techniques
Technologies
Standards
Stages
Features
Protocols
Power Aware
Tools

## Open Issues
Do we need LS strageies or wave off ?
Are we going to use ZERO/ONE/DUAL pin retention cell ?

## Reference
Low Power Spec
https://wiki.ith.intel.com/display/EN/Low+Power+Spec+-+Golden
Here is the broad LP spec from AMBA product
svn://sccj017606.sc.intel.com/trunk/doc/drafts/low-power-spec-v2.docx
This document has Joe’s thoughts on IDI LP
svn://sccj017606.sc.intel.com/doc/ccNoC/Coherency%20Power%20Management.docx
This has a section on LP for RBC/RBM
svn://sccj017606.sc.intel.com/trunk/doc/drafts/RBC-RBM.docx
Fine Grain Power Targets
https://wiki.ith.intel.com/display/EN/Fine+Grain+Power+Targets

## MSS1 Matrix (hidden)
I/T | BISS0 LINK (OCP) | BISS1 LINK (OCP) | BPSS0 DATA (OCP) | BPSS1 DATA (OCP) | BPSS CFG (OCP) | DL PDB (OCP) | MSS1 AXI (AXI) | MSS ACP (AXI) | MSS DMAC (AXI) | MSS PCU (OCP) | MTCU NR (OCP) | PPU CFG (OCP) | PPU DATA (AXI) | UL PDB (OCP) | UPC (AXI)
BISS0 LINK (OCP)
BISS1 LINK (OCP)
BPSS0 DATA (OCP)
BPSS1 DATA (OCP)
BPSS CFG (OCP)
MSS1_AXI (AXI)
MSS CPU M0 (AXI)
MSS DMAC (AXI)
MSS PCU (OCP)
MTCU NRTDB (OCP)
MTCU NR (OCP)
PPU CFG (OCP)
PPU DATA (AXI)
SCHP0 (OCP)
SCHP1 (OCP)
UPC (AXI)
Total | 105 cases | x2 | 210
Ref: