## Summary
NetSpeed Release Checklist Summary
| Orion-NSIP-15.03.2-lx |  |  | Comments / Notes regarding branch
| Trunk SVN version | NA |  | This is the version from which branch < > was created.
| Branch SVN version | Revision: 37331 | https://www.assembla.com/code/netspeed_noc/subversion/nodes/37870/releases/15.03/Orion-NSIP-15.03.2-lx_info/svn_info | This is the version from which the last noc_stable was promoted.
| Category | Owner | Status (%)
| Release database checks | Eric | 0
| License & Beta Testing | Anush | 0
| Documentation | Anush | 0
| HW Verif | JJ (Gemini) Won(AMBA) Yogesh(NSIP) | 0
| HW Design | Joji | 0
| CAD Tools | Rajesh | 0
| NocStudio SW Design | Sailesh / Eric | 0
| NocStudio SW Verif | Bhumesh | 0
Optional: | Customer Specific Tapeout | Joe | 0
Products
Orion
Orion-AMBA
Orion-NSIP
Gemini
All
| Key Customer Information: | <customer name>
<customer project name>
<Netspeed product>
<tapeout date>
<tapeout date>
Notes:
Interrupt Release to Ericsson to address Engineering bugs:
The following bugs are fixed:
· NS 147 – Ability to redirect output to a file
· NS 167 – NocStudio takes a long time to exit the run phase
· NS 172 – Simulator transmits more than 100% of expected traffic
· NS 178 – Core dump on reading the json file
· NS 187 – Cmodel memory leak
Tests Run:
1) Promotion for hw sanity tests
2) Ericsson sanity testbench
3) Sw regresions
sanity TB now with the license file and check the tarball
Owner: Yogesh
results: Verified customer configs and they work fine with generic license file
| SW regressions: | owner: Bhumesh
Ran selftests and Script tests, all are passing. See summary below:
Selftests:
[----------] Global test environment tear-down
[==========] 1667 tests from 38 test cases ran. (291552 ms total)
[ PASSED ] 1667 tests.
YOU HAVE 7 DISABLED TESTS
Script Tests:
[----------] Testcase C1 & C2 statistic
[==========] 377 test(s) total
[==========] 377 test(s) ran (523000 ms)
[ PASSED ] 377 tests
c-Model tests: All 13 passed.

## Database
Summary
Overall Status (%)
0
Task | type | Release Database Checks | Products | Owner | Status (%) | Comments
1 | release NS bin | Netspeed headers are properly generated | All | Eric | 0 | Needs to automate and based on BW | move to sw verif tab?
2 | release NS bin | NocStudio Customer headers properly generated | All | Eric | 0 | Needs to automated
3 | release NS bin | NocStudio tutorial & Examples in the Help | All | Nishant | 0
4 | NS trace | Try trace file with modified trace as customer would and feed back into NocStudio and RTL(streaming only for now). | Orion-NSIP | Eric | 0 | check trace file is generated by NS check NS can read customer trace file and run perf sim | move to sw verif tab?
5 | release branch | NocStudio is identical in noc-dev and noc-stable in branch at release time | All | Eric | 0 | check that last Noc Studio commit was in the promotion
6 | alpha testing | Check quality of release tarball - try examples and check known customer configs | All | Eric | 0
7 | release checklist | Release Checklist filled out and checked into Branch | All | Gloria | 0
8 |  | Documents verified to be correct in release area | All | Ranjeet | 0 |  | dup
9 |  | Description and default settings in Integration Spec reviewed | All | Kate | 0 | Separate amba and NSIP | move to customer facing tab?
10 | release NS bin | Review NocStudio settings(init.txt) | All | Eric | 0 | Goes away soon | Eric - no longer needed
11 | release NS bin | NocStudio Model Sanity runs clean | All | Eric | 0 |  | dup - external sanity
12 | release NS bin | Multiple binaries generate same RTL | All | Eric & Kiran | 0 | There is only one binary that generates rtl | before internal vs external bin of NS - now it's all the same so NA
7 | Sanity Testbench | External Sanity Testbench pass: | All | Ben |  |  | dup
8 | Sanity Testbench | Make sure sanity run_test.sh includes waveform dump in command by default. Check that waveform is visible even in presence of encryption and Sanity Testbench is released |  |  | 0 | Check again | dup
9 | Sanity Testbench | Run released NocStudio binary with filtered NocWeaver random configs and check that, |  |  | 0 |  | dup
10 | Sanity Testbench | Generated RTL is identical between internal binary and external binary |  |  | 0 |  | dup
11 | Sanity Testbench | Released RTL & checkers identical between internal and customer nocstudio binaries |  |  | 0 | not so critical | dup
12 | Sanity Testbench | Sanity is verified to run both with checker knobs ON and OFF, default setting should be Router checker OFF, E2E ON, Bridge ON, Regbus checkers ON, |  |  | 0 | router checker default off since run slow - why | dup
13 | Sanity Testbench | clock generation in the sanity bench like ratio sync, async crossing is exercised |  |  | 0 | verif team | dup
14 | Sanity Testbench | run customer configs |  |  |  |  | dup
15 | Sanity Testbench | Sanity tests with NocStudio generated traces for rb_ahb, etc ACELM, AXI4, AXI3, AHB, APB, regbus run cleanly in release directory |  |  | 0 | Verif | dup

## License, Beta Testing
Summary
Overall Status (%)
0
Task | Type | Customer facing checks | Products | Owner | Status (%) | Comments
1 | location | Release files (tar, docs) verified to be correct in release area | All | Anush | 0
2 | license | License file created for release | All | Anup | 0
3 | beta testing | Generated header from NocStudio always generates correct customer name | All | Ono | 0
4 | beta testing | Check quality of release tarball - try all example configs | All | Eng Team (Gloria TBD) | 0
5 | beta testing | Check quality of release tarball - try known customer configs | All | Ono | 0
6 | license | FlexLM default license file per product approved - made available for alpa & beta testing | All | Support Team (Anush) Eng Team (Gloria TBD) | 0
7 | Bugs - customer | Check if all the customer bugs are addressed in the release | All | Support Team (Anush) | 0 |  | moved from database tab

## Documentation
Summary
Overall Status (%)
0
Task | Type | Customer facing checks | Products | Owner | Status (%) | Comments
1 | doc | NocStudio User Manual - Orion NSIP: Content (Accuracy, Completness) | Orion-NSIP | Joe/Sailesh/JJ | 0 | Content needs to be present 2 weeks before release
2 | doc | NocStudio User Manual - Orion AMBA (Accuracy, Completness) | Orion-AMBA | Joe/Sailesh/JJ | 0 | Content needs to be present 2 weeks before release
3 | doc | NocStudio User Manual - Gemini (Accuracy, Completness) | Gemini | Joe/Sailesh/JJ | 0 | Content needs to be present 2 weeks before release
4 | doc | NocStudio Tutorial - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Sailesh | 0 | Content needs to be present 2 weeks before release
5 | doc | NocStudio Tutorial - Orion AMBA (Accuracy, Completness) | Orion-AMBA | Sailesh | 0 | Content needs to be present 2 weeks before release
6 | doc | NocStudio Tutorial - Gemini (Accuracy, Completness) | Gemini | Sailesh | 0 | Content needs to be present 2 weeks before release
7 | doc | IP Integration Spec - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Kate | 0 | Content needs to be present 2 weeks before release
8 | doc | IP Integration Spec - Orion AMBA (Accuracy, Completness) | Orion-AMBA | Kate | 0 | Content needs to be present 2 weeks before release
9 | doc | IP Integration Spec - Gemini (Accuracy, Completness) | Gemini | Kate | 0 | Content needs to be present 2 weeks before release
10 | doc | NocStudio C++ Model - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Sailesh | 0 | Content needs to be present 2 weeks before release
11 | doc | Physical Design Spec - Orion AMBA (Accuracy, Completness) | Orion-AMBA | Rajesh | 0 | Content needs to be present 2 weeks before release
12 | doc | Physical Design Spec - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Rajesh | 0 | Content needs to be present 2 weeks before release
13 | doc | Physical Design Spec - Gemini (Accuracy, Completness) | Gemini | Rajesh | 0 | Content needs to be present 2 weeks before release
14 | doc | NocStudio Cookbook - Gemini (Accuracy, Completness) | Gemini | Joe | 0 | Content needs to be present 2 weeks before release
15 | doc | Release Notes - NSIP (Accuracy, Completness) | Orion-NSIP | Gloria | 0 | Content needs to be present 2 weeks before release
16 | doc | Release Notes - AMBA (Accuracy, Completness) | Orion-AMBA | Gloria | 0 | Content needs to be present 2 weeks before release
17 | doc | Release Notes - Gemini (Accuracy, Completness) | Gemini | Gloria | 0 | Content needs to be present 2 weeks before release
18 | doc | Router Microarch Spec (Accuracy, Completness) | All | Joji | 0 | Content needs to be present 2 weeks before release
19 | doc | Streaming Interface Protocol & Bridge Microarch Spec - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Rajesh | 0 | Content needs to be present 2 weeks before release
20 | doc | AMBA Protocol Support (Accuracy, Completness) | All | Joe | 0 | Content needs to be present 2 weeks before release
21 | doc | New Features and props/command change document (Accuracy, Completeness) | All | Kiran | 0
22 | doc | NocStudio User Manual - Orion NSIP: Formatting (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
23 | doc | NocStudio User Manual - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
24 | doc | NocStudio User Manual - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
25 | doc | NocStudio Tutorial - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
26 | doc | NocStudio Tutorial - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
27 | doc | NocStudio Tutorial - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
28 | doc | IP Integration Spec - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
29 | doc | IP Integration Spec - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
30 | doc | IP Integration Spec - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
31 | doc | NocStudio C++ Model - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
32 | doc | Physical Design Spec - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
33 | doc | Physical Design Spec - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
34 | doc | Physical Design Spec - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
35 | doc | NocStudio Cookbook - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
36 | doc | Release Notes - NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
37 | doc | Release Notes - AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
38 | doc | Release Notes - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
39 | doc | Router Microarch Spec (Look&Feel, Versioning, etc.) | All | Support Team (Anush) | 0
40 | doc | Streaming Interface Protocol & Bridge Microarch Spec - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
41 | doc | AMBA Protocol Support (Look&Feel, Versioning, etc.) | All | Support Team (Anush) | 0
42 | doc | New Features and props/command change document (Look&Feel, Versioning, etc) | All | Support Team (Anush) | 0
43 | doc - App Notes | Qos Rate Limiter | All | Support Team (Anush) | 0
44 | doc - App Notes | RWC (Ericsson only) | All | Support Team (Anush) | 0
45 | location | Documents verified to be correct in release area | All | Support Team (Anush) | 0

## SW Design
Summary
Overall Status (%)
0
Task | Type | SW design | Products | Owner | Status (%) | Comments
1 | review | All command changes highlighted & approved | All | Sailesh/Eric | 0
2 | doc | help menu feature description in place | All | Sailesh | 0
3 | testing | deep testing | All | Sailesh | 0
4 | review | code reviewed - prevent out of range index, null pointer access, and memory corruption | All | Sailesh | 0
5 | review | memory profiling done on all code including the c model API - prevent memory leaks | All | Sailesh | 0
6 | metrics: Perf | Metrics: record perf on NocStudio bench_noc command output and compare with previous releases | All | Sailesh | 0 | 20% throughput reduction is waived | moved from database tab
7 |  |  | All | Sailesh | 0
8 |  |  | All | Sailesh | 0

## SW Verif
Summary
Overall Status (%)
0
Task | Type | NocStudio SW Verif Checks | Products | Owner | Status (%) | Comments
1 |  | Test all new quarterly release features | All | Kiran | 0 | Test Writing for 15Q1 features is complete based on Aha and Trello lists. Running them repeatedly is an on-going process.
2 |  | Monkey test for GUI | All | Cang | 0 | Only InfoNam GUI team does all the GUI testing
3 |  | Run all SW Verif test suites and make sure all of them pass. | All | Kiran | 0
4 |  | Run all tests that are part of selftest | All | Bhumesh | 0 | All these are run with each promotion run
5 |  | Run all independent selftests (BiridgeTest*, MathUtil*, etc) | All | InfoNam | 0 | BridgeTest*:MathUtil*:Range*:StringHandling*:Math*:SizeConversion*:GridTestGet*:Packet_Test*:RandomTest*:Alias_Test*:Host_Props*:DepUndep*:Default_Props*:Mesh_Props*:Range_test*:Bridge_Props*:Traffic_test*:link_opt*:Link_Props*:Latency_Test*:Trace_Files*:WidthConversion*:ScriptTest*:Rate_Test*
6 |  | Run all C0 OTests | All | InfoNam | 0 | 15 tests from C0 tests are disabled. Total 1678, 7 disabled are waived, 15 are yet to be debugged.
7 |  | Run all C0 LongOTests | All | InfoNam | 0 | LongOTests/OTest.*
8 |  | Run all C0 ReleaseExampleTests | All | InfoNam | 0 | ReleaseExampleTests/OTest.*
9 |  | Run all C0 RegressionTests | All | InfoNam | 0 | RegressionTests/OTest.*
10 |  | Run all PerfCSVTests | All | InfoNam | 0 | PerfCSVTests/CSVCheck.*
11 |  | Run all gold file tests | All | InfoNam | 0 | OFileTests/FileChk.*
12 |  | Run all script tests | All | InfoNam | 0
13 |  | Run all C1 and C2 short script tests | All | InfoNam | 0 | Under otests/script
14 |  | Run all C1 and C2 long script tests | All | InfoNam | 0 | Under otests/long_script
15 |  | Run all CSV property tests | All | InfoNam | 0 | Under otests/script/csv_files/csv_property_test.pl
16 |  | Run all C model tests | All | InfoNam | 0 | Under otests/c_model_tests
17 |  | Review the property testing CSV files along with verif, dev, and release committee | All | Gloria | 0 | First a release committee (Gloria, SW dev team, SW verif team, Marketing team) should review all the CSV files and determine what are valid commands and props and their values.
18 |  | Cross Platform Testing | All | Kiran | 0 | Completed for NSIP, used NSIP license.dat files, yet to do it with AMBA.
19 |  | All Bugzilla bugs and Assembla tickets are fixed and closed. | All | Bhumesh | 0 | All the open Assembla tickets relevant for the release tracked in one Bugzilla bug Once all the relevant Assembla tickets are fixed and closed the tracking Bugzilla bug can be closed . There is no 1503 release blocking ticket open in Assembla or Bugzilla.
20 |  | Review disabled tests in soft tests | All | Bhumesh | 0

## HW Design
Summary
Overall Status (%)
0
Task | Type | HW Design | Products | Owner | Status (%) | Comments | lint clean | new qtr features ok | rtl file list | comments clean | file header ok | bugs fixed | timing ok | area ok | auto emacs ok | no tabs
1 | module | ACE Master | Orion-AMBA | Joji | 0
2 | module | ACE Slave | Orion-AMBA | Joji
3 | module | AHB Master | Orion-AMBA | Sandip
4 | module | AHB Slave | Orion-AMBA | Sandip | 0
5 | module | APB Slave | Orion-AMBA | Rimu | 0
6 | module | AXI-lite Slave | Orion-AMBA | Rimu | 0
7 | module | NSIP Bridge | Orion-NSIP | Rajesh | 0
8 | module | Regbus - Regbus Master (RBM) | All | Jaya | 0
9 | module | Regbus - Ring Master | All | Joji
10 | module | Regbus -Ring Slave | All | Jaya
11 | module | Regbus - Tunnel | All | Jaya
12 | module | Regbus - APB Master | All
13 | module | clk gating | All | Sandip | 0
14 | module | Router | All | Joji | 0
15 | wrapper | AXI4 & AXI3 Master | Orion-AMBA
16 | wrapper | AXI-lite Master | Orion-AMBA
17 | wrapper | AXI4 & AXI3 Slave | Orion-AMBA
18 | wrapper | CCC | Gemini
19 | wrapper | DVM | Gemini
20 | wrapper | NCB | Gemini
21 | wrapper | LLC | Gemini

## HW Verif
Summary
| 3 |  |  |  |  | Overall Status (%)
0
Task | 3 | Type | HW Verification | Products | Owner | Status (%) | Comments
1 |  | Bugs | Release Block Bug CLOSED - All Bugs reviewed and verified to be 'CLOSED' or 'CIAR' - Verified Fixed and not just Resolved Fixed | All | Gloria | 0
2 |  | coverage | NoC level i/o pins toggle coverage on Superconfig | All | JJ | 0 | Not done for Q1
3 |  | coverage | signoff Coverage (Toggle / Functional / Expression) | All | Won | 0
4 |  | coverage | signoff parameter coverage | All | Won | 0
5 |  | regression setup | NocWeaver randomization knobs reviewed for NocStudio range and parameters | All | JJ | 0 | Not done for Q1
6 |  | regression setup | Check for all commented out tests in regress list | All | JJ | 0
7 |  | regression setup | New weights for nocweaver are enabled and exercised | Orion | ? | 0
8 |  | regression setup | Review that no checker is unexpectedly disabled in the internal environment. | All | JJ | 0
9 |  | checkers | Runs verified with Cadence Protocol checker AXI, AHB and APB | All | JJ | 0
10 |  | checkers | Benchmark simulation slow-down with checkers on versus off. | All | JJ | 0
11 |  | checker - Streaming | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-NSIP | Yogesh | 0
12 |  | checker - Router | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | Yogesh | 0
13 |  | checker - AHB | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-AMBA | Shan | 0
14 |  | checker - AXI | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-AMBA | Kate | 0
15 |  | checker - APB | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-AMBA | Vishnu | 0
16 |  | checker - Regbus | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | JJ | 0 | NSIP and AMBA separate
17 |  | checker - Clock Gating | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | JJ | 0
18 |  | checker - end2end | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | JJ | 0
19 |  | checker - global coherency | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0
20 |  | checker - CCC | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0
21 |  | checker - DVM | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0
22 |  | checker - NCB | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0
23 |  | checker - LLC | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0
24 |  | any LP checkers? |  | Orion-AMBA | Vishnu | 0
25 |  | HW regressions (AMBA) | axi full regression | All | JJ | 0
26 |  | HW regressions (AMBA) | nightly | All | JJ | 0
27 |  | HW regressions (AMBA) | VCS axi full regression - reviewed build log and simulation logs and pass | All | JJ | 0
28 |  | HW regressions (AMBA) | Mania (sanity TB) | All | JJ | 0
29 |  | HW regressions (AMBA) | Regbus (addr sweep, sweep, pingster) | All | JJ | 0
30 |  | HW regressions (AMBA) | Regbus Tunnel | All | JJ | 0
31 |  | HW regressions (AMBA) | nemesis (nocweaver) | All | JJ | 0
32 |  | HW regressions (AMBA) | external sanity: includes tarball check on customer configs | All | JJ | 0
33 |  | HW regressions (AMBA) | tarball - run examples & test customer configs | All | JJ | 0
34 |  | HW regressions (NSIP) | Nike (randoms) | All | Yogesh | 0
35 |  | HW regressions (NSIP) | VCS regressions - reviewed build log and simulation logs and pass | All | Yogesh | 0
36 |  | HW regressions (NSIP) | Regbus (sweep) | All | Yogesh | 0
37 |  | HW regressions (NSIP) | Regbus (pingster) | All | Yogesh | 0
38 |  | HW regressions (NSIP) | external sanity | All | Yogesh | 0
39 |  | HW regressions (NSIP) | new RWC nocweaver | All | Yogesh | 0
40 |  | HW regressions (NSIP) | tarball - run examples & test 2 customer config + 7 ex configs | All | Yogesh | 0
41 |  | HW and SW tests | NEW TESTS For new features & bug fixes | All | JJ | 0
42 |  | regressions | promotion | All | Kate | 0
43 |  | sanity - UVM | UVM customer testbench | Orion-AMBA | Yogesh | 0
44 |  | module level regressions | router | Gemini | Yogesh | 0
45 |  | module level regressions | AHB | Gemini | Kate | 0
46 |  | module level regressions | APB | Gemini | Vishnu | 0
47 |  | module level regressions | CCC | Gemini | JJ | 0
48 |  | module level regressions | DVM | Gemini | JJ | 0
49 |  | module level regressions | NCB | Gemini | JJ | 0
50 | verif multiNOC | Multi NOC Compile | All | All | Ben | 0
51 |  | WHAT? | Max Error between Model and RTL is < 10% | All | Eric | 0
52 |  | WHAT? | Internal vs External binary produced NoCs compared over 500 mix br configs | Orion | Ninad | 0
|  |  | todo: add Gemini verif |  | JJ
todo: add low power verif
|  | regression setup | x propagation randomized - multivoltage |  | Vishnu
|  | regression setup | async clks and ratio clks randomized- DVFS |  | Vishnu
27 |  | Sanity | Sanity bench passes with VCS for all benches | All | Kate | 0 |  | dup
28 |  | sanity | Sanity Bench components (Ambaxtor, Regxtor, AHBxtor) and slave models, aHB and APB are cleaned up. | All | JJ | 0 |  | dup
2 |  | checkers | Runs verified with all internal bridge and E2E checkers | All | JJ | 0 |  | dup
10 |  | checkers | No unnecessary in-house checkers are included. Cleanly partition files and code and make sure only external files are included. | All | Kate | 0 |  | dup
29 |  | VCS | Review waived warnings for build log, simulation log for VCS | All | JJ | 0 |  | duplicate with new addition
Reference Data:
Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line
9 |  | regressions | Nemesis runs reviewed for any error, permission and new features | All | ? | 0
10 |  | regressions | All Regressions are run : Nightly, Release, Regbus, Streaming, Promotion, CCC, axi, axi_long, DVM, Router, APB | All | JJ | 0 | Router run by Yogesh, APB by Vishnu | duplicate with new addition
11 |  | regressions | Mixed bridge sanity (inc regbus) passes internal flow for random 500 configs, new features Mania | Orion | Ninad | 0 |  | duplicate with regressions?
12 |  | regressions | Mixed bridge sanity (inc regbus) passes external flow for 1000 configs external sanity | Orion | Ninad | 0 |  | duplicate with regressions?
13 |  | regressions | Run a set of 50 configs with router checker enabled. | Orion-NSIP | Yogesh | 0 | Not Done for Q1 | duplicate with regressions?
14 |  | regressions | (NocWeaver) All agents: axi4m, axi3m, apb, ahblm, ahbls, axi4mls, stream(if applicable), acelm | All | Ben | 0 |  | duplicate with regressions?
15 |  | regressions | (NocWeaver) At least one ahb config should have all 16 slave regions. | All | Ben | 0 |  | duplicate with regressions?
16 |  | regressions | (NocWeaver) At least one apb config should have all 16 slave regions | All | Ben | 0 |  | duplicate with regressions?
17 |  | regressions | (NocWeaver) Both little endian and big endian for both ahblm and ahbls. | All | Ben | 0 |  | duplicate with regressions?
18 |  | regressions | (NocWeaver) w/ and w/o regbus | All | Ben | 0 |  | duplicate with regressions?
19 |  | regressions | (NocWeaver) w/ and w/o async | All | Ben | 0 |  | duplicate with regressions?
20 |  | regressions | (NocWeaver) w/ and w/o clock gating | All | Ben | 0 |  | duplicate with regressions?
21 |  | regressions | (NocWeaver) w/ and w/o data interleaving | All | Ben | 0 |  | duplicate with regressions?
22 |  | regressions | (NocWeaver) All combinations of protection bits, security bits(addr[5:0]) which will affect mania traffic | All | Ben | 0 |  | duplicate with regressions?
23 |  | regressions | (NocWeaver) w/ and w/o overrides | All | Ben | 0 |  | duplicate with regressions?
24 |  | regressions | (NocWeaver) min addr and max addr width | All | Ben | 0 |  | duplicate with regressions?
25 |  | regressions | (NocWeaver) All data widths supported | All | Ben | 0 |  | duplicate with regressions?
26 |  | regressions | Regressions run and pass with checkers and knobs on/off | All | ? | 0 | This is not done for Q1 | duplicate with regressions?
Note on D30: Author: old tests that caught failure a lot of tests and a lot of configs
Note on D31: Author: old tests that caught failure a lot of tests and a lot of configs
Note on D32: Author: old tests that caught failure a lot of tests and a lot of configs
Note on D36: Author: about 1000 configs - test new features
Note on D45: Author: example config ericsson config tutorials external tb - builds run and test

## CAD Tools
Summary
Overall Status (%)
0
Task | Type | Block | CAD Tools | Products | Owner | Status (%) | Comments
1 | timing | Router | Router timing | All | Rajesh | 0
2 |  |  | tb_str200_ly1_routersizes | All | Rajesh | 0
3 | timing | Streaming | Streaming Bridge timing of | Orion-NSIP | Rajesh | 0
4 | customer config |  | Customer config | Orion-NSIP | Rajesh | 0
5 |  |  | Example | Orion-NSIP | Rajesh | 0
6 | synthesis - RC |  | Synthesis logs reviewed, no errors. Warnings/exceptions are documented. | Orion-NSIP | Rajesh | 0
7 | synthesis - DC |  | DC/DCT run on Edna config | Orion-NSIP | Rajesh | 0
8 | Lint |  | Lint (HAL & Quartus) - Daily regressions | Orion-NSIP | Rajesh | 0
9 |  |  | tb_str3_ly8_bridge_codecov | Orion-NSIP | Rajesh | 0
10 |  |  | tb_str9_ly6_priority | Orion-NSIP | Rajesh | 0
11 | synthesis - FPGA |  | FPGA synthesis (Quartus) - Customer config | Orion-NSIP | Rajesh | 0
12 | synthesis - FPGA |  | FPGA synthesis (Vivado) - Customer config | Orion-NSIP | Rajesh | 0
13 | LEC |  | LEC on all synthesis | Orion-NSIP | Rajesh | 0
14 | synthesis - emulation |  | Emulator compile | Orion-NSIP | Rajesh | 0
15 | timing | AMBA | AMBA timing | Orion-AMBA | Rajesh | 0
16 |  |  | tb_axi5_slv6_syn_typ | Orion-AMBA | Rajesh | 0
17 |  |  | tb_axi5_slv6_syn_extrm | Orion-AMBA | Rajesh | 0
18 |  |  | tb_axi6_slv5_amba_supcfg_synth | Orion-AMBA | Rajesh | 0
19 | synthesis - RC |  | Synthesis logs reviewed, no errors. Warnings/exceptions are documented. | Orion-AMBA | Rajesh | 0
20 | synthesis - DC |  | DC/DCT run on a config | Orion-AMBA | Rajesh | 0 | 2 warnings that can be waived
21 | Lint |  | Lint (HAL & Quartus) - Daily regressions | Orion-AMBA | Rajesh | 0
22 |  |  | tb_axi5_slv5_amba_supcfg_lint | Orion-AMBA | Rajesh | 0
23 |  |  | tb_axi6_slv5_amba_supcfg_synth | Orion-AMBA | Rajesh | 0
24 |  |  | tb_axi9_ahblm4_axi3m1_axi4lm2_axi4m2_slv5_axi4ls3_ahbls2_ly1_regbus_addcomp_cg_multi_clock_eco_486421713_0306 | Orion-AMBA | Rajesh | 0
25 |  |  | tb_axi4_axi4m4_slv5_axi3s3_axi4s1_ly2_regbus_tunnel_addcomp_cg_multi_clock_eco_1336040710_0305 | Orion-AMBA | Rajesh | 0
26 |  |  | FPGA synthesis (Quartus) | Orion-AMBA | Rajesh | 0
27 |  |  | Customer Config | Orion-AMBA | Rajesh | 0
28 |  |  | Customer Config | Orion-AMBA | Rajesh | 0 |  | dup
29 | synthesis - FPGA |  | FPGA synthesis (Vivado) | Orion-AMBA | Rajesh | 0
30 |  |  | Customer Config | Orion-AMBA | Rajesh | 0 |  | dup
31 |  |  | Customer Config | Orion-AMBA | Rajesh | 0 |  | dup
32 | LEC |  | LEC on all synthesis | Orion-AMBA | Rajesh | 0
33 | synthesis - emulation |  | Emulator compile | Orion-AMBA | Rajesh | 0
34 | synthesis - RC |  | Verified that RC synthesis scripts run in release directory | All | Rajesh | 0
35 | synthesis - DC |  | Verified that DC synthesis scripts run in release directory | All | Rajesh | 0
36 | synthesis - RC |  | Synthesis for Multi-Clock AMBA and Streaming Noc's - check SDC files, Hier and Top (RC and DC) | All | Rajesh | 0
37 | CDC |  | CDC Checks for async clock crossings and other clks | All | Sandip | 0
38 | IPXACT |  | IPXACT Qual | All | Rajesh | 0
39 | Metrics |  | Physical Metrics generated, reviewed and posted | All | Rajesh | 0 | Metrics: record area, instances, freqency on synthesis output and compare with previous releases
40 |  |  | Metrics: record area, instances, freqency on synthesis output and compare with previous releases | All | Rajesh | 0 |  | dup
41 | DEF |  | DEF File correctness | All | Rajesh | 0
42 | low power |  | CPF File correctness | All
43 | low power |  | UPF File correctness | All
44 | Lint - Spyglass |  | Lint - Spyglass | Gemini
45 | CDC - Spyglass |  | CDC - Spyglass | Gemini
46 | timing |  | timing | Gemini
47 | synthesis - RC |  | synthesis - RC | Gemini
48 | synthesis - DC |  | synthesis - DC | Gemini
49 | Lint |  | Lint | Gemini
50 | synthesis - FPGA |  | synthesis - FPGA | Gemini
51 | LEC |  | LEC | Gemini
52 | synthesis - emulation |  | synthesis - emulation | Gemini

## Customer TO
Summary
Overall Status (%)
|  | ALL checks below - use customer configuration and run on customer branch |  |  | 0
Task | Type | Customer Specific Tapeout Checks | Products | Owner | Status (%) | Comments
1 |  | customer TAPEOUT Config finalized | All | Joe | 0 | checked into agatha branch in ace noc config directory - will change to fix timing by adding pipeline stages in noc studio input
2 |  | Coverage - line coverage reviewed/approved | Gemini | Joe | 0 | <enter % cov>
3 |  | Coverage - functional coverage reviewed/approved | Gemini | JJ | 0 | <enter % cov>
4 |  | gatesim passes (pick 10-100 tests to give best coverage of regbus, network, etc. & external sanity testbench) | Gemini | Rajesh | 0 | make sure get out of reset properly and can run a test note: pick a good list of tests to cover most func of chip: ex. 10-100 tests to cover reg bus, connectivity, external sanity tb test, etc.
5 |  | CCC register tests pass | Gemini | Kate | 0
6 |  | DVM register tests pass | Gemini | Dasa | 0
7 |  | general noc register test pass | Gemini | Dasa | 0
8 |  | all bugs ported | Gemini | Joe | 0 | bug # 2975
9 |  | port trunk verif files to old branch | Gemini | JJ | 0
10 |  | port trunk synthesis files to old branch | Gemini | Rajesh | 0
11 |  | customer timing issues fixed | Gemini | Joe/Joji | 0
12 |  | ratio clk module ok and crossing has instances reviewed/approved | Gemini | Joe | 0 | no special contraints need to be passed to customers review ratio clk module and where it's used
13 |  | lint clean | Gemini | Joe/Joji/Jaya/Rajesh | 0 | mask tab issue
14 |  | synthesis log clean (includes DFT issues) & synthesis contraint file reviewed | Gemini | Joe/Joji/Jaya/Rajesh | 0
15 |  | cherry pick hw changes from trunk to agatha branch | Gemini | Joe/Joji/Jaya/Rajesh | 0 | Joji done; Jaya done; Joe done (no clk gating, APB, AHB) - next Rajesh streaming bug note: check by diff'ing files line by line and annotate diff file with comments on why or why not port code into branch
16 |  | multicycle paths reviewed/approved (async/sync) | Gemini | Rajesh | 0 | NA
17 |  | async signals like reset, interrupts reviewed/approved | Gemini | Joe/Joji | 0 | NA: reset is just a pin - sync reset flops - async assert and sync deassert interrupt are sync with source block note: customer will OR the different interrupts sourced from diff clk domains and route it to their interrupt controller block
18 |  | CDC | Gemini | Sandip | 0 | done before on agatha branch - next: need to redo now note: run with right config with max clk scenarios not cover ratio clks since it's synchronous
19 |  | physical checklist - LEC, IPXACT, etc. | Gemini |  | 0
20 |  | emulation | Gemini | Rajesh | 0 | previous branch emulation was done
21 |  | clk ratio diags pass | Gemini | Joe | 0 | done with ratio clk tests and clk training testing
22 |  | review false paths | Gemini | Rajesh | 0 | NA
23 |  | reset spec reviewed/approved | Gemini | Joe/Joji/jim | 0 | reset different from new reset spec - reset signal goes to each block so up to agatha to assert long enough clks and deassert at same time
note: adding debug regs would change addr map and it would need a new NS bin - not good to do at this point
note: hold time - only check after clk tree in place and get back annotated timing
Key Info:
|  | Intel 14nm Fin Fet - target 750 MHz | should be more than 30% faster than our synthesis using the 28nm library
clk gating is OFF
reg bus is ON

## OLD - Customer Facing
Summary
Overall Status (%)
0
Task | Type | Customer facing checks | Products | Owner | Status (%) | Comments
1 | doc | NoC NSIP Programmers Reference Manual generation is verified correct | Orion-NSIP | Anush/Ono/Alex/William/YT | 0
2 | doc | NoCStudio NSIP Users Manual reviewed | Orion-NSIP | Anush/Ono/Alex/William/YT | 0
3 | doc | Orion NSIP IP Integration Spec reviewed | Orion-NSIP | Anush/Ono/Alex/William/YT | 0 | Description and default settings in Integration Spec reviewed
4 | doc | Orion NSIP Physical Design Spec reviewed | Orion-NSIP | Anush/Ono/Alex/William/YT | 0
5 | doc | NSIP Release notes reviewed | Orion-NSIP | Anush/Ono/Alex/William/YT | 0
6 | doc | NetSpeed Orion C++ Noc Model | Orion-NSIP | Anush/Ono/Alex/William/YT | 0
7 | doc | NSIP Tutorial (might be redundant, if we do the tutorial in S/W) | Orion-NSIP | Anush/Ono/Alex/William/YT | 0
8 | doc | Router Microarch Spec has been reviewed | All | Anush/Ono/Alex/William/YT | 0 | Is it sent everytime??
9 | doc | Streaming Bridge Microarch Spec has been reviewed | Orion-NSIP | Anush/Ono/Alex/William/YT | 0 | Is it sent everytime??
10 | doc - App Notes | Qos Rate Limiter | All | Anush/Ono/Alex/William/YT | 0
11 | doc - App Notes | RWC (Ericsson only) | All | Anush/Ono/Alex/William/YT | 0
12 | doc | NoCStudio AMBA Users Manual reviewed | Orion-AMBA | Anush/Ono/Alex/William/YT | 0
13 | doc | Orion AMBA IP Integration Spec reviewed | Orion-AMBA | Anush/Ono/Alex/William/YT | 0 | Description and default settings in Integration Spec reviewed
14 | doc | Orion AMBA Physical Design Spec reviewed | Orion-AMBA | Anush/Ono/Alex/William/YT | 0
15 | doc | AMBA Release notes reviewed | Orion-AMBA | Anush/Ono/Alex/William/YT | 0
16 | doc | NetSpeed Orion C++ Noc Model | Orion-AMBA | Anush/Ono/Alex/William/YT | 0
17 | doc | AMBA Tutorial (might be redundant, if we do the tutorial in S/W) | Orion-AMBA | Anush/Ono/Alex/William/YT | 0
18 | doc | AMBA Protocol Support | Orion-AMBA | Anush/Ono/Alex/William/YT | 0
19 | doc | Orion Streaming bridge Micro architecture | Orion-AMBA | Anush/Ono/Alex/William/YT | 0
20 | doc - App Notes | Qos Rate Limiter | All | Anush/Ono/Alex/William/YT | 0
21 | doc - App Notes | RWC (Ericsson only) | All | Anush/Ono/Alex/William/YT | 0
22 | doc | ACE master brige Microarch spec has been reviewed | Gemini | Anush/Ono/Alex/William/YT | 0
23 | location | Documents verified to be correct in release area | All | Anush/Ono/Alex/William/YT | 0
24 | doc | All released documents for correctness and typos. | All | Anush/Ono/Alex/William/YT | 0
25 | doc | All released documents reflect the correct revision ID. | All | Anush/Ono/Alex/William/YT | 0
26 | bugs | Bugzilla bugs for customer bugs closed | All | Anush/Ono/Alex/William/YT | 0 | May not be valid
27 | license | License server enabled | All | Anush/Ono/Alex/William/YT | 0 | May not be valid
28 | beta testing | Generated header from NocStudio always generates correct customer name | All | Anush/Ono/Alex/William/YT | 0 | May not be valid
29 | release | Release files on FTP site | All | Anush/Ono/Alex/William/YT | 0
30 | license | NoCstudio expire date setting done(enter date in 'quantify' col) | All | Anush/Ono/Alex/William/YT | 0
31 |  | new: review command changes/additions release doc | All | Anush/Ono/Alex/William/YT | 0
32 | license | FlexLM default license file per product approved - made available for alpa & beta testing |  | Anush/Ono/Alex/William/YT
33 | beta testing | Check quality of release tarball - try examples and check known customer configs | All | Anush/Ono/Alex/William/YT | 0 |  | moved from database tab
34 | Bugs - customer | Check if all the customer bugs are addressed in the release | All | Anush/Ono/Alex/William/YT | 0 | AE Team | moved from database tab
35 | doc | Gemini Users Manual reviewed | Gemini | Anush/Ono/Alex/William/YT | 0
36 | doc | Gemini IP Integration Spec reviewed | Gemini | Anush/Ono/Alex/William/YT | 0 | Description and default settings in Integration Spec reviewed
37 | doc | Gemini Physical Design Spec reviewed | Gemini | Anush/Ono/Alex/William/YT | 0
38 | doc | Gemini Release notes reviewed | Gemini | Anush/Ono/Alex/William/YT | 0
39 | doc | NetSpeed Orion C++ Noc Model | Gemini | Anush/Ono/Alex/William/YT | 0
40 | doc | Gemini Tutorial (might be redundant, if we do the tutorial in S/W) | Gemini | Anush/Ono/Alex/William/YT | 0
41 | doc | Gemini Cookbook | Gemini | Anush/Ono/Alex/William/YT | 0
42 | doc | Release Checklist filled out and checked into Branch | All | Ranjeet | 0 |  | duplicate
43 |  | Point person for bugs and issues identified - WHO ? | All | Anush | 0 | May not be valid