## Summary
NetSpeed Release Checklist Summary |  | Comments / Notes regarding branch
33225 | Trunk SVN version | This is the version from which branch 15.03 was created.
35294 | Branch SVN version | This is the version from which the last noc_stable was promoted.
|  | Owner | Status (%)
1 | Release database checks | Eric | 74
2 | Customer facing checks | Anush | 0
3 | HW Verif | JJ | 74.5455
4 | RTL | Joe | 76.9231
5 | Implementation | Rajesh | 89.1892
6 | NocStudio | Bhumesh | 96.1967
Products
Orion
Orion-AMBA
Orion-NSIP
Gemini
All

## Database
Summary
Task | Release Database Checks |  | Products | Owner | Status (%) | Exp Date | Comments
74
1 | Netspeed headers are properly generated |  | All | Eric | 100 |  | Needs to automate and based on BW
2 | Review NocStudio settings(init.txt) | Release NocStudio binary | All | Eric | 100 |  | Goes away soon
3 | NocStudio Model Sanity runs clean |  | All | Eric | 100
4 | NocStudio Customer headers properly generated |  | All | Eric | 100 |  | Needs to automated
5 | NocStudio tutorial & Examples in the Help |  | All | Nishant | 100
6 | nocstudio is identical in noc-dev and noc-stable in branch at release time |  | All | Eric | 100 |  | Automate it
7 | Check quality of release tarball - try examples and check known customer configs |  | All | Yogesh | 100 |  | Tutorial AE Team
8 | Try trace file with modified trace as customer would and feed back into NocStudio and RTL(streaming only for now). |  | Orion-NSIP | Eric | n/a |  | Automate it
9 | Make sure sanity run_test.sh includes waveform dump in command by default. Check that waveform is visible even in presence of encryption and Sanity Testbench is released |  | All | Yogesh | 100 |  | Check again
10 | Run released NocStudio binary with filtered NocWeaver random configs and check that, |  | All | Ninad | 100
11 | Generated RTL is identical between internal binary and external binary |  |  |  | 100
12 | Released RTL & checkers identical between internal and customer nocstudio binaries |  |  |  | 100 |  | not so critical
13 | Sanity is verified to run both with checker knobs ON and OFF, default setting should be Router checker OFF, E2E ON, Bridge ON, Regbus checkers ON, |  |  |  | 100 |  | Look at integration spec
14 | clock generation in the sanity bench like ratio sync, async crossing is exercised |  |  |  | 100 |  | verif team
15 | Sanity tests with NocStudio generated traces for rb_ahb, etc ACELM, AXI4, AXI3, AHB, APB, regbus run cleanly in release directory |  | All | Ninad | 100 |  | Verif
16 | Documents verified to be correct in release area |  | All | Ranjeet | 0
17 | Release Checklist filled out and checked into Branch |  | All | Gloria | 50
18 | Check quality of release tarball - try examples and check known customer configs |  | All | Ranjeet | 0
19 | Check if all the customer bugs are addressed in the release |  | All | Ranjeet | 0 |  | AE Team
20 | Owner of each verification sign off on their checkers are, |  | Orion-NSIP | Kate
21 | i. in place |  |  |  | 100
22 | ii. with the correct default setting for customer release |  |  |  | 100
23 | iii. with the correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. |  |  |  | NA
24 | iv. Every checker can be disabled from command-line |  |  |  | NA
25 | Metrics: record perf on NocStudio bench_noc command output and compare with previous releases |  | All | Sailesh | 100 |  | 20% throughput reduction is waived
26 | Multi NOC Compile |  | All | Ninad | 0
27 | Multiple binaries generate same RTL |  | All | Eric & Kiran | n/a |  | There is only one binary that generates rtl
28 | Description and default settings in Integration Spec reviewed |  | All | Kate | 100 |  | Separate amba and NSIP
29 | Owner of each verification sign off on their checkers are, |  | Orion-AMBA | JJ
30 | i. in place |  |  |  | 0
31 | ii. with the correct default setting for customer release |  |  |  | 0
32 | iii. with the correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. |  |  |  | NA
33 | iv. Every checker can be disabled from command-line |  |  |  | NA

## CustomerChecks
Summary
Task | 2 | Customer facing checks | Products | Owner | Status (%) | Exp Date | Comments
0
1 | 2.1 | NoC NSIP Programmers Reference Manual generation is verified correct | Orion-NSIP | Ranjeet | 0
2 | 2.2 | NoCStudio NSIP Users Manual reviewed | Orion-NSIP | Ranjeet | 0
3 | 2.3 | Orion NSIP Integration Spec reviewed | Orion-NSIP | Ranjeet | 0 |  | Description and default settings in Integration Spec reviewed
4 | 2.4 | Orion NSIP Physical Design Spec reviewed | Orion-NSIP | Ranjeet | 0
5 | 2.5 | NSIP Release notes reviewed | Orion-NSIP | Ranjeet | 0
6 | 2.7 | NoCStudio AMBA Users Manual reviewed | Orion-AMBA | Ranjeet | 0
7 | 2.8 | Orion AMBA Integration Spec reviewed | Orion-AMBA | Ranjeet | 0 |  | Description and default settings in Integration Spec reviewed
8 | 2.9 | Orion AMBA Physical Design Spec reviewed | Orion-AMBA | Ranjeet | 0
9 | 2.1 | AMBA Release notes reviewed | Orion-AMBA | Ranjeet | 0
10 | 2.12 | Router Microarch Spec has been reviewed | All | Ranjeet | 0 |  | Is it sent everytime??
11 | 2.13 | Streaming Bridge Microarch Spec has been reviewed | Orion-NSIP | Ranjeet | 0 |  | Is it sent everytime??
12 | 2.14 | ACE master brige Microarch spec has been reviewed | Gemini | Ranjeet | 0
13 | 2.15 | Documents verified to be correct in release area | All | Ranjeet | 0
14 | 2.16 | Release Checklist filled out and checked into Branch | All | Ranjeet | 0
15 | 2.18 | All released documents for correctness and typos. | All | Ranjeet | 0
16 | 2.19 | All released documents reflect the correct revision ID. | All | Ranjeet | 0
17 | 2.2 | Bug Modules for customer bugs created | All | Anush | 0 |  | May not be valid
18 | 2.21 | Point person for bugs and issues identified - WHO ? | All | Anush | 0 |  | May not be valid
19 | 2.22 | License server enabled | All | Anush | 0 |  | May not be valid
20 | 2.23 | Generated header fron NocStudio always generates correct customer name | All | Anush | 0 |  | May not be valid
21 | 2.24 | Release files on FTP site | All | Anush | 0
22 | 2.25 | NoCstudio expiry date setting done(enter date in 'quantify' col) | All | Anush | 0

## HW Verif
Summary
Task | 3 |  | HW Verification | Products | Owner | Status (%) | Exp Date | Comments
74.5455
1 |  |  | All Bugs reviewed and verified to be 'CLOSED' or 'CIAR' - Verified Fixed and not just Resolved Fixed | All | Gloria | 0
2 |  |  | Max Error between Model and RTL is < 10% | All | Eric | 0
3 |  |  | Sanity bench passes with VCS for all benches | All | Kate | 100
4 |  |  | Nemesis runs reviewed for any error, permission and new features | All | Ninad | 100
5 |  |  | NocWeaver randomization knobs reviewed for NocStudio range and parameters | All | JJ | 0 |  | Not done for Q1
6 |  |  | Runs verified with all internal bridge and E2E checkers | All | JJ | 100
7 |  |  | Runs verified with Cadence Protocol checker AXI, AHB and APB | All | Shan | 100
8 |  |  | NoC level i/o pins toggle coverage on Superconfig | All | JJ | 0 |  | Not done for Q1
9 |  |  | Check for all commented out tests in regress list | All | JJ | 100
10 |  |  | All Regressions are run : Nightly, Release, Regbus, Streaming, Promotion, CCC, axi, axi_long, DVM, Router, APB | All | JJ | 100 |  | Router run by Yogesh, APB by Vishnu
11 |  |  | Review waived warnings for build log, simulation log for VCS | All | JJ | 100
12 |  |  | Mixed bridge sanity (inc regbus) passes internal flow for random 500 configs, new features Mania | Orion | Ninad | 100
13 |  |  | Mixed bridge sanity (inc regbus) passes external flow for 1000 configs external sanity | Orion | Ninad | 100
14 |  |  | Internal vs External binary produced NoCs compared over 500 mix br configs | Orion | Ninad | 100
15 |  |  | New weights for nocweaver are enabled and exercised | Orion | Ninad | 100
16 |  |  | Review that no checker is unexpectedly disabled in the internal environment. | All | JJ | 100
17 |  |  | No unnecessary in-house checkers are included. Cleanly partition files and code and make sure only external files are included. | All | Kate | 0
18 |  |  | Benchmark simulation slow-down with checkers on versus off. | All | JJ | NA
19 |  |  | Run a set of 50 configs with router checker enabled. | Orion-NSIP | Yogesh | 0 |  | Not Done for Q1
20 |  |  | (NocWeaver) All agents: axi4m, axi3m, apb, ahblm, ahbls, axi4mls, stream(if applicable), acelm | All | Ninad | 100
21 |  |  | (NocWeaver) At least one ahb config should have all 16 slave regions. | All | Ninad | 100
22 |  |  | (NocWeaver) At least one apb config should have all 16 slave regions | All | Ninad | 100
23 |  |  | (NocWeaver) Both little endian and big endian for both ahblm and ahbls. | All | Ninad | 100
24 |  |  | (NocWeaver) w/ and w/o regbus | All | Ninad | 100
25 |  |  | (NocWeaver) w/ and w/o async | All | Ninad | 100
26 |  |  | (NocWeaver) w/ and w/o clock gating | All | Ninad | 100
27 |  |  | (NocWeaver) w/ and w/o data interleaving | All | Ninad | 100
28 |  |  | (NocWeaver) All combinations of protection bits, security bits(addr[5:0]) which will affect mania traffic | All | Ninad | 100
29 |  |  | (NocWeaver) w/ and w/o overrides | All | Ninad | 100
30 |  |  | (NocWeaver) min addr and max addr width | All | Ninad | 100
31 |  |  | (NocWeaver) All data widths supported | All | Ninad | 100
32 |  |  | Sanity Bench components (Ambaxtor, Regxtor, AHBxtor) and slave models, aHB and APB are cleaned up. | All | JJ | 100
33 |  |  | Regressions run and pass with checkers and knobs on/off | All | Ninad | 0 |  | This is not done for Q1
34 |  | Streaming | Checker Comments are cleaned up | Orion-NSIP | Yogesh | 100
35 |  |  | Review checkers: make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. | Orion-NSIP | Yogesh | 100
36 |  |  | Q1 New Features are tested | Orion-NSIP | Yogesh | 100
37 |  |  | Run Coverage (Toggle / Functional / Expression) | Orion-NSIP | Yogesh | NA
38 |  |  | Run parameter coverage | Orion-NSIP | Yogesh | NA
39 |  |  | Unit TB exercises all limits and parameters in NocStudio limit list | Orion-NSIP | Yogesh | NA
40 |  | Router | Checker Comments are cleaned up | All | Yogesh | 100
41 |  |  | Review checkers: make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. | All | Yogesh | 100
42 |  |  | Q1 New Features are tested | All | Yogesh | 100
43 |  |  | Run Coverage (Toggle / Functional / Expression) | All | Yogesh | NA
44 |  |  | Run parameter coverage | All | Yogesh | NA
45 |  |  | Unit TB exercises all limits and parameters in NocStudio limit list | All | Yogesh | NA
46 |  | AHB | Checker Comments are cleaned up | Orion-AMBA | Shan | 0
47 |  |  | Review checkers: make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. | Orion-AMBA | Dasa | 100
48 |  |  | Q1 New Features are tested | Orion-AMBA | Shan | 0 |  | Burst size
49 |  |  | Run Coverage (Toggle / Functional / Expression) | Orion-AMBA | Shan | NA
50 |  |  | Run parameter coverage | Orion-AMBA | Shan | NA
51 |  |  | Unit TB exercises all limits and parameters in NocStudio limit list | Orion-AMBA | Shan | 0
52 |  | AXI | Checker Comments are cleaned up | Orion-AMBA | Kate | 0
53 |  |  | Review checkers: make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. | Orion-AMBA | Kate | 0
54 |  |  | Q1 New Features are tested | Orion-AMBA | Kate | 0
55 |  |  | Run Coverage (Toggle / Functional / Expression) | Orion-AMBA | Kate | NA
56 |  |  | Run parameter coverage | Orion-AMBA | Kate | NA
57 |  |  | Unit TB exercises all limits and parameters in NocStudio limit list | Orion-AMBA | Kate | 0
58 |  | APB | Checker Comments are cleaned up | Orion-AMBA | Vishnu | 100
59 |  |  | Review checkers: make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. | Orion-AMBA | Vishnu | 100
60 |  |  | Q1 New Features are tested | Orion-AMBA | Vishnu | 100
61 |  |  | Run Coverage (Toggle / Functional / Expression) | Orion-AMBA | Vishnu | NA
62 |  |  | Run parameter coverage | Orion-AMBA | Vishnu | NA
63 |  |  | Unit TB exercises all limits and parameters in NocStudio limit list | Orion-AMBA | Vishnu | 100
64 |  | Regbus | Checker Comments are cleaned up | All | JJ | 100 |  | NSIP and AMBA separate
65 |  |  | Review checkers: make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. | All | JJ | 100
66 |  |  | Q1 New Features are tested | All | Ninad | 100
67 |  |  | Run Coverage (Toggle / Functional / Expression) | All | JJ | NA
68 |  |  | Run parameter coverage | All | JJ | NA
69 |  | Clock Gating | Checker Comments are cleaned up | All | JJ | 100
70 |  |  | Review checkers: make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. | All | JJ | 100
71 |  |  | Q1 New Features are tested | All | JJ | NA
72 |  |  | Run Coverage (Toggle / Functional / Expression) | All | JJ | NA
73 |  |  | Run parameter coverage | All | JJ | NA

## RTL
Summary
Task | 4 |  | RTL | Products | Owner | Status (%) | Exp Date | Comments
76.9231
1 | 4.1.1 | AXI | Lint checks run, logs reviewed, no errors. Any exceptions to be documented | Orion-AMBA | Joji | 100
2 | 4.1.2 |  | Review RTL file list | Orion-AMBA | Joji | 0
3 | 4.1.3 |  | Comments reviewed and found to be Customer OK. (no hacks/fixmes etc) | Orion-AMBA | Joji | 100
4 | 4.1.4 |  | Code review complete | Orion-AMBA | Joji | 0
5 | 4.1.5 |  | Review file header for all released RTL files. | Orion-AMBA | Joji | 0
6 | 4.1.6 |  | Bugzilla clean: all bugs closed or reviewed and waived explicitly for release. | Orion-AMBA | Joji | 100
7 | 4.2.1 | AHB | Lint checks run, logs reviewed, no errors. Any exceptions to be documented | Orion-AMBA | Sandip | 100
8 | 4.2.2 |  | Review RTL file list | Orion-AMBA | Sandip | 0
9 | 4.2.3 |  | Comments reviewed and found to be Customer OK. (no hacks/fixmes etc) | Orion-AMBA | Sandip | 100
10 | 4.2.4 |  | Code review complete | Orion-AMBA | Sandip | NA
11 | 4.2.5 |  | Review file header for all released RTL files. | Orion-AMBA | Sandip | 100
12 | 4.2.6 |  | Bugzilla clean: all bugs closed or reviewed and waived explicitly for release. | Orion-AMBA | Sandip | 100
13 | 4.3.1 | APB | Lint checks run, logs reviewed, no errors. Any exceptions to be documented | Orion-AMBA | Rimu | 100
14 | 4.3.2 |  | Review RTL file list | Orion-AMBA | Rimu | 100
15 | 4.3.3 |  | Code review complete | Orion-AMBA | Rimu | 100
16 | 4.3.4 |  | Review file header for all released RTL files. | Orion-AMBA | Rimu | 100
17 | 4.3.5 |  | Bugzilla clean: all bugs closed or reviewed and waived explicitly for release. | Orion-AMBA | Rimu | 100
18 | 4.4.1 | NSIP Bridge | Lint checks run, logs reviewed, no errors. Any exceptions to be documented | Orion-AMBA | Rajesh | 100
19 | 4.4.2 |  | Review RTL file list | Orion-AMBA | Rajesh | 100
21 | 4.4.4 |  | Comments reviewed and found to be Customer OK. (no hacks/fixmes etc) | Orion-NSIP | Rajesh | 100
22 | 4.4.5 |  | Code review complete | Orion-NSIP | Rajesh | 100
23 | 4.4.6 |  | Review file header for all released RTL files. | Orion-NSIP | Rajesh | 100
24 | 4.4.7 |  | Bugzilla clean: all bugs closed or reviewed and waived explicitly for release. | Orion-NSIP | Rajesh | 100
25 | 4.5.1 | Regbus | Lint checks run, logs reviewed, no errors. Any exceptions to be documented | All | Jaya | 100
26 | 4.5.2 |  | Review RTL file list | All | Jaya | 0
27 | 4.5.3 |  | Comments reviewed and found to be Customer OK. (no hacks/fixmes etc) | All | Jaya | 100
28 | 4.5.4 |  | Code review complete | All | Jaya | 0
29 | 4.5.5 |  | Review file header for all released RTL files. | All | Jaya | 100
30 | 4.5.6 |  | Bugzilla clean: all bugs closed or reviewed and waived explicitly for release. | All | Jaya | 100
31 | 4.6.1 | CG | Lint clean: HAL, Quartus, RC | All | Sandip | 100
32 | 4.6.2 |  | Review RTL file list | All | Sandip | 0
33 | 4.6.3 |  | RTL files have NetSpeed header | All | Sandip | 100
34 | 4.6.4 |  | Comments reviewed and found to be Customer OK. (no hacks/fixmes etc) | All | Sandip | 100
35 | 4.6.5 |  | Code review complete | All | Sandip | 100
36 | 4.6.6 |  | Review file header for all released RTL files. | All | Sandip | NA
37 | 4.6.7 |  | Bugzilla clean: all bugs closed or reviewed and waived explicitly for release. | All | Sandip | 100
38 | 4.7.1 | Router | Lint checks run, logs reviewed, no errors. Any exceptions to be documented | All | Joji | 100
39 | 4.7.2 |  | Review RTL file list | All | Joji | 0
40 | 4.7.3 |  | Router code review done and AI completed | All | Joji | NA
41 | 4.7.4 |  | Comments reviewed and found to be Customer OK. (no hacks/fixmes etc) | All | Joji | 100
43 | 4.7.6 |  | Review file header for all released RTL files. | All | Joji | 0
44 | 4.7.7 |  | Bugzilla clean: all bugs closed or reviewed and waived explicitly for release. | All | Joji | 100

## Backend
Summary
Task | 5 |  | Backend | Products | Owner | Status (%) | Exp Date | Comments
89.1892
1 | 5.1 | Router | Router timing | All | Rajesh | 100
2 | 5.1.1 |  | tb_str200_ly1_routersizes | All | Rajesh | 100
3 | 5.2 | Streaming | Streaming Bridge timing of | Orion-NSIP | Rajesh | 100
4 | 5.2.1 |  | Customer config | Orion-NSIP | Rajesh | 100
5 | 5.1.2 |  | Example | Orion-NSIP | Rajesh | 100
6 | 5.3 |  | Synthesis logs reviewed, no errors. Warnings/exceptions are documented. | Orion-NSIP | Rajesh | 100
7 | 5.4 |  | DC/DCT run on Edna config | Orion-NSIP | Rajesh | 100
8 | 5.5 |  | Lint (HAL & Quartus) - Daily regressions | Orion-NSIP | Rajesh | 100
9 | 5.5.1 |  | tb_str3_ly8_bridge_codecov | Orion-NSIP | Rajesh | 100
10 | 5.5.2 |  | tb_str9_ly6_priority | Orion-NSIP | Rajesh | 100
11 | 5.6 |  | FPGA synthesis (Quartus) - Customer config | Orion-NSIP | Rajesh | NA
12 | 5.7 |  | FPGA synthesis (Vivado) - Customer config | Orion-NSIP | Rajesh | NA
13 | 5.8 |  | LEC on all synthesis | Orion-NSIP | Rajesh | 100
14 | 5.9 |  | Emulator compile | Orion-NSIP | Rajesh | NA
15 | 5.1 | AMBA | AMBA timing | Orion-AMBA | Rajesh | 100
16 | 5.10.1 |  | tb_axi5_slv6_syn_typ | Orion-AMBA | Rajesh | 100
17 | 5.10.2 |  | tb_axi5_slv6_syn_extrm | Orion-AMBA | Rajesh | 100
18 | 5.10.3 |  | tb_axi6_slv5_amba_supcfg_synth | Orion-AMBA | Rajesh | 100
19 | 5.11 |  | Synthesis logs reviewed, no errors. Warnings/exceptions are documented. | Orion-AMBA | Rajesh | 100
20 | 5.12 |  | DC/DCT run on a config | Orion-AMBA | Rajesh | 100 |  | 2 warnings that can be waived
21 | 5.13 |  | Lint (HAL & Quartus) - Daily regressions | Orion-AMBA | Rajesh | 100
22 | 5.13.1 |  | tb_axi5_slv5_amba_supcfg_lint | Orion-AMBA | Rajesh | 100
23 | 5.13.2 |  | tb_axi6_slv5_amba_supcfg_synth | Orion-AMBA | Rajesh | 100
24 | 5.13.3 |  | tb_axi9_ahblm4_axi3m1_axi4lm2_axi4m2_slv5_axi4ls3_ahbls2_ly1_regbus_addcomp_cg_multi_clock_eco_486421713_0306 | Orion-AMBA | Rajesh | 100
25 | 5.13.4 |  | tb_axi4_axi4m4_slv5_axi3s3_axi4s1_ly2_regbus_tunnel_addcomp_cg_multi_clock_eco_1336040710_0305 | Orion-AMBA | Rajesh | 100
26 | 5.14 |  | FPGA synthesis (Quartus) | Orion-AMBA | Rajesh | 0
27 | 5.14.1 |  | Customer Config | Orion-AMBA | Rajesh | 0
28 | 5.14.2 |  | Customer Config | Orion-AMBA | Rajesh | 0
29 | 5.15 |  | FPGA synthesis (Vivado) | Orion-AMBA | Rajesh | 100
30 | 5.15.1 |  | Customer Config | Orion-AMBA | Rajesh | 100
31 | 5.15.2 |  | Customer Config | Orion-AMBA | Rajesh | 100
32 | 5.16 |  | LEC on all synthesis | Orion-AMBA | Rajesh | 100
33 | 5.17 |  | Emulator compile | Orion-AMBA | Rajesh | NA
34 | 5.18 |  | Verified that RC synthesis scripts run in release directory | All | Rajesh | 100
35 | 5.19 |  | Verified that DC synthesis scripts run in release directory | All | Rajesh | 100
36 | 5.2 |  | Synthesis for Multi-Clock AMBA and Streaming Noc's - check SDC files, Hier and Top (RC and DC) | All | Rajesh | 100
37 | 5.21 |  | CDC Checks for async clock crossings and other clks | All | Sandip | 100
38 | 5.22 |  | IPXACT Qual | All | Rajesh | 0
39 | 5.23 |  | Physical Metrics generated, reviewed and posted | All | Rajesh | 100
40 | 5.24 |  | Metrics: record area, instances, freqency on synthesis output and compare with previous releases | All | Rajesh | 100
41 | 5.25 |  | DEF File correctness | All | Rajesh | 100

## NocStudio
Task | 7 | NocStudio Checks | Products | Owner | Status (%) | Exp Date | Comments
96.1967
1 | 7.1 | Test all new quarterly release features | All | Kiran | 100 |  | Test Writing for 15Q1 features is complete based on Aha and Trello lists. Running them repeatedly is an on-going process.
4 | 7.4 | Monkey test for GUI | All | Cang | 60 |  | Only InfoNam GUI team does all the GUI testing
5 | 7.5 | Run all SW Verif test suites and make sure all of them pass. | All | Kiran | 99.9095
6 | 7.5.1 | Run all tests that are part of selftest | All | Bhumesh | 99.7286 |  | All these are run with each promotion run
7 | 7.5.1.1 | Run all independent selftests (BiridgeTest*, MathUtil*, etc) | All | InfoNam | 99 |  | BridgeTest*:MathUtil*:Range*:StringHandling*:Math*:SizeConversion*:GridTestGet*:Packet_Test*:RandomTest*:Alias_Test*:Host_Props*:DepUndep*:Default_Props*:Mesh_Props*:Range_test*:Bridge_Props*:Traffic_test*:link_opt*:Link_Props*:Latency_Test*:Trace_Files*:WidthConversion*:ScriptTest*:Rate_Test*
8 | 7.5.1.2 | Run all C0 OTests | All | InfoNam | 99.1 |  | 15 tests from C0 tests are disabled. Total 1678, 7 disabled are waived, 15 are yet to be debugged.
9 | 7.5.1.3 | Run all C0 LongOTests | All | InfoNam | 100 |  | LongOTests/OTest.*
10 | 7.5.1.4 | Run all C0 ReleaseExampleTests | All | InfoNam | 100 |  | ReleaseExampleTests/OTest.*
11 | 7.5.1.5 | Run all C0 RegressionTests | All | InfoNam | 100 |  | RegressionTests/OTest.*
12 | 7.5.1.6 | Run all PerfCSVTests | All | InfoNam | 100 |  | PerfCSVTests/CSVCheck.*
13 | 7.5.1.7 | Run all gold file tests | All | InfoNam | 100 |  | OFileTests/FileChk.*
14 | 7.5.2 | Run all script tests | All | InfoNam | 100
15 | 7.5.2.1 | Run all C1 and C2 short script tests | All | InfoNam | 100 |  | Under otests/script
16 | 7.5.2.2 | Run all C1 and C2 long script tests | All | InfoNam | 100 |  | Under otests/long_script
17 | 7.5.2.3 | Run all CSV property tests | All | InfoNam | 100 |  | Under otests/script/csv_files/csv_property_test.pl
18 | 7.5.3 | Run all C model tests | All | InfoNam | 100 |  | Under otests/c_model_tests
| 7.6 | Review the property testing CSV files along with verif, dev, and release committee | All | Gloria | 70 |  | First a release committee (Gloria, SW dev team, SW verif team, Marketing team) should review all the CSV files and determine what are valid commands and props and their values.
| 7.7 | Cross Platform Testing | All | Kiran | 100 |  | Completed for NSIP, used NSIP license.dat files, yet to do it with AMBA.
| 7.8 | All Bugzilla bugs and Assembla tickets are fixed and closed. | All | Bhumesh | 100 |  | All the open Assembla tickets relevant for the release tracked in one Bugzilla bug Once all the relevant Assembla tickets are fixed and closed the tracking Bugzilla bug can be closed . There is no 1503 release blocking ticket open in Assembla or Bugzilla.
Review disabled tests in soft tests