## Summary
NetSpeed Release Checklist Summary
Comments / Notes regarding branch
| Branch SVN version | 58007 |  | This is the version from which the last noc_stable was promoted. | netspeed-1604_info
| Branch Name | rel_1604 |  | This is the name of the branch in branches directory
| Category | Owner | Status (%)
| Release Package checks | Eric | 0
| HW Verif | JJ (Gemini) Won(AMBA) JJ(NSIP) | 0
| HW Design | Joji | 0
| CAD Tools | Rajesh | 0
| NocStudio SW Design | Eric | 0
| NocStudio SW Verif | Bhumesh | 0
| License & Beta Testing | Anush | 0
| Documentation | Anush | 0
Optional: | Customer Specific Tapeout | Joe | 0
Products
Orion
Orion-AMBA
Orion-NSIP
Gemini
All
| Key Customer Information: | <customer name>
<customer project name>
<Netspeed product>
<tapeout date>
<tapeout date>

## Release Pkg
Summary
Overall Status (%)
0
Task | type | Release Database Checks | Products | Owner | Status (%) | Comments
1 | release NS bin | Netspeed headers are properly generated | All | Nishant | 0 | Needs to automate and based on BW (copyright; version, etc.)
2 | release NS bin | NocStudio Customer headers properly generated | All | Nishant | 0 | Needs to automated (customer header.txt is put after our NS header in fabric.v, etc.)
3 | release NS bin | NocStudio tutorial & Examples in the Help - update with latest commands | All | Nishant | 0 | sw verif self tests already include them in regression so syntax ok
4 | release NS bin | create new NocStudio Tutorials to demonstrate new features | All | Support Team (Anush) | 0 | Alex created new tutorials
4 | NS trace | Try trace file with modified trace as customer would and feed back into NocStudio and RTL(streaming only for now). | Orion-NSIP | Eric | 0 | check trace file is generated by NS check NS can read customer trace file and run perf sim
5 | release branch | NocStudio is identical in noc-dev and noc-stable in branch at release time | All | Eric | 0 | promotion passed - check that last Noc Studio commit was in the promotion
6 | alpha testing | Check quality of release tarball - try examples and check known customer configs | All | Nishant | 0
7 | release checklist | Release Checklist filled out and checked into Branch | All | Gloria | 0 | as much as the team can do

## SW Design
Summary
Overall Status (%)
0
Task | Type | SW design | Products | Owner | Status (%) | Comments
1 | review | All command changes highlighted & approved | All | Nishant | 0 | CSV review done.
2 | doc | help menu feature description in place | All | Pier | 0
3 | testing | deep testing | All | Eric | 0 | SW team did 1.5 days of alpha testing
4 | metrics: Perf | Metrics: record perf on NocStudio bench_noc command output and compare with previous releases | All | Nishant | 0 | Q2: Link cost went up by 7% due to more accurnate modeling; everything else tracks or got better Q1: 20% throughput reduction is waived | moved from database tab
5 | Quality | Valgrind passes (segfault and mem leak detection) | All | Eric | 0 | done on 4/26
6

## SW Verif
Summary
Overall Status (%)
0
Task | Type | NocStudio SW Verif Checks | Products | Owner | Status (%) | Comments
1 |  | Test all new quarterly release features | All | Kiran | 0 | Running these repeatedly is an on-going process. We have not looked at Trello cards yet for Q2 release.
2 |  | Monkey test for GUI | All | Tai Vu | 0 | Only InfoNam GUI team does all the GUI testing
3 |  | Run all SW Verif test suites and make sure all of them pass. | All | Kiran | 0
4 |  | Run all tests that are part of selftest | All | Bhumesh | 0 | All selftests are now run as a cron job on on InstaCompute machine by SW Verif team. All selftests as defined by "make run_selftest", this does not have any filters on selftests, i.e., all self tests are run. Promotion runs are not running any SW selftests now (as of 2015_04_28).
5 |  | Run all independent selftests (BiridgeTest*, MathUtil*, etc) | All | InfoNam | 0 | BridgeTest*:MathUtil*:Range*:StringHandling*:Math*:SizeConversion*:GridTestGet*:Packet_Test*:RandomTest*:Alias_Test*:Host_Props*:DepUndep*:Default_Props*:Mesh_Props*:Range_test*:Bridge_Props*:Traffic_test*:link_opt*:Link_Props*:Latency_Test*:Trace_Files*:WidthConversion*:ScriptTest*:Rate_Test*
6 |  | Run all C0 OTests | All | Bhumesh | 0 | 1800 tests passing out of 1805.
7 |  | Run all C0 LongOTests | All | Bhumesh | 0 | LongOTests/OTest.*
8 |  | Run all C0 ReleaseExampleTests | All | Bhumesh | 0 | ReleaseExampleTests/OTest.*
9 |  | Run all C0 RegressionTests | All | Bhumesh | 0 | RegressionTests/OTest.*
10 |  | Run all PerfCSVTests | All | Bhumesh | 0 | PerfCSVTests/CSVCheck.*
11 |  | Run all gold file tests | All | Bhumesh | 0 | OFileTests/FileChk.*
12 |  | Run all script tests | All | Bhumesh | 0
13 |  | Run all C1 and C2 short script tests | All | Bhumesh | 0 | Under otests/script except csv_property_test.pl and license_check.pl
14 |  | Run all C1 and C2 long script tests | All | Bhumesh | 0 | Under otests/long_script
15 |  | Run the license check test | All | Bhumesh | 0 | Under otests/script/license_check/license_check.pl
16 |  | Run all CSV property tests | All | Kiran | 0 | Under otests/script/csv_files/csv_property_test.pl
17 |  | Run all C model tests | All | Bhumesh | 0 | Under otests/c_model_tests
18 |  | Review the property testing CSV files along with verif, dev, and release committee | All | Kiran | 0
19 |  | Cross Platform Testing | All | Bhumesh | 0 | Not started for Q2 release work. VMs are available, need to test
20 |  | All Bugzilla bugs and Assembla tickets are fixed and closed. | All | Sailesh | 0 | All the open Assembla tickets relevant for the release tracked in one Bugzilla bug Once all the relevant Assembla tickets are fixed and closed the tracking Bugzilla bug can be closed.
21 |  | Review disabled tests in SW tests | All | Bhumesh | 0 | On-going review, a few rounds are completed. Need to review one more time when LP branch to trunk merge is completed
22 |  | Reach 90% Coverage with SW tests | All | Kiran | 0 | Coverage hole filling exercise did not start yet. Initial coverage measurements are giving 85% plus coverage
|  | self tests |  | Bhumesh
|  | script tests (C2) |  | Bhumesh
|  | tests for cmd/prop (CSV) |  | Bhumesh
|  | Flex LM knobs |  | Bhumesh
|  | NSIP cmodel testing |  | Bhumesh
|  | Valgrind |  | Eric
|  | cross platform testing |  | Bhumesh
|  | sw perf regressions (for perf metrics) |  | Nishant
|  | tarball Linux - run examples & tutorials |  | Nishant
|  | tarball windows (zip file) - run examples & tutorials |  | Nishant
|  | customer license files |  | Alex

## HW Verif
Summary
| 3 |  |  |  |  | Overall Status (%)
0
Task | 3 | Type | HW Verification | Products | Owner | Status (%) | Comments
1 |  | Bugs | Release Block Bug CLOSED - All Bugs reviewed and verified to be 'VERIFIED' or 'CIAR' (truly closed) | All | Gloria | 0
2 |  | coverage | NoC level i/o pins toggle coverage on Superconfig | All | JJ | 0 | got first pass data
3 |  | coverage | signoff Coverage (Toggle / Functional / Expression) | All | Won | 0 | made not a gate...do after the release
4 |  | coverage | signoff parameter coverage ** | All | Perry | 0 | **Buildbot is collecting parameter cov data automatically. Some block owners have reviewed.
5 |  | regression setup | NocWeaver randomization knobs reviewed for NocStudio range and parameters | All | JJ | 0 | Not done for Q1
6 |  | regression setup | Check for all commented out tests in regress list | All | Dawn | 0
7 |  | regression setup | New weights for nocweaver are enabled and exercised | Orion | JJ | 0
8 |  | regression setup | Review that no checker is unexpectedly disabled in the internal environment. | All | Kate | 0
9 |  | checkers | Runs verified with Cadence Protocol checker AXI, AHB and APB | All | JJ | 0 | 12 tests to axi full regression and 1 test in mini regression uses cadence vip protocol checkers AXI, AHB, APB
10 |  | checkers | Benchmark simulation slow-down with checkers on versus off. | All | JJ | 0 | nice to do
11 |  | checker - Streaming | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-NSIP | Kate | 0 | ext_sanity does not currently support checker_en plusargs passed on command line
12 |  | checker - Router | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | JJ | 0 | turn off since not support VC remapping
13 |  | checker - AHB | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-AMBA | Kate | 0 | ext_sanity does not currently support checker_en plusargs passed on command line
14 |  | checker - AXI | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-AMBA | Kate | 0 | ext_sanity does not currently support checker_en plusargs passed on command line
15 |  | checker - APB | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Orion-AMBA | Santhosh | 0
16 |  | checker - Regbus | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | JJ | 0 | NSIP and AMBA separate - JJ said no blockers for 16.04 on 5/3
17 |  | checker - Clock Gating | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | JJ | 0 | JJ said no blockers for 16.04 on 5/3
18 |  | checker - end2end | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | All | JJ | 0 | JJ said no blockers for 16.04 on 5/3
19 |  | checker - global coherency | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0 | JJ said no blockers for 16.04 on 5/3
20 |  | checker - CCC | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0 | JJ said no blockers for 16.04 on 5/3
21 |  | checker - DVM | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0 | JJ said no blockers for 16.04 on 5/3
22 |  | checker - IOCB | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0 | JJ said no blockers for 16.04 on 5/3
23 |  | checker - LLC | Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line | Gemini | JJ | 0 | JJ said no blockers for 16.04 on 5/3
24 |  | AMBA LP checkers: Q channel, multivoltage, etc. |  | Orion-AMBA | Won | 0
25 |  | Gemini LP checkers: Q channel, multivoltage, etc. |  | Orion-AMBA | JJ | 0 | Gemini LP alpha only had 5 directed tests - nothing else added for randomization/checking
26 |  | HW regressions (AMBA & Gemini | promotion | All | Ben | 0
27 |  | HW regressions (AMBA & Gemini | nightly | All | KiranB | 0
28 |  | HW regressions (AMBA & Gemini | weekly | All | Kate | 0 | includes axi regression lists
29 |  | HW regressions (AMBA & Gemini | nemesis (nocweaver) | All | Kate | 0
30 |  | HW regressions (AMBA & Gemini | Regbus NocWeaver (sweep, pingster, tunnel) | All | Ben | 0
31 |  | HW regressions (AMBA) | LP NW regressions - 800 seeds nemesis (nocweaver) without Multivoltage | All | Vinayendra | 0 | http://172.29.106.32:8010/builders/1604-lp-nw/builds/2/steps/nocfarm/logs/stdio
32 |  | HW regressions (AMBA) | LP Fixed Regression - regress list | All | Vinayendra | 0 | http://172.29.106.32:8010/builders/1604-lp/builds/4/steps/regress0/logs/stdio
33 |  | HW regressions (AMBA & Gemini | LP - Gemini tests in AXI regress list | All | JJ | 0 | 5 tests
34 |  | HW regressions (AMBA) | LP conformal - 20 configs | All | Santhosh | 0
35 |  | HW regressions (AMBA & Gemini | external sanity (includes sram testbench) | All | Ben | 0
36 |  | HW regressions (AMBA & Gemini | VCS internal regressions & ext sanity | All | Won | 0 | smoke+axi pass
37 |  | HW regressions (AMBA & Gemini | tarball - perf testing | All | Will | 0
38 |  | HW regressions (NSIP) | VCS regressions - reviewed build log and simulation logs and pass | All | Won | 0
39 |  | HW regressions (NSIP) | Regbus NocWeaver (sweep, pingster, tunnel) | All | Ben | 0
40 |  | HW regressions (NSIP) | external sanity | All | Ben | 0
41 |  | HW regressions (NSIP) | new RWC nocweaver | All | Will | 0
42 |  | HW regressions (NSIP) | tarball - run examples & test 2 customer config + 7 ex configs | All | Kate | 0
43 |  | HW regressions | x propagation randomized - multivoltage |  | Won | 0 | X-Prop is on by default
44 |  | HW regressions | async clks and ratio clks randomized- DVFS |  | Won | 0 | extreme ratio clocks on MV (fixed)
45 |  | UVM & Perf | UVM regressions: customer testbench, perf tests, module tests | Orion-AMBA | Will/Kate | 0 | Kate added IMG2
46 |  | module level regressions | router | Gemini | JJ | 0
47 |  | module level regressions | AHB | Gemini | Kate | 0
48 |  | module level regressions | APB | Gemini | Santhosh | 0
49 |  | module level regressions | CCC | Gemini | JJ | 0
50 |  | module level regressions | DVM | Gemini | JJ | 0
51 |  | module level regressions | NCB | Gemini | JJ | 0
52 | verif multiNOC | Multi NOC Compile | test muliNOC and tag project | Orion-NSIP | KiranB | 0
DO NOT CHANGE TEXT BELOW since it's Reference Data for cells above:
Signoff on Checkers: - in place and checks new features for the quarterly release - Unit TB exercises all limits and parameters in NocStudio are on the limit list - doc - checker comments are cleaned up - doc - make sure error messages have no typos or grammatical errors. Check for consistent use of `ns header. - for customer: with correct default setting for customer release - for customer: with correct description on the IP integration on how to program, relevant DV plusargs, any info the customer needs to know to use the checkers. - for customer: every check can be disabled from the command line
Note on D31: Author: old tests that caught failure a lot of tests and a lot of configs
Note on D32: Author: old tests that caught failure a lot of tests and a lot of configs
Note on D33: Author: old tests that caught failure a lot of tests and a lot of configs
Note on D36: Author: about 1000 configs - test new features
Note on D47: Author: example config ericsson config tutorials external tb - builds run and test

## HW Design
Summary
Overall Status (%)
0
Task | Type | HW Design | Products | Owner | Status (%) | Comments | lint clean | new qtr features ok | rtl file list | comments clean | file header ok | bugs fixed | timing ok | area ok | auto emacs ok | no tabs
1 | module | ACE Master | Orion-AMBA | Joji | 0
2 | module | ACE Slave | Orion-AMBA | Joji | 0
3 | module | AHB Master | Orion-AMBA | Perry | 0
4 | module | AHB Slave | Orion-AMBA | Perry | 0
5 | module | APB Slave | Orion-AMBA | Dawn | 0 | Only had a couple bug fixes, otherwise stable rtl.
6 | module | AXI-lite Slave | Orion-AMBA | Joji | 0
7 | module | NSIP Bridge | Orion-NSIP | Rajesh | 0
8 | module | Regbus - Regbus Master (RBM) | All | Joji | 0
9 | module | Regbus - Ring Master | All | Rajesh | 0
10 | module | Regbus -Ring Slave | All | Rajesh | 0
11 | module | Regbus - Tunnel | All | Rajesh | 0
12 | module | Regbus - APB Master | All | Dawn | 0 | NA for this release RTL Updates and NocStudio updates done
13 | module | clk gating | All | Joji | 0
14 | module | Router | All | Joji | 0
15 | module | async link clk cross fifo | All | Dawn | 0
16 | module | IMG2 Slave |  | Dawn | 0
17 | module | IMG4 Master |  | Dawn | 0 | NA for this release
18 | module | Reorder Bridge |  | Joji | 0 | not released
19 | module | Shared Interface Bridge |  | Perry | 0
20 | wrapper | AXI4 & AXI3 Master | Orion-AMBA | Joji | 0
21 | wrapper | AXI-lite Master | Orion-AMBA | Joji | 0
22 | wrapper | AXI4 & AXI3 Slave | Orion-AMBA | Joji | 0
23 | wrapper | CCC | Gemini | Joe | 0
24 | wrapper | DVM | Gemini | Joe | 0
25 | wrapper | IOCB | Gemini | Joe | 0
26 | wrapper | LLC | Gemini | Joe | 0
Note on G17: RTL and NocStudio updates done. No GenStreamX support yet. -Rimu Kaushal

## CAD Tools
Summary
Overall Status (%)
0
Task | Type | Block | CAD Tools | Products | Owner | Status (%) | Comments
1 | timing | Router | Router timing | All | Rajesh | 0
2 |  |  | tb_str200_ly1_routersizes | All | Rajesh | 0
3 | timing | Streaming | Streaming Bridge timing of | Orion-NSIP | Rajesh | 0
4 | customer config |  | Customer config | Orion-NSIP | Rajesh | 0
5 |  |  | Example | Orion-NSIP | Rajesh | 0
6 | synthesis - RC |  | Synthesis logs reviewed, no errors. Warnings/exceptions are documented. | Orion-NSIP | Rajesh | 0
7 | synthesis - DC |  | DC/DCT run on Edna config | Orion-NSIP | Rajesh | 0
8 | Lint |  | Lint (HAL & Quartus) - Daily regressions | Orion-NSIP | Rajesh | 0
9 |  |  | tb_str3_ly8_bridge_codecov | Orion-NSIP | Rajesh | 0
10 |  |  | tb_str9_ly6_priority | Orion-NSIP | Rajesh | 0
11 | synthesis - FPGA |  | FPGA synthesis (Quartus) - Customer config | Orion-NSIP | Rajesh | 0
12 | synthesis - FPGA |  | FPGA synthesis (Vivado) - Customer config | Orion-NSIP | Rajesh | 0
13 | LEC |  | LEC on all synthesis | Orion-NSIP | Rajesh | 0
14 | synthesis - emulation |  | Emulator compile | Orion-NSIP | Rajesh | 0
15 | timing | AMBA | AMBA timing | Orion-AMBA | Rajesh | 0
16 |  |  | tb_axi5_slv6_syn_typ | Orion-AMBA | Rajesh | 0
17 |  |  | tb_axi5_slv6_syn_extrm | Orion-AMBA | Rajesh | 0
18 |  |  | tb_axi6_slv5_amba_supcfg_synth | Orion-AMBA | Rajesh | 0
19 | synthesis - RC |  | Synthesis logs reviewed, no errors. Warnings/exceptions are documented. | Orion-AMBA | Rajesh | 0 | Requested the team, did not hear back
20 | synthesis - DC |  | DC/DCT run on a config | Orion-AMBA | Rajesh | 0
21 | Lint |  | Lint (HAL & Quartus) - Daily regressions | Orion-AMBA | Rajesh | 0
22 |  |  | tb_axi5_slv5_amba_supcfg_lint | Orion-AMBA | Rajesh | 0
23 |  |  | tb_axi6_slv5_amba_supcfg_synth | Orion-AMBA | Rajesh | 0
24 |  |  | tb_axi9_ahblm4_axi3m1_axi4lm2_axi4m2_slv5_axi4ls3_ahbls2_ly1_regbus_addcomp_cg_multi_clock_eco_486421713_0306 | Orion-AMBA | Rajesh | 0
25 |  |  | tb_axi4_axi4m4_slv5_axi3s3_axi4s1_ly2_regbus_tunnel_addcomp_cg_multi_clock_eco_1336040710_0305 | Orion-AMBA | Rajesh | 0
26 |  |  | FPGA synthesis (Quartus) | Orion-AMBA | Rajesh | 0
27 |  |  | Customer Config | Orion-AMBA | Rajesh | 0
28 | synthesis - FPGA |  | FPGA synthesis (Vivado) | Orion-AMBA | Rajesh | 0
29 | LEC |  | LEC on all synthesis | Orion-AMBA | Rajesh | 0
30 | synthesis - emulation |  | Emulator compile | Orion-AMBA | Rajesh | 0 | did for JJ's emulation setup
31 | synthesis - RC |  | Verified that RC synthesis scripts run in release directory | All | Rajesh | 0
32 | synthesis - DC |  | Verified that DC synthesis scripts run in release directory | All | Rajesh | 0
33 | synthesis - RC |  | Synthesis for Multi-Clock AMBA and Streaming Noc's - check SDC files, Hier and Top (RC and DC) | All | Rajesh | 0
34 | CDC |  | CDC Checks for async clock crossings and other clks | All | Dawn | 0
35 | IPXACT |  | IPXACT Qual | All | Rajesh | 0
36 | Metrics |  | Physical Metrics generated, reviewed and posted | All | Rajesh | 0 | Metrics: record area, instances, freqency on synthesis output and compare with previous releases
37 | DEF |  | DEF File correctness | All | Rajesh | 0
38 | low power |  | CPF File correctness | All | Rajesh | 0
39 | low power |  | UPF File correctness | All | Rajesh | 0
40 | Lint - Spyglass |  | Lint - Spyglass | Gemini | Rajesh | 0
41 | CDC - Spyglass |  | CDC - Spyglass | Gemini | Rajesh | 0
42 | timing |  | timing | Gemini | Rajesh | 0
43 | synthesis - RC |  | synthesis - RC | Gemini | Rajesh | 0
44 | synthesis - DC |  | synthesis - DC | Gemini | Rajesh | 0
45 | Lint |  | Lint | Gemini | Rajesh | 0 | HAL
46 | synthesis - FPGA |  | synthesis - FPGA | Gemini | Rajesh | 0
47 | LEC |  | LEC | Gemini | Rajesh | 0
48 | synthesis - emulation |  | synthesis - emulation | Gemini | Rajesh | 0

## License, Beta Testing
Summary
Overall Status (%)
0
Task | Type | Customer facing checks | Products | Owner | Status (%) | Comments
1 | location | Release files (tar, docs) verified to be correct in release area | All | Anush | 0
2 | license | License file created for release | All | Alex | 0 | FlexLM default license file per product approved - made available for alpa & beta testing
3 | beta testing | Generated header from NocStudio always generates correct customer name | All | Support Team (Anush) | 0
4 | beta testing | Check quality of release tarball - try known customer configs | All | Support Team (Anush) | 0
5 | beta testing | Test tutorials and examples in tarballs | All | Support Team (Anush) | 0
6 | beta testing | product testing - negative and positive for license and config controlled features | All | John | 0
7 | Bugs - customer | Check if all the customer bugs are addressed in the release | All | Support Team (Anush) | 0 |  | moved from database tab

## Documentation
Summary
Overall Status (%)
0
Task | Type | Customer facing checks | Products | Owner | Status (%) | Comments
1 | doc | NocStudio User Manual - Orion NSIP: Content (Accuracy, Completness) | Orion-NSIP | Sailesh | 0
2 | doc | NocStudio User Manual - Orion AMBA & Gemini (Accuracy, Completness) | Orion-AMBA | Sailesh | 0
3 | doc | NocStudio Tutorial - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Nishant | 0
4 | doc | NocStudio Tutorial - Orion AMBA (Accuracy, Completness) | Orion-AMBA | Nishant | 0
5 | doc | NocStudio Tutorial - Gemini (Accuracy, Completness) | Gemini | Joe | 0
6 | doc | IP Integration Spec - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Kate | 0
7 | doc | IP Integration Spec - Orion AMBA & Gemini - includes LP (Accuracy, Completness) | Orion-AMBA | Kate | 0 | pull LP addendum in main doc for this release
8 | doc | IP Integration Spec (IMG4/2 addendum) - Orion AMBA (Accuracy, Completness) | Orion-AMBA | Kiran B | 0
9 | doc | IP Integration Spec - AMBA - UVM Testbench (Accuracy, Completness) | Orion-AMBA | Will | 0
10 | doc | NocStudio C++ Model - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Eric | 0
11 | doc | FPGA Flow Cookbook | All | Rajesh | 0 | No Change
12 | doc | Lint Waiver | All | Rajesh | 0 | Updated HAL and Spyglass Waivers
13 | doc | CDC Waiver | All | Dawn | 0
14 | doc | Physical Design Spec - Orion AMBA & Gemini (Accuracy, Completness) | Orion-AMBA | Rajesh | 0 | Updated
15 | doc | New - Spyglass waiver for IMG only | Orion-AMBA | Rajesh | 0 | Done - Added to Lint Waiver Doc
16 | doc | Physical Design Spec - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Rajesh | 0 | Now we have 1 chapter for PD which is common
17 | doc | NocStudio Cookbook - Gemini (Accuracy, Completness) | Gemini | Joe | 0
18 | doc | Release Notes - NSIP (Accuracy, Completness) | Orion-NSIP | Gloria/Joe/Jim/Sailesh/Nishant | 0
19 | doc | Release Notes - Gemini (Accuracy, Completness) | Gemini | Gloria/Joe/Jim/Sailesh/Nishant | 0 | includes AMBA
20 | doc | Router Microarch Spec (Accuracy, Completness) | Orion-NSIP | Joji | 0
21 | doc | Streaming Interface Protocol & Bridge Microarch Spec - Orion NSIP (Accuracy, Completness) | Orion-NSIP | Rajesh | 0 | No Change
22 | doc | AMBA Protocol Support (Accuracy, Completness) | All | Joji/Joe | 0
23 | doc | New Features and props/command change document input (Accuracy, Completeness) | All | Nishant/KiranA | 0
24 | doc | Netspeed Register Bus Protocol | All | Joji | 0
25 | doc | NocStudio User Manual - Orion NSIP: Formatting (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
26 | doc | NocStudio User Manual - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
27 | doc | NocStudio User Manual - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
28 | doc | NocStudio Tutorial - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
29 | doc | NocStudio Tutorial - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
30 | doc | NocStudio Tutorial - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
31 | doc | IP Integration Spec - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
32 | doc | IP Integration Spec - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
33 | doc | IP Integration Spec - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
34 | doc | IP Integration Spec - AMBA - UVM Testbench (Accuracy, Completness) | Gemini | Support Team (Anush) | 0
35 | doc | NocStudio C++ Model - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
36 | doc | FPGA Flow Cookbook | All | Support Team (Anush) | 0
37 | doc | Lint Waiver | All | Support Team (Anush) | 0
38 | doc | CDC Waiver | All | Support Team (Anush) | 0
39 | doc | Physical Design Spec - Orion AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
40 | doc | Physical Design Spec - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
41 | doc | Physical Design Spec - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
42 | doc | NocStudio Cookbook - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
43 | doc | Release Notes - NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
44 | doc | Release Notes - AMBA (Look&Feel, Versioning, etc.) | Orion-AMBA | Support Team (Anush) | 0
45 | doc | Release Notes - Gemini (Look&Feel, Versioning, etc.) | Gemini | Support Team (Anush) | 0
46 | doc | Router Microarch Spec (Look&Feel, Versioning, etc.) | All | Support Team (Anush) | 0
47 | doc | Streaming Interface Protocol & Bridge Microarch Spec - Orion NSIP (Look&Feel, Versioning, etc.) | Orion-NSIP | Support Team (Anush) | 0
48 | doc | AMBA Protocol Support (Look&Feel, Versioning, etc.) | All | Support Team (Anush) | 0
49 | doc | New Features and props/command change document (Look&Feel, Versioning, etc) | All | Support Team (Anush) | 0
50 | doc | Reg bus user manual | All | Support Team (Anush) | 0
51 | doc - App Notes | Qos Rate Limiter | All | Support Team (Anush) | 0
52 | doc - App Notes | RWC (Ericsson only) | All | Support Team (Anush) | 0
53 | location | Documents verified to be correct in release area | All | Support Team (Anush) | 0

## Customer TO
Summary |  | AGATHA TO checklist
Overall Status (%)
|  | ALL checks below - use customer configuration and run on customer branch |  |  | 0
|  | branch off trunk | https://subversion.assembla.com/svn/netspeed_noc/branches/agatha_release_0703_2015_38893
Task | Type | Customer Specific Tapeout Checks | Products | Owner | Status (%) | Comments
1 |  | customer TAPEOUT Config finalized | All | Joe | 0
2 |  | Coverage - line coverage reviewed/approved | Gemini | Joe | 0 |  | /rscratch/xavier/nc0dasak/agatha_release_0703_2015_38893/src/hw/ns_common/coverage_tcl/example_blocks/ns_soc_ip_06Jul2015/ html: file:///rscratch/xavier/nc0dasak/agatha_release_0703_2015_38893/src/hw/ns_common/coverage_tcl/example_blocks/ns_soc_ip_06Jul2015/merged_ns_soc_ip_inst_report_all/index.html
3 |  | Coverage - functional coverage reviewed/approved | Gemini | JJ | 0
4 |  | gatesim passes (pick 10-100 tests to give best coverage of regbus, network, etc. & external sanity testbench) | Gemini | Rajesh | 0
5 |  | CCC register tests pass | Gemini | Kate | 0
6 |  | DVM register tests pass | Gemini | Dasa | 0
7 |  | general noc register test pass | Gemini | Dasa | 0
8 |  | all bugs ported | Gemini | Joe | 0
9 |  | port trunk verif files to old branch | Gemini | JJ | 0
10 |  | port trunk synthesis files to old branch | Gemini | Rajesh | 0
11 |  | customer timing issues fixed | Gemini | Joe/Joji | 0
12 |  | ratio clk module ok and crossing has instances reviewed/approved | Gemini | Joe | 0
13 |  | lint clean | Gemini | Joe/Joji/Jaya/Rajesh | 0
14 |  | synthesis log clean (includes DFT issues) & synthesis contraint file reviewed | Gemini | Joe/Joji/Jaya/Rajesh | 0
15 |  | cherry pick hw changes from trunk to agatha branch | Gemini | Joe/Joji/Jaya/Rajesh | 0
16 |  | multicycle paths reviewed/approved (async/sync) | Gemini | Rajesh | 0
17 |  | async signals like reset, interrupts reviewed/approved | Gemini | Joe/Joji | 0
18 |  | CDC | Gemini | Sandip | 0
19 |  | physical checklist - only IPXACT | Gemini |  | 0
20 |  | emulation | Gemini | Rajesh | 0
21 |  | clk ratio diags pass | Gemini | Joe | 0
22 |  | review false paths | Gemini | Rajesh | 0
23 |  | reset spec reviewed/approved | Gemini | Joe/Joji/jim | 0
24 |  | remove clk gating logic | Gemini | Sandip | 0
25 |  | VCS | Gemini | Kate | 0