## Sheet1
Feature | Owner | Release impacted | Product Impacted? Crux/Orion/Gemini | Release Notes completed? | Chapter Impacted? | Documentation Completed? Yes/No | Target Date? | Todo | Comments
· NSPD-5 Bigger Grid – List as beta only | Akshay | ? |  |  |  | NA |  |  | Avoid it
NoC improvements | Nishant | all | C/O/G | yes |  | NA | 9/6/2016
· NSPD-7 Gemini Low Power Cleanup | JJ | all | G | yes | None | NA | NA | NocStudio need to ensure autowake only. Release notes needs to note that
· NSPD-86 Performance Test bench hooks | John | all | O/G | ph | New chapter in IP Integration Spec | Yes | this weekend 9/3/2016 | add chapter
· NSPD-8 Multi NoC | Kate | all | C/O/G | yes | see below | Yes | 9/2/2016 | add chapter | The new plan is to release the ns_multi_noc.pl script. So, the multinoc chapters need to be revised to describe how to use that script rather than how to construct a complete multinoc manually.
· NSPD-12,13,27 Clock Gating Improvements | Joji | all | O/G | ph |  | No | 9/2/2016
· NSPD-34, 36 Functional Safety updates | Joji | all | C/O/G | ph |  | No | 9/2/2016
· NSPD-14 Synchronizer Depth Programming (and FIFO sizing) | Dawn | all | C/O/G | yes | Several | Yes | NA
· NSPD-48 IMG4 | Dawn | IMG | G |  | None | NA | NA | Update release Notes for IMG4 | Only applies to release notes
· NSPD-15a System C Models - PV | Rocco | all | O | yes | New | Yes |  | Check product impact
· NSPD-69 Low Power: support SLV1 port of regbus tunnel (non blocking reg bus if) | Jim | all | O/G | yes | TRM_Low Power Support.docx | Yes | will try to update it today |  | Updated TRM and Release Notes
· NSPD-6 Fast Tap 256 bit data width | Joe | all | g | ph |  | No
· NSPD-38 Multi-cell-size NoCs | Joe | all | c | ph |  | No
· NSPD-49 LLC ScratchPad Interleaving | Joe | all | p | ph |  | No
· NSPD-52 Exclusive support in LLC | Joe | all | p | ph |  | No
· NSPD-54 LLC Read/Write Allocate Controls | Joe | all | p | ph |  | No
· NSPD-60 Traffic Class only affects first leg of transaction | Joe | all | o/g | ph |  | No
· NSPD-62 LLC Flush Engine | Joe | all | p | ph |  | No
· NSPD-63 LLC Indirect Access | Joe | all | p | ph |  | No
· NSPD-64 LLC Second Port for Memcache Latency/Area Opt | Joe | all | p | ph |  | No
· NSPD-85 Software overrides for system ADDR, ARID, etc. | Joe | all | o/g | ph |  | No
· NSPD-91 Remove a subset of ACE masters from DVM | Joe | all | g | ph |  | No
8.7 RESTICTIONS IN USING THE C++ MODELS
Multi-noc is currently un-tested and might break the models |  |  | C | yes
So the errata should stay in the 1609 release. Maybe remove the phrase “This will be addressed in the next release”? |  |  |  | yes
RR: Can you please clarify which chapter/sections you have updated?
KB:
IP_Integration of Multiple NoCs_Crux.docx
IP_Integration of Multiple NoCs_Gemini.docx
IP_Integration of Multiple NoCs_Orion.docx
2) New X/Z checks on signals. And mention X/Z checks on CSR's if not currently mentioned.
>>> X/Z checks on registers already mentioned.
RR: No documentation updates?
KB:
IP_NoC Verification Components_Crux.docx
4) LLC preloader.
>>> Added NocStudio generated files to table in introduction chapter at 64788(trunk)
RR: No documentation updates?
KB:
IP_Introduction.docx
IP_NoC Verification Components_Gemini.docx
IP_NoC Verification Components_Orion.docx
5) Add documentation for NS_GCT_VERBOSE_MODE and the GCT messages.
>>> Checked-in at 64768(trunk)
RR: Can you please clarify which chapter/sections you have updated?
KB:
IP_NoC Verification Components_Gemini.docx
KB: I also modified this at r64805,
IP_Low Power Support Integration.docx