## FeatureList-Status
2 | S.No | Feature No | Title | Documentation owner | customer impacted (All/Specific Customer) | Chapter impacted | Product impacted (C/O/G/P) | Documentation Status (Pending/Done) | Release Notes | custom_field[priority_level] | custom_field[release_owner_gatekeeper] | workflow_status | custom_field[customerseval_lead] | workflow_kind | custom_field[feature_driver] | Crux | Orion | Gemini | Pegasus | Priority Level | Yes | Status | release for 6.12 | work in Q4 16 | Impl complexity | arch owner | rtl owner | HW verif owner | NocStudio owner | SW Verif | Comment
| 1 | NSPD-103 | NocStudio: Multidie support in iNocStudio | [6 empty] | 0_Customer Commit | Sailesh | Not started | Isabelle | Customer request | Customer request | No | No | No | No |  |  |  | n | y | high | Sailesh | n/a |  | Nishant
| 2 | NSPD-104 | NocStudio: Perf sim improvement (40K cycles/sec loaded) | [6 empty] | 0_Customer Commit | Sailesh | Not started | Quennie | Customer request | Customer request | [7 empty] | n | y | high | Sailesh | n/a |  | eric
| 3 | NSPD-105 | IPXACT improvement | [6 empty] | 1_High | Jim | Not started | Isabelle | Customer request | Customer request | [7 empty] | n | n | high
| 4 | NSPD-106 | NocStudio: Machine learning | [6 empty] | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | n | y | high | Sailesh | n/a | n/a | Nishant/Pier
| 5 | NSPD-107 | NocStudio: Shared BW specification | [6 empty] | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | n | n | high | Sailesh | n/a | n/a | Nishant
| 6 | NSPD-114 | Prefetcher Support | [6 empty] | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | joe | joe | kate | Nishant
| 7 | NSPD-115 | Coherency IP Error Handling | Joe | All |  |  | NA | NA | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | y | y | med | joe | joe | jj | n/a | n/a | Joe: This is not done for 1612
| 8 | NSPD-37 | Large Wrap Requests (above 64B) | [6 empty] | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes |  |  |  | n | y | high | joe | joe | jj | n/a
| 9 | NSPD-110 | DMA Engine | [6 empty] | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | n | high | joji | joji | jj | ?
| 10 | NSPD-65 | Page Locality Enhancement | [6 empty] | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | joe | joe | jj | n/a
| 11 | NSPD-112 | Synchronizer Depth in Crux | [6 empty] | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | y: n; y: n; med: med
| 12 | NSPD-113 | DFT Hooks for LLC RAMs | [6 empty] | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | joe | joe | ? | Nishant
| 14 | NSPD-118 | Integrating CCC & LLC | [6 empty] | 1_High | Joe | Not Started | Xenna, charlotte | Eval request | Eval request | No | No | Yes | Yes |  |  | Release with Errata | n | y | high | joe | joe | jj | Nishant
| 15 | NSPD-101 | Multi level coherency | [6 empty] | 1_High | Joe | Not Started | Xenna, charlotte | Eval request | Eval request | No | No | Yes | Yes |  |  | Release as Alpha | n | y | high | joe | joe | jj | Nishant
| 15 | NSPD-75 | Per-interface layer connectivity (software only) | [6 empty] | 3_Low | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | y | low | n/a | n/a | n/a | Sailesh
| 16 | NSPD-102 | CCIX support | [6 empty] | 1_High | Joe | Not Started | Xenna, charlotte | Eval request | Eval request | No | No | Yes | Yes |  |  | Release as Beta | y: n; y: n; med: high
| 17 | NSPD-79 | CSR Security Requirements Gemini | [6 empty] | 1_High | Joe | Not started |  | Usability enhancement | Usability enhancement | No | No | Yes | Yes |  |  |  | n | y | low | joe | joe | kate | n/a
| 18 | NSPD-116 | LLC: Byte Enable Storage Support (caching partial lines) | [6 empty] | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes | bar: y to y
| 19 | NSPD-82 | NocStudio: Improve Clock Crossing Software UI | [6 empty] | 2_Mid | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | n | med | n/a | n/a | n/a | Akshay | n/a
| 20 | NSPD-89 | Deinterleaver Split size control | [6 empty] | 1_High | Joji | Not started | Harriet | Customer request | Customer request | No | Yes | Yes | No |  |  |  | n | n | med | joji | joji | kate | Nishant
| 21 | NSPD-11b | Regbus Clock Gating (ring master/slave, CSR) | [6 empty] | 1_High | [12 empty] | n | n | high | joji | joji | ? | eric
| 22 | NSPD-129 | CCC configurable QOS overrides | Rajesh | All |  |  | Done | Done | 3_Low | [12 empty] | y | y | low | Joe | Joe | jj | nishant | y | few props. Control qos for generated and flowthrough commands. See the nocstudio props for CCC.
| 23 | NSPD-121 | AXI multi-cell size to -1 |  | All |  |  |  |  | 3_Low | [12 empty] | y: n; y: y; jj: won; n/a: pier
| 24 | NSPD-122 | CCC preloading (1_High) |  | All |  |  |  |  | ? | [12 empty] | y: n; y: y; jj: jj; n/a: Nishant
| 25 | NSPD-123 | Low power support for NOC middle hops (2_med) |  | All |  |  |  |  | ? | [12 empty] | y: n; y: n; n/a: eric
| 26 | NSPD-124 | Clock gating bugs in NSIP (1_high) |  | All |  |  |  |  | ? | [12 empty] | n | n |  |  | joji | won | n/a
| 27 | NSPD-125 | Clock gating checkers and stimulus completion (all products) |  | All |  |  |  |  | 3_Low | [12 empty] | n | n |  |  | all | won | n/a
| 28 | NSPD-126 | ACE Bridge for Master port of Coherent cluster |  | All |  |  |  |  | 2_Mid | [12 empty] | n | y | high | joe | joji | jj | Nishant
| 29 | NSPD-127 | CHI Bridge for Master port of Coherent cluster |  | All |  |  |  |  | 2_Mid | bar: y to y
| 30 | NSPD-128 | Broadcast, multicast support - Hardware |  | All |  |  |  |  | 3_Low | [12 empty] | n | n | high | Joe | joji | jj | eric
| 31 | NSPD-15b | NocStudio: System C Models - AT |  | All |  |  |  |  | 1_High | Sailesh | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  |  | y: n; y: y; joe: n/a; n/a: akshay
| 32 | NSPD-16 | Trace and Debug: debug fencing |  | All |  |  |  |  | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | 1_High | No | In Implementation | n | n |  | jim | dawn | santosh
| 33 | NSPD-108 | Async clock crossing improvements | Akshay | All |  |  | NA | Done | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | y | y | med | n/a | n/a | n/a | Akshay | need info
| 34 | NSPD-18 | Trace and Debug: segregate regbus address space |  | All |  |  |  |  | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | 3_Low | No | Nearly Done | n | n | high | jim | dawn | Kiran B | eric
| 36 | NSPD-109 | Deadlock Avoidance Unit (PCI/ACE deadlock) | Rajesh |  | 1.12 DAU in TRM_Functional Description Coherency Components |  | Done | Done
| 36 | NSPD-109 | Deadlock Avoidance Unit (PCI/ACE deadlock) update User Manual | Rajesh | All | Added new chapter 1.3.5 DAU in UM |  | Done |  | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | y | y | low | joe | joe | jj | Nishant | y
| 37 | NSPD-20 | Trace and Debug: trace transport across NoC |  | All |  |  |  |  | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | 16.09 release |  | Done | n | n |  | jim | dawn | santosh
| 38 | NSPD-21 | UPF Support |  | All |  |  |  |  | 2_Mid | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | bar: y to y
| 39 | NSPD-22 | user sideband for Crux |  | All |  |  |  |  | 2_Mid | Joji | In Implementation | Isabelle | Customer request | Customer request | Yes | No | No | No | bar: y to y
| 40 | NSPD-23 | Bridge Latency Reduction (Rresp bypass width conv) |  | All |  |  |  |  | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes | bar: y to y
| 41 | NSPD-11 | Regbus Clock Gating ( CSR) |  | All |  |  |  |  | 1_High | Joji | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  |  | n | n | med | joji | joji | Won | n/a | n/a
| 42 | NSPD-26 | Clock Gate Fast Wakeup |  | All |  |  |  |  | 2_Mid | Joe | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes | bar: n n to n n
| 43 | NSPD-28 | Fast Path RX bypass |  | All |  |  |  |  | 2_Mid | Joe | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | y | med | joji | joji | kate | eric
| 44 | NSPD-29 | Fast Tap Pipelining |  | All |  |  |  |  | 2_Mid | Joe | Not started | Harriet | Eval request | Eval request | No | No | Yes | Yes |  |  |  | n | y | high | joe | joe | jj | Nishant
| 45 | NSPD-30 | Fast Tap to multiple CCCs |  | All |  |  |  |  | 2_Mid | Joe | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes | bar: n n to n n
| 46 | NSPD-111 | RAM module (modified LLC) TRM | Rajesh | All |  |  | NA | NA | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | y | y | high | joe | joe | jj | Nishant | y | add_ram… lcc has a slave and a master port. LLC for scratchpad without master port, but other exclusive support. Remove tag/ miss queue logic, master port.
| 45 | NSPD-111 | RAM module (modified LLC) Update User Manual | Nishant |  |  |  | NA | NA | bar: n joji; n n/a
| 48 | NSPD-117 | Streaming bridge enhancements | Joji | All |  |  | NA | NA | 3_Low | [12 empty] | y | y | high | joji | Joji | joji | eric | n/a | not user visible based on Joji's feedback
| 49 | NSPD-35 | Functional Safety: Packet Checksum |  | All |  |  |  |  | 2_Mid | Joji | Not started | Ingrid/M | Customer request | Customer request | Yes | Yes | Yes | Yes | N/A |  | HW Done; Waiting for SW | n | n | med | joji | Joji | Won | pier
| 50 | NSPD-119 | Functional safety: ECC and Parity | Joji | All |  |  | NA | NA | 0_Customer Commit | [12 empty] | y | y | high | joji | joji | Ben | pier | n/a | no new featrue. Only DV work.
| 51 | NSPD-4 | AHB master area reduction |  | All |  |  |  |  | 1_High | Joe | Not Started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes |  |  |  | n | y | high | perry | Perry | ? | n/a
| 52 | NSPD-40 | NocStudio: Hierarchical NoCs |  | All |  |  |  |  | 2_Mid | John | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes | bar: y to y
| 53 | NSPD-41 | NocStudio: Host behavior modelling (DDR) |  | All |  |  |  |  | 1_High | Sailesh | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes | bar: y to y
| 54 | NSPD-120 | Regbus verification support | Won | All |  |  | NA | NA | 0_Customer Commit | [12 empty] | y | y | med | n/a | n/a | Won | pier | n/a
| 55 | NSPD-17 | Trace and Debug: master bridge trace probe | Jim | All |  |  | NA | NA | 0_Customer Commit | Jim | In Implementation | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | 2_Mid | No | Partial Support | y | y | high | jim | dawn | Kiran B | eric | y
| 56 | NSPD-43 | Read Data Interleave Support |  | All |  |  |  |  | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes | bar: n y to n y
| 57 | NSPD-45 | Virtual Interface for Master Bridge |  | All |  |  |  |  | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes | bar: n y to n y
| 58 | NSPD-47 | Directory Disable (convert to snoop only) |  | All |  |  |  |  | 2_Mid | Joe | Not started | Agatha | Customer request | Customer request | No | No | Yes | Yes | bar: n y to n y
| 59 | NSPD-50 | NocStudio: Incremental NoC construction / freezing |  | All |  |  |  |  | 2_Mid | Eric | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | bar: n y to n y
| 60 | NSPD-53 | Expressway (variant of fast-bypass, but with arbitration) |  | All |  |  |  |  | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes | bar: n y to n y
| 61 | NSPD-55 | NocStudio Perf Sim: Model bridge skip between ccc/llc |  | All |  |  |  |  | 2_Mid | Sailesh | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes | bar: n y to n y
| 62 | NSPD-56 | NocStudio Perf Sim: RTL vs NocStudio correlation |  | All |  |  |  |  | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | n y: n; n y: y; n n/a: n/a; n pier: Reza
| 63 | NSPD-56 | NocStudio Perf Sim: Model snoop traffic capability |  | All |  |  |  |  | 2_Mid | Sailesh | Not started | Ingrid | Eval request | Eval request | No | No | Yes | Yes | bar: n y to n y
| 64 | NSPD-57 | NocStudio: Host Model import (IPXACT) |  | All |  |  |  |  | 2_Mid | Sailesh | Not started | Nella | Eval request | Eval request | No | Yes | Yes | Yes | bar: n y to n y
| 65 | NSPD-59 | Sideband wire reduction |  | All |  |  |  |  | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes | bar: n y to n y
| 66 | NSPD-61 | 32 port router |  | All |  |  |  |  | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | Yes | Yes | Yes | Yes | bar: n y to n y
| 67 | NSPD-19 | Trace and Debug: slave bridge trace probe | Jim | All |  |  | NA | NA | 0_Customer Commit | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | N/A | No | Debugging | y | y | high | jim | dawn | Kiran B | eric | y
| 68 | NSPD-66 | Low Power: Multi-Voltage for ACE bridges |  | All |  |  |  |  | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes | bar: n y to n y
| 69 | NSPD-67 | Low Power: Multi-Voltage in NoC |  | All |  |  |  |  | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes | bar: n y to n y
| 70 | NSPD-68 | Low Power: remaining tune_power fixes |  | All |  |  |  |  | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes | bar: n y to n y
| 71 | NSPD-70 | Low Power: support user regbus |  | All |  |  |  |  | 2_Mid | Jim | Debugging | Ingrid | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n y: n; n y: n; n Won: santosh
| 72 | NSPD-71 | NocStudio: AMBA Bridge perf modelling in perf sim |  | All |  |  |  |  | 2_Mid | Sailesh | In Implementation | Harriet | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n y: n; n y: y; n n/a: n/a
| 73 | NSPD-24 | Change CR/CD to put CR on sideband | Joji | All |  |  | NA | Done | 2_Mid | Joe | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes |  |  |  | y | y | low | joji | joji | joji | Nishant | y
| 74 | NSPD-73 | Width Conversion info returned from Slave Bridge (PPA) |  | All |  |  |  |  | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | No | bar: n y to n y
| 75 | NSPD-74 | 8 interfaces streaming bridge (today 4 interfaces avail) |  | All |  |  |  |  | 3_Low | Joe | Not started | Isabelle | Customer request | Customer request | Yes | No | No | No | bar: n y to n y
| 76 | NSPD-32 | Frequency Target: 1066MHz | Joji | All |  |  | NA | NA | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes |  |  |  | y | y | low | n/a | all | n/a | n/a | n/a | Internal timing improvements
| 77 | NSPD-76 | Reorder Bridge (ace, ace-lite, axi, LP) |  | All |  |  |  |  | 3_Low | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes | bar: n y to n y
| 78 | NSPD-77 | Reorder bridge: Remove AID table |  | All |  |  |  |  | 3_Low | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes | bar: n y to n y
| 79 | NSPD-78 | APB access with no tunnel (and NSIP) |  | All |  |  |  |  | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | y | low |  | dawn | ben | pier
| 80 | NSPD-33 | Functional Safety: CSR Parity | Joji | All |  |  | Done | Done | 0_Customer Commit | Joji | Not started | Ingrid/M | Customer request | Customer request | Yes | Yes | Yes | Yes |  | Maybe | SW Done; Waiting for HW | y | y | low | joe | Joji | won | pier | y
| 81 | NSPD-80 | Interrupt Register Default Properties (bridges, IP) |  | All |  |  |  |  | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes | bar: y to y
| 82 | NSPD-81 | Mesochronous Cleanup |  | All |  |  |  |  | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes | bar: y to y
| 83 | NSPD-42 | OCP: Master Bridge (1_high) | Perry | All |  |  | Done | Done | 0_Customer Commit | Perry | In Implementation | Isabelle | Customer request | Customer request | No | Yes | Yes | Yes |  |  | HW, SW Done; Waiting for Verif | y | y | high | perry | Perry | Kiran B | will | n/a
| 84 | NSPD-83 | Priority Address Map: Negative Address Ranges |  | All |  |  |  |  | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes | bar: y to y
| 85 | NSPD-84 | regbus master/tunnel port selections |  | All |  |  |  |  | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes | bar: y to y
| 86 | NSPD-88 | Support of max outstanding different from Reorder Buffer depth |  | All |  |  |  |  | 1_High | Joji | Not started | Harriet | Customer request | Customer request | No | Yes | Yes | No | bar: y to y
| 87 | NSPD-42b | OCP: Slave Bridge (1_high) | Perry | All |  |  | NA | NA | 0_Customer Commit | Perry | In Implementation | Isabelle | Customer request | Customer request | No | Yes | Yes | Yes |  |  | Waiting for spec | y | y | high | perry | Perry | Kiran B | will | n/a | Babu: Not in 1612
| 88 | NSPD-90 | Virtual Interface Configurable Data/Split size |  | All |  |  |  |  | 1_High | Joji | Not started | Harriet | Customer request | Customer request | No | Yes | Yes | No | bar: y to y
| 89 | NSPD-72 | SIB Multiple bridges in same location | Nishant | All |  |  | NA | NA | 2_Mid | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | y | y | med | n/a | n/a | kiran B | Nishant | y | Is not tested. This should not be added to release.
| 90 | NSPD-91 | FPGA Friendly: Modify components Agatha Cyclone 5 targets | Joji | All |  |  | NA | NA | 0_Customer Commit | Joji | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | No | No | 0_Customer Commit | No | Not Started | y | y | med | n/a | joji | n/a | n/a | n/a | This is only preliminary work to optimize for FOGA flow. Next release might have more details to document
| 91 | NSPD-93 | Functional Safety: End-to-end ecc, parity |  | All |  |  |  |  | 1_High | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | joe | joji | ? | pier
| 92 | NSPD-94 | Functional Safety: Parity with ECC |  | All |  |  |  |  | 1_High | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | joe | joji | ? | pier
| 93 | NSPD-95 | Functional Safety: User bits through the system |  | All |  |  |  |  | 1_High | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | joe | joji | ? | pier
| 94 | NSPD-92 | Functional Safety: ECC on RAM Index |  | All |  |  |  |  | 0_Customer Commit | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | Joe | Joe | JJ | pier | y
| 95 | NSPD-96 | Broadcast, multicast support for Queenie - Software | Eric | All |  |  | NA | Done | 0_Customer Commit | Sailesh | Not started | Quennie | Customer request | Customer request | Yes | No | No | No |  |  | Waiting for resource | y | y | high | Sailesh | n/a | n/a | eric | n/a
| 96 | NSPD-98 | CHI (Latest rev) Master Support |  | All |  |  |  |  | 1_High | Joe | In Implementation | Nella | Eval request | Eval request | No | No | Yes | Yes |  |  | Release | n | y | high | joe | Joji | ? | nishant
| 97 | NSPD-99 | CHI (Latest rev) Slave Support |  | All |  |  |  |  | 1_High | Joe | In Implementation | Nella | Eval request | Eval request | No | No | Yes | Yes |  |  | Release | n | n | high | joe |  |  | nishant
| 98 | NSPD-134 | Snowflakes support |  | All |  |  |  |  | 0_Customer Commit | Eric | Not started | Quennie | Customer request | Customer request | Yes | No | No | No |  |  |  | y | y | med | Eric | n/a | JJ | eric | y
| 99 | NSPD-130 | LLC Error Handling: No allocation on error | Joe | All |  |  | NA | NA | 3_Low | [12 empty] | y | y | low | Joe | Joe | jj | n/a | n/a | This is more of a fix than a feature. No need to expose this to customers. allocate on read, allocate space and allocate data. If data is bad due to slave error put it in the cache. And future reads woul get corrupted data. Not allocation error
| 100 | NSPD-131 | Per node clock delay | Eric | All |  |  | NA | Done | 3_Low | [12 empty] | y | y | low | n/a | n/a | n/a | Eric | y
| 101 | NSPD-132 | Warning hiding / control | Eric | All |  |  | NA | Done | 3_Low | [12 empty] | y | y | low | n/a | n/a | n/a | Eric | y
| 102 | NSPD-133 | define/defcmd macros | Eric | All |  |  | NA | Done | 3_Low | [12 empty] | y | y | med | n/a | n/a | n/a | Eric | y
| 101 | NSPD-135 | MultiNOC Deadloack Analysis Support | Sailesh | All |  |  | Done | Done | 0_Customer Commit | [12 empty] | y | y | med | Sailesh | n/a | n/a | Sailesh | y
Other updates |  |  | Reset consolidation | Jim |  |  |  | Done | Done | bar: n/a Joe n/a n/a n/a to eric n/a Eric Eric Eric
Other updates |  |  | nsps grouping | Jim |  |  |  | Done | Done | bar: n/a Joe n/a n/a n/a to eric n/a Eric Eric Eric
Other updates |  |  | clarify ns_acmb_rrob_regfile in noc_modifiable_rtl | John |  |  |  | Done | NA | bar: n/a Joe n/a n/a n/a to eric n/a Eric Eric Eric
Other updates |  |  | ICCC | Rajesh | All |  |  | Pending | Done | [21 empty] | Waiting for feedback from Joe | bar: n/a Joe n/a n/a n/a to eric n/a Eric Eric Eric
Other updates |  |  | ICCC Update User Manual | Nishant |  |  |  | Done | bar: n/a Joe n/a n/a n/a to eric n/a Eric Eric Eric
Other updates |  |  | map_opt improvements | Nishant |  |  |  | NA | Pending | bar: n/a Joe n/a n/a n/a to eric n/a Eric Eric Eric
Other updates |  |  | router arbitration change - enable_round_robin | Nishant |  |  |  | NA | Pending | bar: n/a Joe n/a n/a n/a to eric n/a Eric Eric Eric
Other updates |  |  | Updated Weighted BW | Ono | All |  |  | Done | NA
Other updates |  |  | Specific NoC Construction Improvements | Nishant |  |  |  | NA | NA | [21 empty] | Nishant: Nothing to be called out specifically
Other updates |  |  | GUI Enhancements - Per Node clock delay | Akshay |  |  |  | NA | Done
Other updates |  |  | Update Programmers Model chapters | Alex |  |  |  | Pending | NA
Review |  |  | Erratas | Alex |  |  |  | NA | Pending
Review |  |  | Update Changes_to_Commands_and_Properties under trunk__doc\release_docs\Release Notes\1612 | Nishant |  |  |  | NA | Done
Review |  |  | Review Installation chapter | Alex |  |  |  | NA | Pending
Review |  |  | Review Deliverables cahpter | Alex |  |  |  | NA | Pending
Review |  |  | Review EDA chapter | Alex |  |  |  | NA | Pending
Review |  |  | Ree Review Tab | Rajesh |  |  |  | Pending | Pending
Note on AB43: CSR - low ring master/slave - hig
Note on D82: LLC MDA waived

## Review
Anush Release Noets
Gemini
Done | 1 – TRM should not be a sub-bullet of b. It should be item #c in the list
Done | 3.1 GUI enhancements – Is it really just 1 enhancement ? If it is, then it is better to add it as a sub-bullet under 3.4 and remove the GUI enhancement section
Done | 3.2 Multi-NoC Deadlock Analysis: If we are mentioning this in the release notes, we need more documentation on how users are going to be using this. Alternatively, if Tesla is the only customer for this feature, we need to remove this from the release notes
Done | 3.6 User defined command – Have you looked at the help menu for this. Is it good ?
Done | 4.1 OCP – OCP is a beta feature; Remove it from the general release notes
Pending | 5.1 – map_opt has gone through bunch of bug fixes. Need a section here
Done | Typos – There are typos in 5.1, 5.4, 5.5 that need to be fixed. Please run spell check on the final version
Done | 5.3, 5.4 – Please add following sentence at the end of paragraph – “Please note that this IP block requires a special license key for access”
Done | 10 – This entire section needs to be revisited. Commands/props related to following should not be listed in the release notes
ICCC
DAU
OCP
Trace & Debug
Items missing from the release notes
Pending | Router arbitration change (The enable_round_robin prop that is mentioned in 10.8)
Orion
Done | Most comments on Gemini apply here
Done | 4.1 OCP – OCP is a beta feature; Remove it from the general release notes
Done | 8 – Remove following commands/props related to:
OCP
Items missing from the release notes
Pending | Router arbitration change
Crux
Done | 3.3 - Do we really support functional safety for Crux ?
Pending | 3.4, 3.7, 3.8 – Do these apply to Crux ?
Done | 3.9 – Definitely does not apply to Crux
Done | 4.1 – Multicast is meant only for Qualcomm and is not part of the general release; Please remove
Done | 8 – Remove following commands/props related to:
Multicast
Done | 8.9 – VC prop changes: I only see a link instead of contents
Items missing from the release notes
Pending | Router arbitration change

## Analysis
Count - S.No | workflow_status
custom_field[priority_level] | (empty) | Debugging | In Implementation | Not started | Total Result
1_High | 1 |  | 2 | 26 | 29
2_Mid | 2 | 1 | 2 | 24 | 29
3_Low |  |  |  | 4 | 4
0_Customer Commit | 2 |  | 3 | 8 | 13
? | 3 |  |  |  | 3
Total Result | 8 | 1 | 7 | 62 | 78