## FeatureList-Status
2 | S.No | Aha No | name | priority_level | Release commit | release_owner | Project Impacted | Chapter Impacted | Documentation Status | Comments | Release Notes Status | workflow_status | customer | workflow_kind | feature_driver | Crux | Orion | Gemini | Pegasus | Priority Level | Yes | Status
| 1 |  | SRAMs of different physical dimesions instantiating same module | 2_Mid | No | eric |  |  | Pending |  | Pending | [8 empty] | 0_Customer Commit | No | Not Started
| 2 |  | FPGA readiness - Qsys support | 1_High | No | Babu | NA | separate Altera FPGA cookbook | Pending | Not part of general release | NA | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | Yes | Yes | 1_High | No | In Implementation
| 3 |  | Integrating NoCs from different NocStudio releases | 1_High | No | Babu |  | NA only Release Note | NA | Only Release Note |  | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | 2_Mid | No | Partial Support
| 4 |  | NocStudio: Host Model import (IPXACT) | 1_High | No | Babu |  |  | NA | May/Maynot do incremental work |  | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | Yes | Yes | 3_Low | No | Nearly Done
| 5 |  | Max outstanding different from Reorder Buffer depth | 1_High | No | Babu |  |  | NA | Need further investigation |  | Not Started | Sarah | Customer request | Customer request | No | Yes | Yes | Yes | N/A | Next Rel | Debugging
| 6 |  | AHB bridge improvement (Area, AHB5) | 2_Mid | No | Bob |  |  | NA |  | Done | Not Started | Sarah | Customer request | Customer request | No | Yes | Yes | Yes | 17.04 release |  | Done
| 7 |  | 32 port router | 2_Mid | No | Babu | [5 empty] | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | Dropped | Maybe | SW Done; Waiting for HW
| 8 |  | Reorder bridge | 2_Mid | Next Rel | Babu | [5 empty] | Not Started | Sarah | Eval request | Eval request | No | Yes | Yes | Yes | N/A |  | HW Done; Waiting for SW
| 9 |  | Inode Stamping support | 0_Customer Commit | Yes | eric |  | Separate Addendum/App Note | Done | Separate Addendum/App Note | NA
| 10 |  | Tcl interface to NoCStudio | 1_High | Yes | eric |  |  | NA - in Help |  | Done | [10 empty] | HW, SW Done; Waiting for Verif
| 11 |  | Trace & Debug thelma release | 0_Customer Commit | Yes | Jim | NA | App Note - $SVN/trunk/doc/release_docs/Releasable Internal Docs/Master Docs/NetSpeed IP Integration Spec Addendum - Trace Probe | Done | App Note - $SVN/trunk/doc/release_docs/Releasable Internal Docs/Master Docs/NetSpeed IP Integration Spec Addendum - Trace Probe | NA | Not Started | Thelma | Customer request | Customer request | No | Yes | Yes | Yes
| 12 |  | Snowflakes support | 1_High | No | eric |  |  | NA |  |  | Not Started | Quennie | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  | Waiting for spec
| 13 |  | Regfile support for LLC, CCC,IOCB | 0_Customer Commit | yes | John |  |  | Done |  | Done | [10 empty] | Waiting for resource
| 14 |  | FuSa: ECC on RAM Index | 0_Customer Commit | No | joe | G |  | Pending | Need to syncup with Joe | Done | [10 empty] | Release
| 15 |  | Low power support for NOC middle hops | 2_Mid | No | jim | [15 empty] | Release
| 16 |  | CCC Pre-loader | 1_High | No | JJ |  |  | NA | Next Release |  | Not Started | Ingrid | Customer request | Customer request | No | No | Yes | Yes |  |  | Release with Errata
| 17 |  | RAMs outside of the NoC | 1_High | No | Joe |  |  | Pending |  |  | Not Started | Xena | Customer request | Customer request | No | No | No | Yes |  |  | Release as Alpha
| 18 |  | CHI Support - Gemini | 1_High | No | Joe |  |  | Pending |  |  | Not Started | Nella | Customer request | Customer request | No | No | Yes | Yes |  |  | Release as Beta
| 19 |  | CSR Security Requirements Gemini | 1_High | No | joe |  |  | Pending
| 20 |  | Non-coherent traffic going through CCC | 0_Customer Commit | Yes | Joe | Not Started | Peggy | NA | Beta feature. | NA
| 21 |  | LLC: Byte Enable Storage Support (caching partial lines) | 0_Customer Commit | No | joe | G/P |  | Pending | Need to syncup with Joe | Pending
| 22 |  | 512bit IOCB support (remove Wack) | 1_High | yes | Joe |  |  | Done | Need to syncup with Joe | Done
| 23 |  | NocStudio - RTL vs. Perf sim accuracy improvement (Inputs from Sarah) | 1_High | No | John |  |  | NA | Dirty Laundry. John "Agree with Ono, definitely seems like dirty laundry we don’t want to list in the release notes as it would open up a whole load of other awkard questions". Ono "In the past, RTL had some bubbles during the arbitration while S/W assumes 100% utilization. The issues which exist in 16.12 and are expected to be fixed are 1. Latency mismatch through clock domain crossing 2. store&forward (maybe)" | NA | Not Started | Sarah | Eval request | Eval request | Yes | Yes | Yes | Yes
| 24 |  | FuSa:Parity on registers (LLC, DVM) | 2_Mid | No | joe
| 25 |  | NocStudio: DDR & Agent modeling | 2_Mid | Yes | John |  | John working on separate App Note | Pending - App note (John) | John working on separate App Note | NA | Not Started | Mabel | Customer request | Customer request | Yes | Yes | Yes | Yes
| 26 |  | Pegasus - AXI user bits transfer support | 2_Mid | Next Rel | Joe | [5 empty] | Not Started | Sarah | Eval request | Eval request | No | No | No | Yes
| 27 |  | Pegasus - Read & invalidate | 2_Mid | Next Rel | Joe | [5 empty] | Not Started | Sarah | Eval request | Eval request | No | No | No | Yes
| 28 |  | Pegasus - Write-through support | 2_Mid | Next Rel | Joe | [5 empty] | Not Started | Xena | Customer request | Customer request | No | No | Yes | Yes
| 29 |  | Prefetcher Support | 3_Low | No | joe |  |  | Pending |  | Pending |  | Sarah | Eval request | Eval request | No | No | No | Yes
| 30 |  | FuSa - Interface parity check | 0_Customer Commit | Yes | joji |  |  | Done | Interface Parity | Done | Not Started | Isabelle | Customer request | Customer request | Yes | No | No | No
| 31 |  | Isabelle: Perf counters/register updates | 0_Customer Commit | Yes | joji |  |  | NA | There is a bug on JIRA | Done | Not Started | Sarah | Eval request | Eval request | No | Yes | Yes | Yes
| 32 |  | Asymetric rd & wr width sizes | 0_Customer Commit | yes | joji |  |  | NA |  | Done
| 33 |  | Regfile support for reorder buffers - 2 port regfile | 1_High | Yes | John |  |  | Done |  | Done | Not Started
| 34 |  | Memory controller deadlock fix - HW | 1_High | yes | joji |  | Only Release Note | Done | Only Release Note | Done
| 35 |  | ROB (Reorder Bridge) for Orion (Non LP) | 0_Customer Commit | Yes | Kiran |  | winnie | Done |  | Done
| 36 |  | SRAM/Regfile support for reorder buffers - 1&2 port SRAM | 1_High | Next Rel | joji
| 37 |  | CHI Support - Xilinx | 1_High | No | Joe | NA | Separate documentation for Xilinx | Pending - Xena documentation (John) | Separate documentation for Xilinx | NA | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | Yes | Yes
| 38 |  | Split size enhancement | 2_Mid | No | joji
| 39 |  | Clock gating bugs in NSIP | 2_Mid | No | joji
| 40 |  | Flop structure parity - All FIFOs, non FIFOs in Bridges (ASIL) | 2_Mid | No | joji |  |  | Pending - Documentation (Joji) |  | Pending
| 41 |  | End to End ECC Data (ASIL) | 2_Mid | No | joji
| 42 |  | Page Locality Enhancement | 2_Mid | Next Rel | joji
| 43 |  | Interface Parity including the R5/R7 (ASIL) - NS implementation | 2_Mid | No | joji |  |  | Pending |  | Pending
| 44 |  | Virtual AXI: Adding VCs on transmit side | 2_Mid | Next Rel | joji
| 45 |  | Width Conversion info returned from Slave Bridge (PPA) | 2_Mid | Next Rel | joji | [6 empty] | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes
| 46 |  | FuSa - Packet checksum | Dropped | no | joji | [5 empty] | Not Started
| 47 |  | Memory controller deadlock fix - SW | 1_High | yes | Nishant |  | Only Release Note | NA | Only Release Note | Done |  | Isabelle | Customer request | Customer request | No | Yes | Yes | No
| 48 |  | OCP - Master and slave support | 2_Mid | No | Perry |  |  | NA | Same as 1609. Maybe available for eval purposes | NA | Not Started | Thelma | Customer request | Customer request | No | Yes | Yes | Yes
| 49 |  | SystemC support - AT models (Orion) | 0_Customer Commit | No | Sailesh |  |  | Pending |  | Done | Not Started | Isabelle | Internal | Internal | No | Yes | Yes | Yes
| 50 |  | Machine learning based build - Gemini | 0_Customer Commit | Yes | Sailesh |  | Only Release Note | NA | Only Release Note | Done | Not Started | Isabelle | Internal | Internal | Yes | Yes | No | No
| 51 |  | Machine learning based build - Orion | 0_Customer Commit | Yes | Sailesh |  | Only Release Note | NA | Only Release Note | Done | Not Started | Thelma | Customer request | Customer request | Yes | Yes | Yes | Yes
| 52 |  | SystemC support - AT models (Gemini) | 1_High | No | Sailesh |  |  | Pending | This most probably will not make it | Pending | Not Started | Thelma | Customer request | Customer request | No | Yes | Yes | Yes
| 53 |  | SystemC support - Cache models for Pegasus & Directory | 1_High | No | Sailesh |  |  | Pending | This most probably will not make it | Pending | Not Started
|  |  | Commands and Properties | 0_Customer Commit | Yes | x-Nishant |  |  | NA | Nishant working on this. Will close closer to the release date | Pending
|  |  | NoC Improvements | 0_Customer Commit | Yes | x-Nishant |  |  | NA | I synced up with Sailesh on the below topics. NoC Improvements: No updates here. The only updates related to NoC construction are in machine learning (I think you have 2 separate rows for this). We’ll have a new command for it but there isn’t too much else to explain apart from how to use the command. We don’t want to be exposing how we do machine learning or what techniques are used there. | NA
|  |  | GUI Enhancements | 0_Customer Commit | Yes | x-Nishant |  |  | NA | GUI Enchancements: Currently no changes here. This quarter the main focus has been on improving the stability of the GUI and fixing various bugs. | NA |  | Isabelle | Customer request | Customer request | No | Yes | Yes | Yes
| 57 |  | OCP sanity test bench support | 2_Mid | Next Rel | Will | [5 empty] | Not Started
| 58 |  | Bridge Latency Reduction (Rresp bypass width conv) | 2_Mid | Next Rel
| 59 |  | NocStudio: Hierarchical NoCs | 2_Mid | Next Rel
| 60 |  | NocStudio: Incremental NoC construction / freezing | 2_Mid | Next Rel
| 61 |  | NocStudio: Sideband wire reduction | 2_Mid | Next Rel
| 62 |  | Regbus Clock Gating (ring master/slave, CSR) | 2_Mid | Next Rel
| 63 |  | SIB Multiple bridges in same location | 2_Mid | Next Rel
| 64 |  | T&D: debug fencing | 2_Mid | Next Rel
| 65 |  | T&D: segregate regbus address space | 2_Mid | Next Rel
| 66 |  | T&D: trace transport across NoC | 2_Mid | Next Rel
| 67 |  | ECC checking for directory control buffer (ASIL) | 2_Mid | Next Rel
| 68 |  | Constant parameter arrays - parity (ASIL) | 2_Mid | Next Rel
| 69 |  | CCC – Snoop Queue parity protection (ASIL) | 2_Mid | Next Rel
| 70 |  | LLC – SPRT storage parity protection (ASIL) | 2_Mid | Next Rel
| 71 |  | DMA Engine | 3_Low | Next Rel
| 72 |  | UPF Support | 3_Low | Next Rel
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
90
90

## FeatureList-Owners
2 | S.No | Aha No | name | priority_level |  | release_owner | workflow_status | Arch Owner | SW Owner | SW Verif Owner | HW Owner | HW Verif Owner | Priority Level | Yes | Status
| 1 |  | SRAMs of different physical dimesions instantiating same module | 2_Mid | No | eric |  | Joe | Nishant | Nishant | Joe | JJ | 0_Customer Commit | No | Not Started
| 2 |  | FPGA readiness - Qsys support | 1_High | No | Babu | Not Started | Joe | Nishant | Nishant | Joe | JJ | 1_High | No | In Implementation
| 3 |  | Integrating NoCs from different NocStudio releases | 1_High | No | Babu | Not Started | Bob |  |  |  |  | 2_Mid | No | Partial Support
| 4 |  | NocStudio: Host Model import (IPXACT) | 1_High | No | Babu | Not Started | Perry | Eric | Eric | Perry | Kiran | 3_Low | No | Nearly Done
| 5 |  | Max outstanding different from Reorder Buffer depth | 1_High | No | Babu | Not Started | [5 empty] | N/A | No | Debugging
| 6 |  | AHB bridge improvement (Area, AHB5) | 2_Mid | No | Bob | Not Started | [5 empty] | 16.09 release |  | Done
| 7 |  | 32 port router | 2_Mid | No | Babu | Not Started | [6 empty] | Maybe | SW Done; Waiting for HW
| 8 |  | Reorder bridge | 2_Mid | Next Rel | Babu | Not Started | [5 empty] | N/A |  | HW Done; Waiting for SW
| 10 |  | Tcl interface to NoCStudio | 1_High | Yes | eric | [8 empty] | HW, SW Done; Waiting for Verif
| 12 |  | Snowflakes support | 1_High | No | eric | Not Started | [7 empty] | Waiting for spec
| 13 |  | Regfile support for LLC, CCC,IOCB | 0_Customer Commit | yes | John | [8 empty] | Waiting for resource
| 14 |  | FuSa: ECC on RAM Index | 0_Customer Commit | No | joe | [8 empty] | Release
| 15 |  | Low power support for NOC middle hops | 2_Mid | No | jim | [8 empty] | Release
| 16 |  | CCC Pre-loader | 1_High | No | JJ | Not Started | [7 empty] | Release with Errata
| 17 |  | RAMs outside of the NoC | 1_High | No | Joe | Not Started | [7 empty] | Release as Alpha
| 18 |  | CHI Support - Gemini | 1_High | No | Joe | Not Started | [7 empty] | Release as Beta
| 30 |  | FuSa - Interface parity check | 0_Customer Commit | Yes | joji | Not Started
| 19 |  | CSR Security Requirements Gemini | 1_High | No | joe
| 20 |  | Non-coherent traffic going through CCC | 0_Customer Commit | Yes | Joe
| 21 |  | LLC: Byte Enable Storage Support (caching partial lines) | 0_Customer Commit | No | joe
| 24 |  | FuSa:Parity on registers (LLC, DVM) | 2_Mid | No | joe
| 25 |  | NocStudio: DDR & Agent modeling | 2_Mid | Yes | John | Not Started
| 22 |  | 512bit IOCB support (remove Wack) | 1_High | yes | Joe
| 26 |  | Pegasus - AXI user bits transfer support | 2_Mid | Next Rel | Joe | Not Started
| 27 |  | Pegasus - Read & invalidate | 2_Mid | Next Rel | Joe | Not Started
| 28 |  | Pegasus - Write-through support | 2_Mid | Next Rel | Joe | Not Started
| 31 |  | Isabelle: Perf counters/register updates | 0_Customer Commit | Yes | joji | Not Started
| 32 |  | Asymetric rd & wr width sizes | 0_Customer Commit | yes | joji
| 35 |  | ROB (Reorder Bridge) for Orion (Non LP) | 0_Customer Commit | Yes | Kiran
| 38 |  | Split size enhancement | 2_Mid | No | joji
| 39 |  | Clock gating bugs in NSIP | 2_Mid | No | joji
| 40 |  | Flop structure parity - All FIFOs, non FIFOs in Bridges (ASIL) | 2_Mid | No | joji
| 41 |  | End to End ECC Data (ASIL) | 2_Mid | No | joji
| 42 |  | Page Locality Enhancement | 2_Mid | Next Rel | joji
| 43 |  | Interface Parity including the R5/R7 (ASIL) - NS implementation | 2_Mid | No | joji
| 44 |  | Virtual AXI: Adding VCs on transmit side | 2_Mid | Next Rel | joji
| 45 |  | Width Conversion info returned from Slave Bridge (PPA) | 2_Mid | Next Rel | joji
| 46 |  | FuSa - Packet checksum | Dropped | no | joji | Not Started
| 47 |  | Memory controller deadlock fix - SW | 1_High | yes | Nishant
| 48 |  | OCP - Master and slave support | 2_Mid | No | Perry | Not Started
| 49 |  | SystemC support - AT models (Orion) | 0_Customer Commit | No | Sailesh | Not Started
| 50 |  | Machine learning based build - Gemini | 0_Customer Commit | Yes | Sailesh | Not Started
| 51 |  | Machine learning based build - Orion | 0_Customer Commit | Yes | Sailesh | Not Started
| 52 |  | SystemC support - AT models (Gemini) | 1_High | No | Sailesh | Not Started
| 53 |  | SystemC support - Cache models for Pegasus & Directory | 1_High | No | Sailesh | Not Started
|  |  | Commands and Properties | 0_Customer Commit | Yes | x-Nishant
|  |  | NoC Improvements | 0_Customer Commit | Yes | x-Nishant
|  |  | GUI Enhancements | 0_Customer Commit | Yes | x-Nishant
| 57 |  | OCP sanity test bench support | 2_Mid | Next Rel | Will | Not Started
| 58 |  | Bridge Latency Reduction (Rresp bypass width conv) | 2_Mid | Next Rel
| 59 |  | NocStudio: Hierarchical NoCs | 2_Mid | Next Rel
| 60 |  | NocStudio: Incremental NoC construction / freezing | 2_Mid | Next Rel
| 61 |  | NocStudio: Sideband wire reduction | 2_Mid | Next Rel
| 62 |  | Regbus Clock Gating (ring master/slave, CSR) | 2_Mid | Next Rel
| 63 |  | SIB Multiple bridges in same location | 2_Mid | Next Rel
| 64 |  | T&D: debug fencing | 2_Mid | Next Rel
| 65 |  | T&D: segregate regbus address space | 2_Mid | Next Rel
| 66 |  | T&D: trace transport across NoC | 2_Mid | Next Rel
| 67 |  | ECC checking for directory control buffer (ASIL) | 2_Mid | Next Rel
| 68 |  | Constant parameter arrays - parity (ASIL) | 2_Mid | Next Rel
| 69 |  | CCC – Snoop Queue parity protection (ASIL) | 2_Mid | Next Rel
| 70 |  | LLC – SPRT storage parity protection (ASIL) | 2_Mid | Next Rel
| 71 |  | DMA Engine | 3_Low | Next Rel
| 72 |  | UPF Support | 3_Low | Next Rel
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Analysis
Project Status |  | Architecture Owners |  | SW Owners |  | SW Verif Owners |  | HW Owners |  | HW Verif Owners
Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No
Not Started | 28 | Bob | 1 | Eric | 1 | Eric | 1 | Joe | 2 | JJ | 2
(blank) | 59 | Joe | 2 | Nishant | 2 | Nishant | 2 | Perry | 1 | Kiran | 1
Grand Total | 87 | Perry | 1 | (blank) | 87 | (blank) | 87 | (blank) | 87 | (blank) | 87
|  | (blank) | 86 | Grand Total | 90 | Grand Total | 90 | Grand Total | 90 | Grand Total | 90
|  | Grand Total | 90