## LP V2 Phase3 Verif Schedule
Item | Feature / Task | Sub-Feature / Sub-task / Bug | Owner | Effort Estimate | Start Date | End Date | % Completed | Dependency | Comments/Remarks
Testplan | Multi voltage HW LP Testplan |  | Vishnu Won | 8 | 2015-10-21 | 2015-10-26 | 10% | Spec | Dependant on Jim MV spec updates coming by 10/23
| Multi voltage SW LP Testplan |  | Vishnu | 3 | 2015-10-23 | 2015-10-27 | 100% |  | VD and PD assignments and for NS generated CPFs and RTL etc.,
| LP functional coverage plan |  | Vishnu | 5 | 2015-10-28 | 2015-11-03 | 70%
| Regbus layer HW LP Testplan |  | Vishnu Ben | 6 | 2015-10-12 | 2015-10-14 | 90% | Needs feedback (Rajesh + Ben + Santhosh) | Testplan on Regbus, w/ tunnel slv0 and slv1, Host config bridges, w/ autowake (vishnu) and error scenarios (vishnu)
| Regbus layer SW LP Testplan |  | Vishnu | 3 | 2015-11-04 | 2015-11-06 | 100% |  | Power domain assignments to Regbus elements Clock domain assignments to Regbus elements Ring assignments based on clock and power domains Tunnel, rbm/m and rbm/s power domain assignments
Nemesis | Nemesis (Automated) regbus traffic | Bugs 3803, 3804 and 3824 | Ben | 20 | 2015-09-21 | 2015-10-16 |  |  | from REGXTOR through Tunnel on both slv0 and slv1 ports to Host config bridges Autowake traffic Dynamic configuration of QoS values
| Nemesis to support power domains more than 32 | Bug 3771 | Santhosh | 2 | 2015-10-06 | 2015-10-07 | 100% |  | Currently Nemesis limits to maximum 32 power domains only
IMG2 only | IMG bridge LP nemesis support |  | Santhosh |  |  |  |  | KiranB needs to enable IMG2 and IMG4 in internal testbench | Estimate will be given after Jim update on spec by 10/20
| Meta bridge LP nemesis support |  | Santhosh | low_priority | low_priority | low_priority | low_priority | Spec | Estimate will be given after Jim update on spec by 10/23 As per Anush/Jim discussion as on 2015_10_28, this can be low priority for Q4 release.
| Re-order bridge LP nemesis support |  | Santhosh | low_priority | low_priority | low_priority | low_priority | Jim to close with Gloria | Estimate will be given after Jim discussion with Gloria on this. As per Anush/Jim discussion as on 2015_10_28, this can be low priority for Q4 release.
NocWeaver | Automated ECO mode testing for power domain assignments | Bug 3799 | Santhosh |  |  |  |  | Won to close on whether to support for Q4 release | NoC layer routers Regbus layer elements non-lp eco mode features impacting LP tune_power etc.,
| Multi voltage NW LP support |  | Santhosh | 5 | 2015-10-19 | 2015-10-23 | 100% |  | All changes are in Nocweaver. Need to start enabling them
| Regbus layer NW LP support |  | Santhosh | 3 | NA | NA | NA | Jim to decide whether this is required for Q4 | Only host config bridges support to be done in NW regbus
| Assign NoC node PD and VD usage |  | Santhosh | 5 | 2015-10-13 | 2015-10-19 | 100% |  | As per Jim, assign_noc_node_voltage_domain is not going to be supported
| NSPS position, clk and PD assignment |  | Santhosh | 3 | 2015-10-08 | 2015-10-12 | 100% |  | Bug 3882 is gating NSPS clk enabling . All nocweaver changes are done
| Property coverage monitor |  | VinayPatel | 5 | 2015-10-20 | 2015-10-26
TB | Host PDs modelling in TB top.cpf | Bugs 3812 and 3814 | Vishnu | 5 | 2015-09-21 | 2015-09-25 | 100% |  | Injecting X's on NoC input ports
| testbench.cpf for UVM bench |  | Yogesh Vishnu | 3 |  |  |  |  | Yogesh to provide start date on this
| External or TB clock gating implementation | Bug 3800 | Vishnu | 5 | 2015-11-09 | 2015-11-13 | 50% |  | Won's gen_StreamX changes will be done by 10/19 Vishnu to see if this can be done before 9-Nov
| Gen_StreamX changes for per power domain clocks integration in top.v |  | Won | 3 | 2015-10-15 | 2015-10-19 | 100% |  | Won: 2015_10_29: Final bugs have been fixed.
| External or TB global reset control per power domains or entire NoC | Bug 3793 | Vishnu | 3 | 2015-10-19 | 2015-10-21 | 50%
| Gen_StreamX changes for per power domain resets integration in top.v |  | Won | 3 | 2015-10-16 | 2015-10-19 | 100%
| Gen_StreamX changes for Multi voltage NoC stitching |  | Won | 2 | 2015-10-19 | 2015-10-20 | 90% |  | Won: 2015_10_29: Apart from the delivery of first MV config with gsX fixes, no progress has been made
QREQ Stagger | Implementing bugs raised during KT |  | Vishnu | 10 | 2015-11-16 | 2015-11-27 | 25% |  | Enhancement related bugs during KT meetings on SYNC, PP switching etc.,
Checkers | Multi voltage functional LP checkers |  | Vinayendra | 7 | 2015-10-24 | 2015-11-02 |  | Won to come up with testplan
| Regbus layer LP element level checkers | Bugs 3802, 3840 and 3842 | Vinayendra | 3 | 2015-09-30 | 2015-10-02 | 80% | Bugs on Rajesh - more checks | Ring master Ring slave Tunnel Host config bridges
| Regbus layer Isolation checkers |  | Vinayendra | 5 | 2015-10-05 | 2015-10-14 | 100%
| Q-channel LP checker to be part of UVM bench | Bug 3820 | Yogesh | 1 | 2015-10-16 | 2015-10-16 |  |  | Mostly going to work as per Yogesh
| Element, NSPS and Isolation checkers compatabile for UVM |  | Yogesh | 3 | 2015-10-14 | 2015-10-16 |  |  | Mostly going to work as per Yogesh
| MB element level additional LP checks | Bug 3080, Bug 3947 and few more yet to be filed | Vinayendra | 5 | 2015-10-14 | 2015-10-20 | 70% | self-fence check | PD checks per QOS path checks + cleanup
| Checkers to be VCS compatible |  | Vinayendra | 3 | 2015-10-21 | 2015-10-23 | 100%
Coverage | LP functional coverage |  | VinayPatel Vinayendra | 20 | 2015-10-19 | 2015-11-16 | 70% | Vishnu to come up with functional coverage plan | NoC layer elements Regbus layer elements NSPS Q-channel
| Code coverage |  | VinayPatel | 20 | 2015-10-26 | 2015-11-20 |  |  | Come up with handwritten and NW generated configs and also with nemesis modifications for maximum coverage
Tools | Conformal-LP on Multi voltage |  | Vishnu Won | 7 | 2015-10-29 | 2015-11-06 | 20% |  | Jim/Rajesh to give template cpfs on the multi voltage by 10/19 to Pier/Anup
| Lint |  | Rajesh |  | 2015-10-20 | 2015-12-01 |  | Daily run on NW LP configs
| CDC |  | Dawn |  | 2015-10-20 | 2015-12-01
| RC |  | Rajesh |  | 2015-11-06 | 2015-12-01 |  | Selected configs
Q2+ Pending | Verification of all pending design bugs |  | Vinayendra Santhosh VinayPatel Vishnu | 5 | 2015-10-20 | 2015-10-26 | 75% | only autowake remains | Autowake (HW) AHBLM (HW) credit_inc flow during sleep_ack (HW)