## LP V2 Phase3 Feature Status
Feature No. | Feature Name | Sub Feature | Sub-Feature / Sub-task / Bug No. Description | HW Dev Effort Estimate | HW Dev Start Date | HW Dev End Date | HW Dev Owner | SW Dev Effort Estimate | SW Dev Start Date | SW Dev End Date | SW Dev Owner | HW Verif Effort Estimate | HW Verif Start Date | HW Verif End Date | HW Verif Owner | SW Verif Effort Estimate | SW Verif Start Date | SW Verif End Date | SW Verif Owner
1 | Fix outstanding bugs | a | Bug 3381 - Allow NoC elements in host-only PDs. |  |  |  | NA | 0.5 | Done | Done | Pier |  |  |  | Santhosh | 2.5 |  |  | InfoNam
1 | Fix outstanding bugs | b | Bug 3558 - Clock pins:bring out 1 clock pin per power domain |  |  |  | NA | 1 | Done | Done | Pier |  |  |  | Won | 1 |  |  | InfoNam
1 | Fix outstanding bugs | c | Bug 3748 - SDC tracking: Ratio clock domains should be in the same clock group as their NoC clock domains |  |  |  | Rajesh | 2 | Done | Done | Pier |  |  |  | NA | 0.5 |  |  | Bhumesh
1 | Fix outstanding bugs | d | Bug 3793 - Reset_n: implement per power domain |  |  |  | NA | 1 |  |  | Pier |  |  |  | Won | 1 |  |  | InfoNam
1 | Fix outstanding bugs | e | Fencing Atomicity and Other AXI bridge fencing corner cases |  |  |  |  | ? |  |  | Anup
1 | Fix outstanding bugs | e.i | Atomicity for splits: Bug 3171, Bug 3672 |  |  |  | Joji | NA |  |  | Anup |  |  |  | Vishnu | 0.5 |  |  | InfoNam
1 | Fix outstanding bugs | e.ii | Autowake interdependency when downstream PD is same as master PD |  |  |  | Jim | ? |  |  | Anup |  |  |  | Vishnu | 1 |  |  | InfoNam
1 | Fix outstanding bugs | e.iii | Probably requires a minor change to PD assignment done by NocStudio |  |  |  | Jim | ? |  |  | Anup |  |  |  | Vishnu | 0.5 |  |  | InfoNam
1 | Fix outstanding bugs | f | Bug 3763 - Output credit_inc high after sleep_ack_n - local fix, RTL only, no SW impact |  |  |  | Joji | NA | NA | NA | NA |  |  |  | Vishnu | NA | NA | NA | NA
1 | Fix outstanding bugs | g | AHBLM - several outstanding bugs (Bugs 3540, 3692, 3723, 3724, 3727, 3729, 3733) |  |  |  | Perry | NA | NA | NA | NA |  |  |  | Vishnu | NA | NA | NA | NA
1 | Fix outstanding bugs | h | Bug 3882 - clk_nsps needs to be created explicitly to drive NSPS |  |  |  | NA | 1 | Done | Done | Pier |  |  |  | Won | 1.5 |  |  | InfoNam
1 | Fix outstanding bugs | i | Bug 3890 - Low Power: provide option to prevent creation of NSPS for always_on power domains |  |  |  | NA | 1 |  |  | Pier |  |  |  | Santhosh | 2 |  |  | InfoNam
1 | Fix outstanding bugs | j | Bug 3948 - Replace global PD ids in the ns_power_map_table with local PD ids |  |  |  | NA | 1 | Done | Done | Pier | 2 | Done | Done | Vinay | NA | NA | NA | NA
1 | Fix outstanding bugs | k | Synthesis and other physical design related issues (SDC and DEF generation, particularly with RTL grouping) |  |  |  | Rajesh | ? |  |  | Pier/Anup |  |  |  | NA | 1 |  |  | Bhumesh
2 | RTL Grouping |  | RTL Grouping to include agents - flatten hierarchy so everything including agents appears below ns_fabric and will support power domain grouping. |  |  |  | NA | 0 | NA | NA | Yes |  |  |  | Won | NA | NA | NA | NA
3 | Multi-Voltage | a | Properly implement voltage domain boundaries at non-compound (AXI) host/bridge interfaces (fix incomplete Q2+ implementation) |  |  |  | Joji | Done |  |  | Eric |  |  |  | Won
3 | Multi-Voltage | a.i | Properly reset both sides of segregated FIFO to cleanly restore operation after power state changes |  |  |  | Joji | Done |  |  | Eric |  |  |  | Won | NA | NA | NA | NA
3 | Multi-Voltage | a.ii | Implement proper fencing/draining & sleep_req_n/sleep_ack_n around this VD boundary FIFO (need wrapper logic) |  |  |  | Joji | ? |  |  | Eric |  |  |  | Won | NA | NA | NA | NA
3 | Multi-Voltage | a.iii | Work out how to specify voltages and clocks in NocStudio to be able to properly generate CPF to infer correct level shifting structures. |  |  |  | Jim | 3 |  |  | Anup |  |  |  | Won | NA | NA | NA | NA
3 | Multi-Voltage | a.iv | Update CPF (and UPF) to properly infer level shifters. |  |  |  | Jim | 2 |  |  | Anup |  |  |  | Won | 2 |  |  | Bhumesh
3 | Multi-Voltage | a.v | Any special treatment required for SDC? |  |  |  | Rajesh | ? |  |  | Pier |  |  |  | NA | 0.5 |  |  | Bhumesh
4 | Regbus | a | Support arbitrary clocking on regbus layer (eliminate regbus_clk, treat regbus layer like all others) |  |  |  | Rajesh | 1 | Done | Done | Pier |  |  |  | Won | 4 |  |  | InfoNam
4 | Regbus | b | Ring-master PD should be same as that of the router attached to it, see LP spec |  |  |  | Rajesh | 1 |  |  | Anup |  |  |  | Santhosh | 1 |  |  | InfoNam
4 | Regbus | c | Bug 4063: Regbus Master NoC clock domain: does not support async interface on NoC link to first hop regbus router… noc_clk == host_clk. - Fix this. |  |  |  | Rajesh | NA | NA | NA | NA |  |  |  | Ben | NA | NA | NA | NA
5 | Sanity bench (external) | a | Implement basic LP support in UVM bench |  |  |  | NA | NA | NA | NA | NA |  |  |  | Yogesh | NA | NA | NA | NA
5 | Sanity bench (external) | b | Include some LP transactors and additional checkers to facilitate explicit testing of LP functionality (IMG really wants this). |  |  |  | NA | NA | NA | NA | NA |  |  |  | Yogesh | NA | NA | NA | NA
6 | QDENY implementation | a | Review QDENY implementation, possibly refine it - if we have no compelling need to assert QDENY, I'm thinking we should disable this path in the FSM. For Phase 3, need to consider if we should at least implement a property that allows this behavior to be switched in NS config. |  |  |  | Jim | NA | NA | NA | NA |  |  |  | Vishnu | NA | NA | NA | NA
7 | Clock Gating | a | For Phase 3, we need to at minimum define and articulate plans to IMG for how we intend to address the following within next release. Implementation deferred to next phase. |  |  |  | Jim | NA | NA | NA | NA |  |  |  | Won | NA | NA | NA | NA
7 | Clock Gating | a.i | Overhaul coarse grained clock gating to make sure it works as intended. |  |  |  | Jim | NA | NA | NA | NA |  |  |  | Won | NA | NA | NA | NA
7 | Clock Gating | a.ii | Resolve any issues (e.g., coding style, lack of clock enable, etc.) that prevent synthesis from achieving acceptable fine grained inferred clock gating. |  |  |  | Jim | NA | NA | NA | NA |  |  |  | Won | NA | NA | NA | NA
8 | DEF support for NSPS |  | IMG would like to see explicit placement info for NSPS. |  |  |  | YT | NA | NA | NA | NA |  |  |  | NA | NA | NA | NA | NA
9 | NSPS for always_on PDs | a | Bug 3890 - Low Power: provide option to prevent creation of NSPS for always_on power domains. If this is easy, we should slip this in into phase3. |  |  |  | Jim | 0.5 |  |  | Anup |  |  |  | Vishnu | 1 |  |  | InfoNam
Legend: Red = must have (required by Ingrid or otherwise very important) Orange = highly desirable (might become "must have" depending on Ingrid decisions) Blue = Desirable or needs marketing input Green = less important/stretch Black = probably not within next release).
Note on L2: Kiran Adduri: High HW Verif impact. Pier provided a patch.
Note on L3: Kiran Adduri: Pier provideda patch
Note on L6: Kiran Adduri: Waiting for input from Jim on whether something needs to be done, and what needs to be done. Based on that effort estimate will be given.
Note on L7: Kiran Adduri: Waiting for input from Jim on whether something needs to be done, and what needs to be done. Based on that effort estimate will be given. 11/3: Jim : Not sure what is required from SW team for this. Joji: Nothing needed from SW team. We are not waiting for any SW changes for Atomicity related issues. No SW changes needed.
Note on L8: Kiran Adduri: Waiting for input from Jim on whether something needs to be done, and what needs to be done. Based on that effort estimate will be given. 11/3: Jim: We finally bottomed-out on what needs to be done. Will require NS to calculate the time-out parameter for the PD state machine. Documented on the confluence page. At this point, just need to communicate to SW team what needs to be done. Jim and Anup will setup a meeting in the next one or two days to discuss what needs to be done by SW team.
Note on L9: Kiran Adduri: Waiting for input from Jim on whether something needs to be done, and what needs to be done. Based on that effort estimate will be given.
Note on L12: Kiran Adduri: Pier provided a patch.
Note on L13: Kiran Adduri: High HW Verif impact. Jim has not yet defined the design, so deferred.
Note on L14: Kiran Adduri: Pier provided a patch.
Note on L15: Kiran Adduri: CPF and DEF, Anup will take care of it. 10/26: There is a meeting called for tomorrow, where this effort estimate will also be discussed. 11/3: Anup: Rajesh or Jim shoulld be able to comment. Jim: For now there are no known changes for synthesis. Rimu: When we have parallel signals (as opposed to only one signal crossing the VD) that cross VDs, do we need to have any special handling for delay matching ? Jim: Not that we are aware of, if there are any specific concerns we can look into the issues. Joji: Start point and End point are in one domain, but there is some combo logic in the other domain. The way NS currently generates SDC file content is per pin, The timing paths will only be shown at the top level. Not very sure how SDC constraints are specified when the write path and read path are in separate domains. Rajesh's opinion is: THis should work at top level as is without any changes needed to the way NS generates SDC. AI on Rajesh : Won/Joji: Block level synthesis and the correctness of SDC files for this is still open. Rajesh will need to take a look at this. If STA tool run is done that is a good first step, tryin to run GLS with timing annotations would require a lot more setup. AI on Rajesh : A top level timing run either in RC or STA tool (Tempus) from cadence.
Note on L17: Kiran Adduri: Eric mentioned earlier, this is mostly done.
Note on L19: Kiran Adduri: Jim: On RTL side Joji. On SW side, Jim will work with Eric. Joji: The HW design part can be targeted for the next 2 days. Then Joji can take a SW patch from Eric and work with that. Kiran: Any HW verif changes for this ? Won: There should be significant changes/additions to checkers to comprehend the new fencing and draining changes.
Note on I22: Kiran Adduri: 10/26: Some of it is onion peeling, some of it we'll figure out in tomorrow's meeting.
Note on L23: Kiran Adduri: Pier provided a patch. 10/26: Won: So far we checked that the patch does no harm. Next step is to test that the patch does what it is supposed to do.
Note on B29: Kiran Adduri: IMG (and probably other customers) is expecting to see high 90's percentiles (has indicated competition achieves 99%) clock gating efficiency.
Note on B30: Kiran Adduri: IMG (and probably other customers) is expecting to see high 90's percentiles (has indicated competition achieves 99%) clock gating efficiency.
Note on B31: Kiran Adduri: IMG (and probably other customers) is expecting to see high 90's percentiles (has indicated competition achieves 99%) clock gating efficiency.
Note on I33: Kiran Adduri: HW Verif might be somewhat open ended.