## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Complete
Phase1 M1 | 53 days | Mon 23-02-15 | Wed 06-05-15 |  |  | 100%
RTL Design | 53 days | Mon 23-02-15 | Wed 06-05-15 |  |  | 100%
Micro-arch document | 3 days | Mon 23-02-15 | Wed 25-02-15 |  | Joji,Rimu | 100%
MB changes | 5 days | Thu 09-04-15 | Wed 15-04-15 |  | Joji | 100%
SB and RTR changes | 5 days | Thu 16-04-15 | Wed 22-04-15 | 3,4 | Rimu | 100%
Isolation LP Control signals to low | 1 day | Thu 23-04-15 | Thu 23-04-15 | 4,5 | Joji | 100%
V1 arch RTL cleanup in the design | 5 days | Thu 30-04-15 | Wed 06-05-15 | 6 | Rimu,Joji | 100%
NSPS: | 5 days | Thu 23-04-15 | Wed 29-04-15 |  |  | 100%
Aggregation logic | 2 days | Tue 28-04-15 | Wed 29-04-15 | 10 | Rimu | 100%
PDS | 3 days | Thu 23-04-15 | Mon 27-04-15 | 4,5 | Rimu | 100%
Gen_ip: | 34 days | Wed 11-03-15 | Mon 27-04-15 |  |  | 100%
Valid traffic flow with PD information | 3 days | Wed 11-03-15 | Fri 13-03-15 |  | Anup | 100%
Valid traffic flow with CD information | 2 days | Mon 20-04-15 | Tue 21-04-15 |  | Anup | 100%
Cleanup of V1 architecture code | 1 day | Thu 16-04-15 | Thu 16-04-15 |  | Eric | 100%
Cleanup for REGBUS | 2 days | Fri 17-04-15 | Mon 20-04-15 | 14 | Eric | 100%
V2 Architecture integration | 2 days | Fri 24-04-15 | Mon 27-04-15 | 15,6,4,5 | Eric | 100%
Tune_power: | 6 days | Tue 21-04-15 | Tue 28-04-15 |  |  | 100%
Cleanup for REGBUS | 1 day | Tue 21-04-15 | Tue 21-04-15 |  | Sailesh | 100%
Support for V2 architecture | 5 days | Wed 22-04-15 | Tue 28-04-15 | 18 | Sailesh | 100%
TB XTOR Sync changes | 6 days | Tue 17-03-15 | Tue 24-03-15 |  |  | 100%
SYNC_UNIT design | 2 days | Mon 23-03-15 | Tue 24-03-15 |  | Harsha | 100%
CXT changes for sync | 2 days | Tue 17-03-15 | Wed 18-03-15 |  | Joe | 100%
AHBXTOR changes for sync | 1 day | Thu 19-03-15 | Thu 19-03-15 |  | Jaya | 100%
AMBAXTOR (Sanity) changes for sync | 1 day | Fri 20-03-15 | Fri 20-03-15 |  | Joe | 100%
PMXTOR design | 6 days | Wed 11-03-15 | Wed 18-03-15 |  | Vishnu | 100%
GenStreamX changes for LP TB integration | 3 days | Mon 04-05-15 | Wed 06-05-15 | 11,20,25 | Santhosh | 100%
Test/Coverage Plan | 7 days | Mon 02-03-15 | Tue 10-03-15 |  | Vishnu | 100%
Phase1 M2 | 18 days | Mon 20-04-15 | Wed 13-05-15 |  |  | 98%
Isolation of output ports to low | 4 days | Fri 08-05-15 | Wed 13-05-15 |  | Joji | 100%
AXI4 GenCPF: | 8 days | Wed 22-04-15 | Fri 01-05-15 |  |  | 100%
Cleanup for REGBUS | 1 day | Wed 22-04-15 | Wed 22-04-15 | 13 | Anup | 100%
Changes from pin-level to PD level Iso rules | 1 day | Thu 23-04-15 | Thu 23-04-15 | 31 | Anup | 100%
RTL grouping | 5 days | Fri 24-04-15 | Thu 30-04-15 | 32 | Anup | 100%
Tech and Lib pointers | 1 day | Fri 01-05-15 | Fri 01-05-15 | 33 | Anup | 100%
CLP scritps | 2 days | Mon 04-05-15 | Tue 05-05-15 | 30 | Harsha | 100%
Nemesis traffic generation | 10 days | Mon 20-04-15 | Fri 01-05-15 |  |  | 100%
SYNC_UNIT traffic generation * | 1 day | Mon 20-04-15 | Mon 20-04-15 |  | Santhosh | 100%
Power and Clock gating/enabling * | 5 days | Tue 21-04-15 | Mon 27-04-15 | 37 | Santhosh | 100%
Cold boot randomization * | 2 days | Tue 28-04-15 | Wed 29-04-15 | 38 | Santhosh | 100%
Error scenarios for LP * | 2 days | Thu 30-04-15 | Fri 01-05-15 | 39 | Santhosh | 100%
AXI4 LP Checkers work | 4 days | Thu 07-05-15 | Tue 12-05-15 |  |  | 100%
Element level LP checker | 2 days | Thu 07-05-15 | Fri 08-05-15 | 11,26,30 | Vinay | 100%
Power Domain level Isolation LP checker | 2 days | Thu 07-05-15 | Fri 08-05-15 | 11,26,35,30 | Harsha | 100%
NSPS PD Sequence LP checker | 2 days | Mon 11-05-15 | Tue 12-05-15 | 43,11,26,30 | Santhosh[25%],Harsha[75%] | 100%
CLP and LPS AXI4 hand written cfgs passing | 5 days | Thu 07-05-15 | Wed 13-05-15 | 11,17,26,35,20,25,30 | Vishnu[50%] | 100%
Test/Coverage Plan Review | 2 days | Thu 23-04-15 | Fri 24-04-15 |  | Vishnu | 65%
Phase1 M3 | 18 days | Mon 04-05-15 | Wed 27-05-15 |  |  | 88%
NS integration of AHB master splitting | 3 days | Thu 14-05-15 | Mon 18-05-15 |  | Eric | 100%
AXI4 GenLPBindCheckers: | 3 days | Mon 11-05-15 | Wed 13-05-15 |  |  | 100%
Element level LP checker | 1 day | Mon 11-05-15 | Mon 11-05-15 | 11,42 | Anup | 100%
Power Domain level Isolation LP checker | 1 day | Tue 12-05-15 | Tue 12-05-15 | 11,50,43 | Anup | 100%
NSPS PD Sequence LP checker | 1 day | Wed 13-05-15 | Wed 13-05-15 | 11,51,44 | Anup | 100%
Non-AXI4 GenCPF: | 3 days | Mon 04-05-15 | Wed 06-05-15 |  |  | 100%
Changes from pin-level to PD level Iso rules | 1 day | Mon 04-05-15 | Mon 04-05-15 | 34 | Anup | 100%
RTL grouping | 1 day | Tue 05-05-15 | Tue 05-05-15 | 54,33 | Anup | 100%
Tech and Lib pointers | 1 day | Wed 06-05-15 | Wed 06-05-15 | 55,34 | Anup | 100%
Non-AXI4 GenLPBindCheckers: | 3 days | Tue 19-05-15 | Thu 21-05-15 |  |  | 100%
Element level LP checker | 1 day | Tue 19-05-15 | Tue 19-05-15 | 2,11,53,62 | Anup | 100%
Power Domain level Isolation LP checker | 1 day | Wed 20-05-15 | Wed 20-05-15 | 58,2,11,53,63 | Anup | 100%
NSPS PD Sequence LP checker | 1 day | Thu 21-05-15 | Thu 21-05-15 | 59,2,11,53 | Anup | 100%
Non-AXI4 LP Checkers work | 6 days | Mon 11-05-15 | Mon 18-05-15 |  |  | 91%
Element level LP checker | 6 days | Mon 11-05-15 | Mon 18-05-15 | 42 | Vinay | 90%
Power Domain level Isolation LP checker | 1 day | Wed 13-05-15 | Wed 13-05-15 | 43,44 | Harsha | 100%
AXI4 Handwritten cfgs CDC runs | 5 days | Thu 14-05-15 | Wed 20-05-15 | 45 | Sandip | 100%
AXI4 Handwritten cfgs Synthesis runs | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Rajesh | 50%
CLP NW Regression health (AXI4 80%) | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Vishnu[25%] | 100%
LPS NW Regression health (AXI4 80% w/o host checkers) | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Vishnu[25%] | 100%
Code Coverage (AXI4 80%) | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Harsha[50%],Rimu[25%],Joji[25%] | 100%
Verification Plan Documentation and Review | 8 days | Thu 14-05-15 | Mon 25-05-15 | 75 | Vishnu[50%] | 65%
Phase1 M4 | 33 days | Mon 27-04-15 | Wed 10-06-15 |  |  | 72%
SW Verif | 23 days | Mon 27-04-15 | Wed 27-05-15 |  |  | 95%
Testplan: | 5 days | Mon 27-04-15 | Fri 01-05-15 |  |  | 88%
Tune_power | 3 days | Mon 27-04-15 | Wed 29-04-15 | 46 | Bhum | 80%
CPFs | 1 day | Thu 30-04-15 | Thu 30-04-15 | 73,46 | Vishnu | 100%
LP RTL | 1 day | Fri 01-05-15 | Fri 01-05-15 | 74,46 | Vishnu | 100%
Verif | 15 days | Thu 07-05-15 | Wed 27-05-15 |  |  | 96%
Tune_power | 6 days | Thu 07-05-15 | Thu 14-05-15 | 75,53 | Bhum | 90%
CPFs | 8 days | Thu 07-05-15 | Mon 18-05-15 | 75,53 | Infonam1 | 100%
LP RTL | 10 days | Thu 07-05-15 | Wed 20-05-15 | 75,53 | Infonam2 | 90%
LP Property Coverage monitor | 15 days | Thu 07-05-15 | Wed 27-05-15 | 75,53 | Infonam3 | 100%
Error PD & CD Sequence test | 6 days | Wed 13-05-15 | Wed 20-05-15 | 36,44 | Santhosh | 100%
CPFs for DVFS | 8 days | Wed 29-04-15 | Fri 08-05-15 |  |  | 100%
Definition of DVFS modes of operation | 4 days | Wed 29-04-15 | Mon 04-05-15 | 19 | Sailesh | 100%
GenCPF update for DVFS | 2 days | Thu 07-05-15 | Fri 08-05-15 | 83,56 | Anup | 100%
CPFs for Scan | 12 days | Thu 30-04-15 | Fri 15-05-15 |  |  | 100%
Definition of Scan aware synthesis strategy | 2 days | Thu 30-04-15 | Fri 01-05-15 |  | Rajesh | 100%
GenCPF update for Scan | 2 days | Thu 14-05-15 | Fri 15-05-15 | 86,84,52 | Anup | 100%
AXI4 and Non-AXI4 CDC runs | 10 days | Thu 21-05-15 | Wed 03-06-15 | 11,64 | Sandip | 50%
AXI4 and Non-AXI4 Synthesis runs | 10 days | Thu 28-05-15 | Wed 10-06-15 | 65,11 | Rajesh | 0%
Functional Coverage Coding (70%) | 10 days | Thu 21-05-15 | Wed 03-06-15 | 81,44 | Vinay[25%],Santhosh[50%] | 30%
CLP NW Regression health (AXI4 100%, Non-AXI4 90%) | 10 days | Thu 28-05-15 | Wed 10-06-15 | 66 | Santhosh[25%],Vishnu[25%] | 80%
LPS NW Regression health (AXI4 100%, Non-AXI4 90%) | 10 days | Thu 28-05-15 | Wed 10-06-15 | 67 | Vinay[25%],Vishnu[25%] | 80%
Code Coverage (AXI4 100%, Non-AXI4 90%) | 10 days | Thu 28-05-15 | Wed 10-06-15 | 68 | Harsha[50%] | 70%
Functional Coverage (50%) | 3 days | Thu 04-06-15 | Mon 08-06-15 | 90 | Harsha[50%] | 0%
Phase1 M5 | 15 days | Thu 04-06-15 | Wed 24-06-15 |  |  | 38%
Functional Coverage Coding (100%) | 5 days | Thu 04-06-15 | Wed 10-06-15 | 90 | Vinay[25%],Santhosh[50%] | 20%
Functional Coverage (100%) | 5 days | Thu 11-06-15 | Wed 17-06-15 | 96,94 | Vinay[25%] | 0%
CLP NW Regression health (100%) | 10 days | Thu 11-06-15 | Wed 24-06-15 | 91 | Vinay[25%] | 80%
LPS NW Regression health (100%) | 10 days | Thu 11-06-15 | Wed 24-06-15 | 92 | Vinay[25%] | 80%
Code Coverage (100%) | 7 days | Thu 11-06-15 | Fri 19-06-15 | 93 | Vinay[25%] | 80%
CDC runs on customer and super cfgs | 10 days | Thu 04-06-15 | Wed 17-06-15 | 88 | Sandip | 0%
CLP and RC at pre and post synthesis on customer and super cfgs | 8 days | Thu 11-06-15 | Mon 22-06-15 | 89 | Rajesh | 0%
Checklist status review | 4 days | Thu 11-06-15 | Tue 16-06-15 | 91,92 | Vishnu[25%] | 0%
Phase2 M6 | 41 days | Wed 20-05-15 | Wed 15-07-15 |  |  | 16%
RTL Design | 5 days | Wed 27-05-15 | Tue 02-06-15 |  |  | 100%
Voltage Crossing FIFO | 2 days | Thu 28-05-15 | Fri 29-05-15 |  | Joji | 100%
RBM and RM changes | 2 days | Wed 27-05-15 | Thu 28-05-15 |  | Jaya | 100%
Bridge hierarchy modifications for Voltage Crossing and Integration of FIFO | 2 days | Mon 01-06-15 | Tue 02-06-15 | 106 | Joji | 100%
Gen_ip | 21 days | Fri 29-05-15 | Fri 26-06-15 |  |  | 43%
Integration for bridge hierarchy modifications | 3 days | Wed 24-06-15 | Fri 26-06-15 | 106108 | Eric | 0%
regbus elements LP signal aggregation | 2 days | Fri 29-05-15 | Mon 01-06-15 | 107 | Eric | 100%
valid traffic flows for DVFS | 1 day | Wed 03-06-15 | Wed 03-06-15 | 106108 | Eric[50%] | 0%
valid traffic flows for regbus | 1 day | Mon 01-06-15 | Mon 01-06-15 |  | Eric[50%] | 100%
Gen_CPF | 24 days | Tue 02-06-15 | Fri 03-07-15 |  |  | 38%
CPFs for DVFS | 2 days | Mon 29-06-15 | Tue 30-06-15 | 110 | Anup | 0%
CPFS for regbus | 3 days | Tue 02-06-15 | Thu 04-06-15 | 111 | Anup | 100%
tech and Lib pointers | 1 day | Wed 01-07-15 | Wed 01-07-15 | 115116 | Anup | 0%
sdc generation | 1 day | Thu 02-07-15 | Thu 02-07-15 | 117 | Anup | 0%
RTL grouping | 1 day | Fri 03-07-15 | Fri 03-07-15 | 118 | Anup | 0%
Verif Plan for DVFS | 2 days | Wed 20-05-15 | Thu 21-05-15 |  | Won | 100%
Verif Plan for regbus | 3 days | Wed 27-05-15 | Fri 29-05-15 |  | Jaya | 100%
Verif changes for new hierarchies | 2 days | Mon 29-06-15 | Tue 30-06-15 | 110 | Won | 0%
regbus verif infra changes | 5 days | Mon 01-06-15 | Fri 05-06-15 | 107121 | Jaya | 0%
DVFS verif infra changes | 4 days | Fri 29-05-15 | Wed 03-06-15 |  | Won | 50%
GenStreamX changes for DVFS | 3 days | Thu 04-06-15 | Mon 08-06-15 | 124 | Won | 50%
GenStreamX changes for regbus | 3 days | Mon 08-06-15 | Wed 10-06-15 | 123 | Jaya | 0%
Regbus sweep and error scenario tests | 5 days | Thu 11-06-15 | Wed 17-06-15 | 123126 | Jaya | 0%
Regbus LP checkers | 7 days | Thu 18-06-15 | Fri 26-06-15 |  |  | 0%
Element level LP checker | 4 days | Thu 18-06-15 | Tue 23-06-15 | 127 | Jaya | 0%
Power Domain level Isolation LP checker | 3 days | Wed 24-06-15 | Fri 26-06-15 | 129 | Jaya | 0%
NW for DVFS and regbus | 5 days | Mon 06-07-15 | Fri 10-07-15 | 119 | Santhosh | 0%
CLP scripts for DVFS | 2 days | Mon 29-06-15 | Tue 30-06-15 | 110111 | Vishnu | 0%
regbus code coverage analysis | 3 days | Thu 18-06-15 | Mon 22-06-15 | 127 | Won | 0%
regbus functional coverage coding | 3 days | Mon 29-06-15 | Wed 01-07-15 | 130 | Jaya | 0%
DVFS and REGBUS CDC runs | 10 days | Thu 18-06-15 | Wed 01-07-15 | 127 | Sandip | 0%
DVFS and REGBUS Synthesis runs | 15 days | Thu 18-06-15 | Wed 08-07-15 | 127 | Rajesh | 0%
DVFS and REGBUS CLP runs | 10 days | Thu 18-06-15 | Wed 01-07-15 | 127 | Vishnu | 0%
LPS NW Regression runs | 10 days | Mon 29-06-15 | Fri 10-07-15 | 130 | Vishnu | 0%
SW verification for DVFS and regbus | 5 days | Thu 18-06-15 | Wed 24-06-15 | 127 | Bhum | 0%
Sanity bench | 5 days | Mon 29-06-15 | Fri 03-07-15 | 130 | Vishnu | 0%
Documentation | 8 days | Mon 06-07-15 | Wed 15-07-15 | 140 | Vishnu | 0%