## LP V2 Phase1
Task No. | Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Complete
1 | Phase1 M1 | 53 days | Mon 23-02-15 | Wed 06-05-15 |  |  | 49%
2 | RTL Design | 53 days | Mon 23-02-15 | Wed 06-05-15 |  |  | 30%
3 | Micro-arch document | 3 days | Mon 23-02-15 | Wed 25-02-15 |  | Joji,Rimu | 100%
4 | MB changes | 5 days | Thu 09-04-15 | Wed 15-04-15 |  | Joji | 60%
5 | SB and RTR changes | 5 days | Thu 16-04-15 | Wed 22-04-15 | 3,4 | Rimu | 20%
6 | Isolation polarity changes for output ports * | 5 days | Thu 23-04-15 | Wed 29-04-15 | 4,5 | Joji | 0%
7 | V1 arch RTL cleanup in the design | 5 days | Thu 30-04-15 | Wed 06-05-15 | 6 | Rimu,Joji | 0%
8 | NSPS: | 5 days | Thu 23-04-15 | Wed 29-04-15 |  |  | 30%
9 | Aggregation logic | 2 days | Tue 28-04-15 | Wed 29-04-15 | 10 | Rimu | 0%
10 | PDS | 3 days | Thu 23-04-15 | Mon 27-04-15 | 4,5 | Rimu | 50%
11 | Gen_ip: | 38 days | Wed 11-03-15 | Fri 01-05-15 |  |  | 50%
12 | Valid traffic flow with PD information | 3 days | Wed 11-03-15 | Fri 13-03-15 |  | Anup | 100%
13 | Valid traffic flow with CD information | 2 days | Mon 20-04-15 | Tue 21-04-15 |  | Anup | 100%
14 | Cleanup of V1 architecture code | 1 day | Thu 16-04-15 | Thu 16-04-15 |  | Eric | 0%
15 | Cleanup for REGBUS | 2 days | Fri 17-04-15 | Mon 20-04-15 | 14 | Eric | 0%
16 | V2 Architecture integration | 2 days | Thu 30-04-15 | Fri 01-05-15 | 15,6,4,5 | Eric | 0%
17 | Tune_power: | 6 days | Tue 21-04-15 | Tue 28-04-15 |  |  | 0%
18 | Cleanup for REGBUS | 1 day | Tue 21-04-15 | Tue 21-04-15 |  | Sailesh | 0%
19 | Support for V2 architecture | 5 days | Wed 22-04-15 | Tue 28-04-15 | 18 | Sailesh | 0%
20 | TB XTOR Sync changes | 6 days | Tue 17-03-15 | Tue 24-03-15 |  |  | 100%
21 | SYNC_UNIT design | 2 days | Mon 23-03-15 | Tue 24-03-15 |  | Harsha | 100%
22 | CXT changes for sync | 2 days | Tue 17-03-15 | Wed 18-03-15 |  | Joe | 100%
23 | AHBXTOR changes for sync | 1 day | Thu 19-03-15 | Thu 19-03-15 |  | Jaya | 100%
24 | AMBAXTOR (Sanity) changes for sync | 1 day | Fri 20-03-15 | Fri 20-03-15 |  | Joe | 100%
25 | PMXTOR design | 6 days | Wed 11-03-15 | Wed 18-03-15 |  | Vishnu | 100%
26 | GenStreamX changes for LP TB integration | 3 days | Mon 04-05-15 | Wed 06-05-15 | 11,20,25 | Santhosh | 0%
27 | Test/Coverage Plan | 7 days | Mon 02-03-15 | Tue 10-03-15 |  | Vishnu | 100%
28 | Phase1 M2 | 30 days | Thu 02-04-15 | Wed 13-05-15 |  |  | 7%
29 | AXI4 GenCPF: | 8 days | Wed 22-04-15 | Fri 01-05-15 |  |  | 0%
30 | Cleanup for REGBUS | 1 day | Wed 22-04-15 | Wed 22-04-15 | 13 | Anup | 0%
31 | Changes from pin-level to PD level Iso rules | 1 day | Thu 23-04-15 | Thu 23-04-15 | 30 | Anup | 0%
32 | RTL grouping | 5 days | Fri 24-04-15 | Thu 30-04-15 | 31 | Anup | 0%
33 | Tech and Lib pointers | 1 day | Fri 01-05-15 | Fri 01-05-15 | 32 | Anup | 0%
34 | CLP scritps | 2 days | Mon 04-05-15 | Tue 05-05-15 | 29 | Harsha | 0%
35 | Nemesis traffic generation | 22 days | Thu 02-04-15 | Fri 01-05-15 |  |  | 23%
36 | SYNC_UNIT traffic generation * | 1 day | Mon 20-04-15 | Mon 20-04-15 |  | Santhosh | 70%
37 | Power and Clock gating/enabling * | 5 days | Tue 21-04-15 | Mon 27-04-15 | 36 | Santhosh | 50%
38 | Dynamic change of frequences or DVFS * | 4 days | Thu 02-04-15 | Tue 07-04-15 |  | JJ | 0%
39 | Cold boot randomization * | 2 days | Tue 28-04-15 | Wed 29-04-15 | 37 | Santhosh | 0%
40 | Error scenarios for LP * | 2 days | Thu 30-04-15 | Fri 01-05-15 | 39 | Santhosh | 0%
41 | AXI4 LP Checkers work | 4 days | Thu 07-05-15 | Tue 12-05-15 |  |  | 0%
42 | Element level LP checker | 2 days | Thu 07-05-15 | Fri 08-05-15 | 11,26,29 | Vinay | 0%
43 | Power Domain level Isolation LP checker | 2 days | Thu 07-05-15 | Fri 08-05-15 | 11,26,34,29 | Harsha | 0%
44 | NSPS PD Sequence LP checker | 2 days | Mon 11-05-15 | Tue 12-05-15 | 43,11,26,29 | Santhosh[25%],Harsha[75%] | 0%
45 | CLP and LPS AXI4 hand written cfgs passing | 5 days | Thu 07-05-15 | Wed 13-05-15 | 11,17,26,34,20,25,29 | Vishnu[50%] | 0%
46 | Test/Coverage Plan Review | 2 days | Thu 23-04-15 | Fri 24-04-15 |  | Vishnu | 0%
47 | Verification Plan Documentation and Review | 8 days | Mon 04-05-15 | Wed 13-05-15 | 74 | Vishnu[50%] | 0%
48 | Phase1 M3 | 18 days | Mon 04-05-15 | Wed 27-05-15 |  |  | 0%
49 | AXI4 GenLPBindCheckers: | 3 days | Mon 11-05-15 | Wed 13-05-15 |  |  | 0%
50 | Element level LP checker | 1 day | Mon 11-05-15 | Mon 11-05-15 | 11,42 | Anup | 0%
51 | Power Domain level Isolation LP checker | 1 day | Tue 12-05-15 | Tue 12-05-15 | 11,50,43 | Anup | 0%
52 | NSPS PD Sequence LP checker | 1 day | Wed 13-05-15 | Wed 13-05-15 | 11,51,44 | Anup | 0%
53 | Non-AXI4 GenCPF: | 3 days | Mon 04-05-15 | Wed 06-05-15 |  |  | 0%
54 | Changes from pin-level to PD level Iso rules | 1 day | Mon 04-05-15 | Mon 04-05-15 | 33 | Anup | 0%
55 | RTL grouping | 1 day | Tue 05-05-15 | Tue 05-05-15 | 54,32 | Anup | 0%
56 | Tech and Lib pointers | 1 day | Wed 06-05-15 | Wed 06-05-15 | 55,33 | Anup | 0%
57 | Non-AXI4 GenLPBindCheckers: | 3 days | Tue 19-05-15 | Thu 21-05-15 |  |  | 0%
58 | Element level LP checker | 1 day | Tue 19-05-15 | Tue 19-05-15 | 2,11,53,62 | Anup | 0%
59 | Power Domain level Isolation LP checker | 1 day | Wed 20-05-15 | Wed 20-05-15 | 58,2,11,53,63 | Anup | 0%
60 | NSPS PD Sequence LP checker | 1 day | Thu 21-05-15 | Thu 21-05-15 | 59,2,11,53 | Anup | 0%
61 | Non-AXI4 LP Checkers work | 6 days | Mon 11-05-15 | Mon 18-05-15 |  |  | 0%
62 | Element level LP checker | 6 days | Mon 11-05-15 | Mon 18-05-15 | 42 | Vinay | 0%
63 | Power Domain level Isolation LP checker | 1 day | Wed 13-05-15 | Wed 13-05-15 | 43,44 | Harsha | 0%
64 | AXI4 Handwritten cfgs CDC runs | 5 days | Thu 14-05-15 | Wed 20-05-15 | 45 | Sandip | 0%
65 | AXI4 Handwritten cfgs Synthesis runs | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Rajesh | 0%
66 | CLP NW Regression health (AXI4 80%) | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Vishnu[25%] | 0%
67 | LPS NW Regression health (AXI4 80% w/o host checkers) | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Vishnu[25%] | 0%
68 | Code Coverage (AXI4 80%) | 10 days | Thu 14-05-15 | Wed 27-05-15 | 45 | Harsha[50%],Rimu[25%],Joji[25%] | 0%
69 | Phase1 M4 | 33 days | Mon 27-04-15 | Wed 10-06-15 |  |  | 0%
70 | SW Verif | 23 days | Mon 27-04-15 | Wed 27-05-15 |  |  | 0%
71 | Testplan: | 5 days | Mon 27-04-15 | Fri 01-05-15 |  |  | 0%
72 | Tune_power | 3 days | Mon 27-04-15 | Wed 29-04-15 | 46 | Vishnu | 0%
73 | CPFs | 1 day | Thu 30-04-15 | Thu 30-04-15 | 72,46 | Vishnu | 0%
74 | LP RTL | 1 day | Fri 01-05-15 | Fri 01-05-15 | 73,46 | Vishnu | 0%
75 | Verif | 15 days | Thu 07-05-15 | Wed 27-05-15 |  |  | 0%
76 | Tune_power | 6 days | Thu 07-05-15 | Thu 14-05-15 | 74,53 | Bhum | 0%
77 | CPFs | 8 days | Thu 07-05-15 | Mon 18-05-15 | 74,53 | Infonam1 | 0%
78 | LP RTL | 10 days | Thu 07-05-15 | Wed 20-05-15 | 74,53 | Infonam2 | 0%
79 | LP Property Coverage monitor | 15 days | Thu 07-05-15 | Wed 27-05-15 | 74,53 | Infonam3 | 0%
80 | Error PD & CD Sequence test | 6 days | Wed 13-05-15 | Wed 20-05-15 | 35,44 | Santhosh | 0%
81 | CPFs for DVFS | 8 days | Wed 29-04-15 | Fri 08-05-15 |  |  | 0%
82 | Definition of DVFS modes of operation | 4 days | Wed 29-04-15 | Mon 04-05-15 | 19 | Sailesh | 0%
83 | GenCPF update for DVFS | 2 days | Thu 07-05-15 | Fri 08-05-15 | 82,56 | Anup | 0%
84 | CPFs for Scan | 12 days | Thu 30-04-15 | Fri 15-05-15 |  |  | 0%
85 | Definition of Scan aware synthesis strategy | 2 days | Thu 30-04-15 | Fri 01-05-15 |  | Rajesh | 0%
86 | GenCPF update for Scan | 2 days | Thu 14-05-15 | Fri 15-05-15 | 85,83,52 | Anup | 0%
87 | AXI4 and Non-AXI4 CDC runs | 10 days | Thu 21-05-15 | Wed 03-06-15 | 11,64 | Sandip | 0%
88 | AXI4 and Non-AXI4 Synthesis runs | 10 days | Thu 28-05-15 | Wed 10-06-15 | 65,11 | Rajesh | 0%
89 | Functional Coverage Coding (70%) | 10 days | Thu 21-05-15 | Wed 03-06-15 | 80,44 | Vinay[25%],Santhosh[50%] | 0%
90 | CLP NW Regression health (AXI4 100%, Non-AXI4 90%) | 10 days | Thu 28-05-15 | Wed 10-06-15 | 66 | Santhosh[25%],Vishnu[25%] | 0%
91 | LPS NW Regression health (AXI4 100%, Non-AXI4 90%) | 10 days | Thu 28-05-15 | Wed 10-06-15 | 67 | Vinay[25%],Vishnu[25%] | 0%
92 | Code Coverage (AXI4 100%, Non-AXI4 90%) | 10 days | Thu 28-05-15 | Wed 10-06-15 | 68 | Harsha[50%] | 0%
93 | Functional Coverage (50%) | 3 days | Thu 04-06-15 | Mon 08-06-15 | 89 | Harsha[50%] | 0%
94 | Phase1 M5 | 20 days | Thu 28-05-15 | Wed 24-06-15 |  |  | 0%
95 | Release Documentation | 15 days | Thu 28-05-15 | Wed 17-06-15 | 66,67 | Vishnu[50%] | 0%
96 | Functional Coverage Coding (100%) | 5 days | Thu 04-06-15 | Wed 10-06-15 | 89 | Vinay[25%],Santhosh[50%] | 0%
97 | Functional Coverage (100%) | 5 days | Thu 11-06-15 | Wed 17-06-15 | 96,93 | Vinay[25%] | 0%
98 | CLP NW Regression health (100%) | 10 days | Thu 11-06-15 | Wed 24-06-15 | 90 | Vinay[25%] | 0%
99 | LPS NW Regression health (100%) | 10 days | Thu 11-06-15 | Wed 24-06-15 | 91 | Vinay[25%] | 0%
100 | Code Coverage (100%) | 7 days | Thu 11-06-15 | Fri 19-06-15 | 92 | Vinay[25%] | 0%
101 | CDC runs on customer and super cfgs | 10 days | Thu 04-06-15 | Wed 17-06-15 | 87 | Sandip | 0%
102 | CLP and RC at pre and post synthesis on customer and super cfgs | 8 days | Thu 11-06-15 | Mon 22-06-15 | 88 | Rajesh | 0%
103 | Checklist status review | 4 days | Thu 11-06-15 | Tue 16-06-15 | 90,91 | Vishnu[25%] | 0%