## FeatureList-Status
S.No | Aha No | name | custom_field[priority_level] | custom_field[release_owner_gatekeeper] | workflow_status | custom_field[customerseval_lead] | workflow_kind | custom_field[feature_driver] | Crux | Orion | Gemini | Pegasus | Priority Level | Yes | Status
3 | NSPD-4 | AHB master area reduction | 1_High | Joe | Not Started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | 0_Customer Commit | No | Not Started
4 | NSPD-5 | Bigger Grid | 16.09 release | Sailesh | Done | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | 1_High | No | In Implementation
5 | NSPD-6 | Fast Tap 256 bit data width | 16.09 release | Joe | Done | Ingrid | Customer request | Customer request | No | No | Yes | Yes | 2_Mid | No | Partial Support
6 | NSPD-7 | Gemini Low Power Cleanup | 16.09 release | JJ | In Implementation | Ingrid | Customer request | Customer request | No | No | Yes | Yes | 3_Low | No | Nearly Done
7 | NSPD-8 | Multi NoC | 16.09 release | Kate | Nearly Done | Isabelle | Customer request | Customer request | Yes | Yes | Yes | Yes | N/A | No | Debugging
8 | NSPD-9 | NocStudio: Improve NoC Construction | 16.09 release | Nishant | Done | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | 16.09 release |  | Done
9 | NSPD-10 | NocStudio: Improve tree construction | 1_High | Sailesh | Nearly Done | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  | Maybe | SW Done; Waiting for HW
10 | NSPD-11 | Regbus Clock Gating | 1_High | Joji | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | N/A |  | HW Done; Waiting for SW
11 | NSPD-12 | Slave Bridge Clock Gating | 16.09 release | Joji | Done | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes |  |  | HW, SW Done; Waiting for Verif
12 | NSPD-13 | Switch Clock Gating in Master/Slave Bridge | 16.09 release | Joji | Done | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  | Waiting for spec
13 | NSPD-14 | Synchronizer Depth Programming (and FIFO sizing) | 16.09 release | Dawn | Done | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  | Waiting for resource
14 | NSPD-15a | System C Models - PV | 16.09 release | Eric | Done | Ingrid | Customer request | Customer request | No | Yes | No | Yes |  |  | Release
15 | NSPD-15b | System C Models - AT | 1_High | Sailesh | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  | Release
16 | NSPD-16 | Trace and Debug: debug fencing | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes |  |  | Release with Errata
17 | NSPD-17 | Trace and Debug: master bridge trace probe | 1_High | Jim | In Implementation | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes |  |  | Release as Alpha
18 | NSPD-18 | Trace and Debug: segregate regbus address space (debug APB) | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  | Release as Beta
19 | NSPD-19 | Trace and Debug: slave bridge trace probe | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes
20 | NSPD-20 | Trace and Debug: trace transport across NoC | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes
21 | NSPD-21 | UPF Support | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes
22 | NSPD-22 | user sideband for Crux | 1_High | Joji | In Implementation | Isabelle | Customer request | Customer request | Yes | No | No | No
23 | NSPD-23 | Bridge Latency Reduction (Rresp bypass width conv) | 1_High | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes
24 | NSPD-24 | Change CR/CD to put CR on sideband | 1_High | Joe | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes
25 | NSPD-25 | CHIe Master Support | 1_High | Joe | In Implementation | Nella | Eval request | Eval request | No | No | Yes | Yes
26 | NSPD-26 | Clock Gate Fast Wakeup | 1_High | Joe | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes
27 | NSPD-27 | Clock Gate Heartbeat (Get rid of Hysteresis) | 16.09 release | Joji | Done | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes
28 | NSPD-28 | Fast Path RX bypass | 1_High | Joe | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes
29 | NSPD-29 | Fast Tap Pipelining | 2_Mid | Joe | Waiting for resource | Harriet | Eval request | Eval request | No | No | Yes | Yes
30 | NSPD-30 | Fast Tap to multiple CCCs | 1_High | Joe | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes
31 | NSPD-31 | Frequency Target with Pipeline: 2.4 GHz @ 16 nm | 16.09 release | Joji | HW, SW Done; Waiting for Verif | Thelma | Eval request | Eval request | No | Yes | Yes | Yes
32 | NSPD-32 | Frequency Target: 1066MHz | 1_High | Joe | Nearly Done | Harriet | Eval request | Eval request | No | Yes | Yes | Yes
33 | NSPD-33 | Functional Safety: CSR Parity | 1_High | Joji | Not started | Agatha | Eval request | Eval request | Yes | Yes | Yes | Yes
34 | NSPD-34 | Functional Safety: Flit-level ECC | 16.09 release | Joji | In Implementation | Agatha | Eval request | Eval request | Yes | Yes | Yes | Yes
35 | NSPD-35 | Functional Safety: Packet Checksum | 1_High | Joji | Not started | Agatha | Eval request | Eval request | Yes | Yes | Yes | Yes
36 | NSPD-36 | Functional Safety: Per-hop info parity | 16.09 release | Joji | In Implementation | Agatha | Eval request | Eval request | Yes | Yes | Yes | Yes
37 | NSPD-37 | Large Wrap Requests (above 64B) | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes
38 | NSPD-38 | Multi-cell-size NoCs | 16.09 release | Joe | Done | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes
39 | NSPD-39 | NocStudio Perf Sim: Clean APIs for Orion, Gemini | 1_High | Sailesh | In Implementation | Harriet | Eval request | Eval request | No | Yes | Yes | Yes
40 | NSPD-40 | NocStudio: Hierarchical NoCs | 1_High | John | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes
41 | NSPD-41 | NocStudio: Host behavior modelling | 1_High | Sailesh | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes
42 | NSPD-42 | OCP Master Bridge | 1_High | Perry | In Implementation | Isabelle | Eval request | Eval request | No | Yes | Yes | Yes
43 | NSPD-43 | Read Data Interleave Support | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes
44 | NSPD-44 | Thelma Rate Limit based on Watermark | 3_Low | Joe | Not started | Thelma | Eval request | Eval request | No | Yes | Yes | Yes
45 | NSPD-45 | Virtual Interface for Master Bridge | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes
46 | NSPD-46 | Customer Verif: Preloading cache values | 2_Mid | Joe | Not started | Agatha | Customer request | Customer request | No | No | Yes | Yes
47 | NSPD-47 | Directory Disable (convert to snoop only) | 2_Mid | Joe | Not started | Agatha | Customer request | Customer request | No | No | Yes | Yes
48 | NSPD-48 | IMG4 | 16.09 release | Dawn | Done | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes
49 | NSPD-49 | LLC ScratchPad Interleaving | 16.09 release | Joe | Done | Ingrid | Customer request | Customer request | No | No | No | Yes
50 | NSPD-50 | NocStudio: Incremental NoC construction / freezing | 2_Mid | Eric | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes
51 | NSPD-51 | UVM customer TB - Gemini | 16.09 release | Will | Done | Ingrid | Customer request | Customer request | No | No | Yes | No
52 | NSPD-52 | Exclusive support in LLC | 16.09 release | Joe | Done | Thelma | Eval request | Eval request | No | No | No | Yes
53 | NSPD-53 | Expressway (variant of fast-bypass, but with arbitration) | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes
54 | NSPD-54 | LLC Read/Write Allocate Controls | 16.09 release | Joe | Done | Thelma | Eval request | Eval request | No | No | No | Yes
55 | NSPD-55 | NocStudio Perf Sim: Model bridge skip between ccc/llc | 2_Mid | Sailesh | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes
56 | NSPD-56 | NocStudio Perf Sim: Model snoop traffic capability | 2_Mid | Sailesh | Not started | Ingrid | Eval request | Eval request | No | No | Yes | Yes
57 | NSPD-57 | NocStudio: Host Model import (IPXACT) | 2_Mid | Sailesh | Not started | Nella | Eval request | Eval request | No | Yes | Yes | Yes
58 | NSPD-58 | Short-packet Broadcast | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes
59 | NSPD-59 | Sideband wire reduction | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes
60 | NSPD-60 | Traffic Class only affects first leg of transaction | 16.09 release | Joe | In Implementation | Thelma | Eval request | Eval request | Yes | Yes | Yes | Yes
61 | NSPD-61 | 32 port router | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | Yes | Yes | Yes | Yes
62 | NSPD-62 | LLC Flush Engine | 16.09 release | Joe | Done |  | PPA enhancement | PPA enhancement | No | No | No | Yes
63 | NSPD-63 | LLC Indirect Access | 16.09 release | Joe | HW, SW Done; Waiting for Verif |  | PPA enhancement | PPA enhancement | No | No | No | Yes
64 | NSPD-64 | LLC Second Port for Memcache Latency/Area Opt | 16.09 release | Joe | Debugging |  | PPA enhancement | PPA enhancement | No | No | No | Yes
65 | NSPD-65 | Page Locality Enhancement | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes
66 | NSPD-66 | Low Power: Multi-Voltage for ACE bridges | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
67 | NSPD-67 | Low Power: Multi-Voltage in NoC | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
68 | NSPD-68 | Low Power: remaining tune_power fixes | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
69 | NSPD-69 | Low Power: support SLV1 port of regbus tunnel (non blocking reg bus if) | 16.09 release | Jim | Done | Ingrid | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
70 | NSPD-70 | Low Power: support user regbus | 1_High | Jim | Debugging | Ingrid | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
71 | NSPD-71 | NocStudio: AMBA Bridge perf modelling in perf sim | 2_Mid | Sailesh | In Implementation | Harriet | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
72 | NSPD-72 | SIB Multiple bridges in same location | 2_Mid | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes
73 | NSPD-73 | Width Conversion info returned from Slave Bridge (PPA) | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | No
74 | NSPD-74 | 8 interfaces streaming bridge (today 4 interfaces avail) | 3_Low | Joe | Not started | Isabelle | Customer request | Customer request | Yes | No | No | No
75 | NSPD-75 | Per-interface layer connectivity (software only) | 3_Low | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes
76 | NSPD-76 | Reorder Bridge (ace, ace-lite, axi, LP) | 3_Low | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes
77 | NSPD-77 | Reorder bridge: Remove AID table | 3_Low | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes
78 | NSPD-78 | APB access with no tunnel (and NSIP) | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
79 | NSPD-79 | CSR Security Requirements Gemini | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | No | Yes | Yes
80 | NSPD-80 | Interrupt Register Default Properties (bridges, IP) | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes
81 | NSPD-81 | Mesochronous Cleanup | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
82 | NSPD-82 | NocStudio: Improve Clock Crossing Software UI | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes
83 | NSPD-83 | Priority Address Map: Negative Address Ranges | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes
84 | NSPD-84 | regbus master/tunnel port selections | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes
85 | NSPD-85 | Software overrides for system ADDR, ARID, etc. (software only) | 16.09 release | Joe | Nearly Done |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes
86 | NSPD-86 | Performance Test bench hooks for Gemini (spec only) | 16.09 release | JJ | In Implementation | Ingrid | Customer request |  | No | Yes | Yes | Yes
87 | NSPD-88 | Support of max outstanding different from Reorder Buffer depth | 1_High | Joji | Not started | Harriet | Customer request |  | No | Yes | Yes | No
88 | NSPD-89 | Deinterleaver Split size control | 1_High | Joji | Not started | Harriet | Customer request |  | No | Yes | Yes | No
89 | NSPD-90 | Virtual Interface Configurable Data/Split size | 1_High | Joji | Not started | Harriet | Customer request |  | No | Yes | Yes | No
90 | NSPD-91 | Remove a subset of ACE masters from DVM | 16.09 release | Joe | Done | Ingrid | Customer request | Usability enhancement | No | No | Yes | No
90 | NSPD-97 | Response QOS independent of orig request QOS | 3_Low | Joji | In Implementation | Ingrid | Customer request | Usability enhancement | No | No | Yes | No

## Analysis
custom_field[priority_level] | 16.09 release
Row Labels | Count of S.No
Done | 8
Nearly Done | 7
Debugging | 3
In Implementation | 9
Grand Total | 27