## FeatureList-Status
2 | S.No | Feature No | name | custom_field[priority_level] | custom_field[release_owner_gatekeeper] | workflow_status | custom_field[customerseval_lead] | workflow_kind | custom_field[feature_driver] | Crux | Orion | Gemini | Pegasus | Priority Level | Yes | Status | release for 6.12 | work in Q4 16 | Impl complexity | arch owner | rtl owner | HW verif owner | NocStudio owner | SW Verif
| 1 | NSPD-103 | NocStudio: Multidie support in iNocStudio | 0_Customer Commit | Sailesh | Not started | Isabelle | Customer request | Customer request | No | No | No | No |  |  |  | n | y | high | Sailesh | n/a |  | Nishant
| 2 | NSPD-104 | NocStudio: Perf sim improvement (40K cycles/sec loaded) | 0_Customer Commit | Sailesh | Not started | Quennie | Customer request | Customer request | [7 empty] | n | y | high | Sailesh | n/a |  | eric
| 3 | NSPD-105 | IPXACT improvement | 1_High | Jim | Not started | Isabelle | Customer request | Customer request | [7 empty] | n | n | high
| 4 | NSPD-106 | NocStudio: Machine learning | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | n | y | high | Sailesh | n/a | n/a | Nishant/Pier
| 5 | NSPD-107 | NocStudio: Shared BW specification | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | n | n | high | Sailesh | n/a | n/a | Nishant
| 6 | NSPD-114 | Prefetcher Support | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | joe | joe | kate | Nishant
| 7 | NSPD-115 | Coherency IP Error Handling | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | joe | joe | jj | n/a | n/a
| 8 | NSPD-37 | Large Wrap Requests (above 64B) | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes |  |  |  | n | y | high | joe | joe | jj | n/a
| 9 | NSPD-110 | DMA Engine | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | n | high | joji | joji | jj | ?
| 10 | NSPD-65 | Page Locality Enhancement | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | joe | joe | jj | n/a
| 11 | NSPD-112 | Synchronizer Depth in Crux | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | n | med
| 12 | NSPD-113 | DFT Hooks for LLC RAMs | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | joe | joe | ? | Nishant
| 14 | NSPD-118 | Integrating CCC & LLC | 1_High | Joe | Not Started | Xenna, charlotte | Eval request | Eval request | No | No | Yes | Yes |  |  | Release with Errata | n | y | high | joe | joe | jj | Nishant
| 15 | NSPD-101 | Multi level coherency | 1_High | Joe | Not Started | Xenna, charlotte | Eval request | Eval request | No | No | Yes | Yes |  |  | Release as Alpha | n | y | high | joe | joe | jj | Nishant
| 15 | NSPD-75 | Per-interface layer connectivity (software only) | 3_Low | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | y | low | n/a | n/a | n/a | Sailesh
| 16 | NSPD-102 | CCIX support | 1_High | Joe | Not Started | Xenna, charlotte | Eval request | Eval request | No | No | Yes | Yes |  |  | Release as Beta | n | n | high
| 17 | NSPD-79 | CSR Security Requirements Gemini | 1_High | Joe | Not started |  | Usability enhancement | Usability enhancement | No | No | Yes | Yes |  |  |  | n | y | low | joe | joe | kate | n/a
| 18 | NSPD-116 | LLC: Byte Enable Storage Support (caching partial lines) | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | n
| 19 | NSPD-82 | NocStudio: Improve Clock Crossing Software UI | 2_Mid | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | n | med | n/a | n/a | n/a | Akshay | n/a
| 20 | NSPD-89 | Deinterleaver Split size control | 1_High | Joji | Not started | Harriet | Customer request | Customer request | No | Yes | Yes | No |  |  |  | n | n | med | joji | joji | kate | Nishant
| 21 | NSPD-11b | Regbus Clock Gating (ring master/slave, CSR) | 1_High | [12 empty] | n | n | high | joji | joji | ? | eric
| 22 | NSPD-129 | CCC configurable QOS overrides | 3_Low | [12 empty] | y | y | low | Joe | Joe | jj | nishant | y
| 23 | NSPD-121 | AXI multi-cell size to -1 | 3_Low | [12 empty] | n | y |  |  |  | won | pier
| 24 | NSPD-122 | CCC preloading (1_High) | ? | [12 empty] | n | y |  |  |  | jj | Nishant
| 25 | NSPD-123 | Low power support for NOC middle hops (2_med) | ? | [12 empty] | n | n |  |  |  |  | eric
| 26 | NSPD-124 | Clock gating bugs in NSIP (1_high) | ? | [12 empty] | n | n |  |  | joji | won | n/a
| 27 | NSPD-125 | Clock gating checkers and stimulus completion (all products) | 3_Low | [12 empty] | n | n |  |  | all | won | n/a
| 28 | NSPD-126 | ACE Bridge for Master port of Coherent cluster | 2_Mid | [12 empty] | n | y | high | joe | joji | jj | Nishant
| 29 | NSPD-127 | CHI Bridge for Master port of Coherent cluster | 2_Mid | [12 empty] | n | y
| 30 | NSPD-128 | Broadcast, multicast support - Hardware | 3_Low | [12 empty] | n | n | high | Joe | joji | jj | eric
| 31 | NSPD-15b | NocStudio: System C Models - AT | 1_High | Sailesh | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  |  | n | y |  |  | n/a |  | akshay
| 32 | NSPD-16 | Trace and Debug: debug fencing | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | 1_High | No | In Implementation | n | n |  | jim | dawn | santosh
| 33 | NSPD-108 | Async clock crossing improvements | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | y | y | med | n/a | n/a | n/a | Akshay | need info
| 34 | NSPD-18 | Trace and Debug: segregate regbus address space | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | 3_Low | No | Nearly Done | n | n | high | jim | dawn | Kiran B | eric
| 35 | NSPD-109 | Deadlock Avoidance Unit (PCI/ACE deadlock) | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | y | y | low | joe | joe | jj | Nishant | y
| 36 | NSPD-20 | Trace and Debug: trace transport across NoC | 1_High | Jim | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes | 16.09 release |  | Done | n | n |  | jim | dawn | santosh
| 37 | NSPD-21 | UPF Support | 2_Mid | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes |  |  |  | n | n
| 38 | NSPD-22 | user sideband for Crux | 2_Mid | Joji | In Implementation | Isabelle | Customer request | Customer request | Yes | No | No | No |  |  |  | n | n
| 39 | NSPD-23 | Bridge Latency Reduction (Rresp bypass width conv) | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | n
| 40 | NSPD-11 | Regbus Clock Gating ( CSR) | 1_High | Joji | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  |  | n | n | med | joji | joji | Won | n/a | n/a
| 41 | NSPD-26 | Clock Gate Fast Wakeup | 2_Mid | Joe | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | n
| 42 | NSPD-28 | Fast Path RX bypass | 2_Mid | Joe | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | y | med | joji | joji | kate | eric
| 43 | NSPD-29 | Fast Tap Pipelining | 2_Mid | Joe | Not started | Harriet | Eval request | Eval request | No | No | Yes | Yes |  |  |  | n | y | high | joe | joe | jj | Nishant
| 44 | NSPD-30 | Fast Tap to multiple CCCs | 2_Mid | Joe | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes |  |  |  | n | n
| 45 | NSPD-111 | RAM module (modified LLC) | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | y | y | high | joe | joe | jj | Nishant | y
| 46 | NSPD-117 | Streaming bridge enhancements | 3_Low | [12 empty] | y | y | high | joji | Joji | joji | eric | n/a
| 47 | NSPD-35 | Functional Safety: Packet Checksum | 2_Mid | Joji | Not started | Ingrid/M | Customer request | Customer request | Yes | Yes | Yes | Yes | N/A |  | HW Done; Waiting for SW | n | n | med | joji | Joji | Won | pier
| 48 | NSPD-119 | Functional safety: ECC and Parity | 0_Customer Commit | [12 empty] | y | y | high | joji | joji | Ben | pier | n/a
| 49 | NSPD-4 | AHB master area reduction | 1_High | Joe | Not Started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes |  |  |  | n | y | high | perry | Perry | ? | n/a
| 50 | NSPD-40 | NocStudio: Hierarchical NoCs | 2_Mid | John | Not started | Isabelle | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | n
| 51 | NSPD-41 | NocStudio: Host behavior modelling (DDR) | 1_High | Sailesh | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | n
| 52 | NSPD-120 | Regbus verification support | 0_Customer Commit | [12 empty] | y | y | med | n/a | n/a | Won | pier | n/a
| 53 | NSPD-17 | Trace and Debug: master bridge trace probe | 0_Customer Commit | Jim | In Implementation | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | 2_Mid | No | Partial Support | partial | y | high | jim | dawn | Kiran B | eric | y
| 54 | NSPD-43 | Read Data Interleave Support | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes |  |  |  | n | n
| 55 | NSPD-45 | Virtual Interface for Master Bridge | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes |  |  |  | n | n
| 56 | NSPD-47 | Directory Disable (convert to snoop only) | 2_Mid | Joe | Not started | Agatha | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n
| 57 | NSPD-50 | NocStudio: Incremental NoC construction / freezing | 2_Mid | Eric | Not started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  |  | n | n
| 58 | NSPD-53 | Expressway (variant of fast-bypass, but with arbitration) | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | n
| 59 | NSPD-55 | NocStudio Perf Sim: Model bridge skip between ccc/llc | 2_Mid | Sailesh | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes |  |  |  | n | n
| 60 | NSPD-56 | NocStudio Perf Sim: RTL vs NocStudio correlation | 1_High | Sailesh | Not started | Ingrid | Eval request | Eval request | [7 empty] | n | y |  |  | n/a |  | Reza
| 61 | NSPD-56 | NocStudio Perf Sim: Model snoop traffic capability | 2_Mid | Sailesh | Not started | Ingrid | Eval request | Eval request | No | No | Yes | Yes |  |  |  | n | n
| 62 | NSPD-57 | NocStudio: Host Model import (IPXACT) | 2_Mid | Sailesh | Not started | Nella | Eval request | Eval request | No | Yes | Yes | Yes |  |  |  | n | n
| 63 | NSPD-59 | Sideband wire reduction | 2_Mid | Joe | Not started | Quennie | Eval request | Eval request | Yes | Yes | Yes | Yes |  |  |  | n | n
| 64 | NSPD-61 | 32 port router | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | Yes | Yes | Yes | Yes |  |  |  | n | n
| 65 | NSPD-19 | Trace and Debug: slave bridge trace probe | 0_Customer Commit | Jim | Not started | Ingrid | Customer request | Customer request | No | Yes | Yes | Yes | N/A | No | Debugging | partial | y | high | jim | dawn | Kiran B | eric | y
| 66 | NSPD-66 | Low Power: Multi-Voltage for ACE bridges | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | y
| 67 | NSPD-67 | Low Power: Multi-Voltage in NoC | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | n
| 68 | NSPD-68 | Low Power: remaining tune_power fixes | 2_Mid | Jim | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | n
| 69 | NSPD-70 | Low Power: support user regbus | 2_Mid | Jim | Debugging | Ingrid | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | n |  |  |  | santosh
| 70 | NSPD-71 | NocStudio: AMBA Bridge perf modelling in perf sim | 2_Mid | Sailesh | In Implementation | Harriet | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | y |  |  | n/a
| 71 | NSPD-24 | Change CR/CD to put CR on sideband | 2_Mid | Joe | Not started | Mabel | Eval request | Eval request | No | No | Yes | Yes |  |  |  | y | y | low | joji | joji | joji | Nishant | y
| 72 | NSPD-73 | Width Conversion info returned from Slave Bridge (PPA) | 2_Mid | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | No |  |  |  | n | n
| 73 | NSPD-74 | 8 interfaces streaming bridge (today 4 interfaces avail) | 3_Low | Joe | Not started | Isabelle | Customer request | Customer request | Yes | No | No | No |  |  |  | n | n
| 74 | NSPD-32 | Frequency Target: 1066MHz | 1_High | Joe | Not started | Harriet | Eval request | Eval request | No | Yes | Yes | Yes |  |  |  | y | y | low | n/a | all | n/a | n/a | n/a
| 75 | NSPD-76 | Reorder Bridge (ace, ace-lite, axi, LP) | 3_Low | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes |  |  |  | n | n
| 76 | NSPD-77 | Reorder bridge: Remove AID table | 3_Low | Joe | Not started |  | PPA enhancement | PPA enhancement | No | Yes | Yes | Yes |  |  |  | n | n
| 77 | NSPD-78 | APB access with no tunnel (and NSIP) | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | y | low |  | dawn | ben | pier
| 78 | NSPD-33 | Functional Safety: CSR Parity | 0_Customer Commit | Joji | Not started | Ingrid/M | Customer request | Customer request | Yes | Yes | Yes | Yes |  | Maybe | SW Done; Waiting for HW | y | y | low | joe | Joji | won | pier | y
| 79 | NSPD-80 | Interrupt Register Default Properties (bridges, IP) | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | n
| 80 | NSPD-81 | Mesochronous Cleanup | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | Yes | Yes | Yes | Yes |  |  |  | n | n
| 81 | NSPD-42 | OCP: Master Bridge (1_high) | 0_Customer Commit | Perry | In Implementation | Isabelle | Customer request | Customer request | No | Yes | Yes | Yes |  |  | HW, SW Done; Waiting for Verif | y | y | high | perry | Perry | Kiran B | will | n/a
| 82 | NSPD-83 | Priority Address Map: Negative Address Ranges | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | n
| 83 | NSPD-84 | regbus master/tunnel port selections | 3_Low | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | n
| 84 | NSPD-88 | Support of max outstanding different from Reorder Buffer depth | 1_High | Joji | Not started | Harriet | Customer request | Customer request | No | Yes | Yes | No |  |  |  | n | n
| 85 | NSPD-42b | OCP: Slave Bridge (1_high) | 0_Customer Commit | Perry | In Implementation | Isabelle | Customer request | Customer request | No | Yes | Yes | Yes |  |  | Waiting for spec | n | y | high | perry | Perry | Kiran B | will | n/a
| 86 | NSPD-90 | Virtual Interface Configurable Data/Split size | 1_High | Joji | Not started | Harriet | Customer request | Customer request | No | Yes | Yes | No |  |  |  | n | n
| 87 | NSPD-72 | SIB Multiple bridges in same location | 2_Mid | Joe | Not started |  | Usability enhancement | Usability enhancement | No | Yes | Yes | Yes |  |  |  | n | y | med | n/a | n/a | kiran B | Nishant | y
| 88 | NSPD-91 | FPGA Friendly: Modify components Agatha Cyclone 5 targets | 0_Customer Commit | Joji | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | No | No | 0_Customer Commit | No | Not Started | y | y | med | n/a | joji | n/a | n/a | n/a
| 89 | NSPD-93 | Functional Safety: End-to-end ecc, parity | 1_High | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | joe | joji | ? | pier
| 90 | NSPD-94 | Functional Safety: Parity with ECC | 1_High | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | joe | joji | ? | pier
| 91 | NSPD-95 | Functional Safety: User bits through the system | 1_High | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | joe | joji | ? | pier
| 92 | NSPD-92 | Functional Safety: ECC on RAM Index | 0_Customer Commit | Joji | Not started | Ingrid/M | Customer request | Customer request | No | No | Yes | Yes |  |  |  | n | n | med | Joe | Joe | JJ | pier | y
| 93 | NSPD-96 | Broadcast, multicast support for Queenie - Software | 0_Customer Commit | Sailesh | Not started | Quennie | Customer request | Customer request | Yes | No | No | No |  |  | Waiting for resource | y | y | high | Sailesh | n/a | n/a | eric | n/a
| 94 | NSPD-98 | CHI (Latest rev) Master Support | 1_High | Joe | In Implementation | Nella | Eval request | Eval request | No | No | Yes | Yes |  |  | Release | n | y | high | joe | Joji | ? | nishant
| 95 | NSPD-99 | CHI (Latest rev) Slave Support | 1_High | Joe | In Implementation | Nella | Eval request | Eval request | No | No | Yes | Yes |  |  | Release | n | n | high | joe |  |  | nishant
| 96 | NSPD-134 | Snowflakes support | 0_Customer Commit | Eric | Not started | Quennie | Customer request | Customer request | Yes | No | No | No |  |  |  | n | n | med | Eric | n/a | JJ | eric | y
| 97 | NSPD-130 | LLC Error Handling: No allocation on error | 3_Low | [12 empty] | y | y | low | Joe | Joe | jj | n/a | n/a
| 98 | NSPD-131 | Per node clock delay | 3_Low | [12 empty] | y | y | low | n/a | n/a | n/a | Eric | y
| 99 | NSPD-132 | Warning hiding / control | 3_Low | [12 empty] | y | y | low | n/a | n/a | n/a | Eric | y
| 100 | NSPD-133 | define/defcmd macros | 3_Low | [12 empty] | y | y | med | n/a | n/a | n/a | Eric | y
| 101 | NSPD-135 | MultiNOC Deadloack Analysis Support | 0_Customer Commit | [12 empty] | y | y | med | Sailesh | n/a | n/a | Sailesh | y
Note on V42: CSR - low ring master/slave - hig
Note on D80: LLC MDA waived

## Analysis
Count - S.No | workflow_status
custom_field[priority_level] | (empty) | Debugging | In Implementation | Not started | Total Result
1_High | 1 |  | 2 | 26 | 29
2_Mid | 2 | 1 | 2 | 24 | 29
3_Low |  |  |  | 4 | 4
0_Customer Commit | 2 |  | 3 | 8 | 13
? | 3 |  |  |  | 3
Total Result | 8 | 1 | 7 | 62 | 78