## FeatureList-Status
2 | S.No | Aha No | name | priority_level | Release commit | release_owner | workflow_status | customer | workflow_kind | feature_driver | Crux | Orion | Gemini | Pegasus | Priority Level | Yes | Status
| 1 |  | FuSa - Interface parity check | 0_Customer Commit | Yes | joji | Not Started | Mabel | Customer request | Customer request | Yes | Yes | Yes | Yes | 0_Customer Commit | No | Not Started
| 2 |  | FuSa: ECC on RAM Index | 0_Customer Commit | No | joe |  | Mabel | Customer request | [5 empty] | 1_High | No | In Implementation
| 3 |  | Isabelle: Perf counters/register updates | 0_Customer Commit | Yes | joji | Not Started | Isabelle | Customer request | Customer request | Yes | No | No | No | 2_Mid | No | Partial Support
| 4 |  | Trace & Debug thelma release | 0_Customer Commit | Yes | Jim | Not Started | Thelma | Customer request | Customer request | No | Yes | Yes | Yes | 3_Low | No | Nearly Done
| 5 |  | LLC: Byte Enable Storage Support (caching partial lines) | 0_Customer Commit | No | joe |  | Peggy | Customer request | [5 empty] | N/A | Next Rel | Debugging
| 6 |  | Inode Stamping support | 0_Customer Commit | Yes | eric |  | Ingrid | Customer request | [5 empty] | 17.04 release |  | Done
| 7 |  | 512bit IOCB support (remove Wack) | 0_Customer Commit | yes | Joe |  | Peggy | Customer request | [5 empty] | Dropped | Maybe | SW Done; Waiting for HW
| 8 |  | Non-coherent traffic going through CCC | 0_Customer Commit | Yes | joe | Not Started | Peggy | [6 empty] | N/A |  | HW Done; Waiting for SW
| 9 |  | Asymetric rd & wr width sizes | 0_Customer Commit | yes | joji |  | winnie
| 10 |  | Regfile support for reorder buffers - 2 port regfile | 0_Customer Commit | Yes | joji | Not Started | Sarah | Eval request | Eval request | No | Yes | Yes | Yes |  |  | HW, SW Done; Waiting for Verif
|  |  | SRAM/Regfile support for reorder buffers - 1&2 port SRAM | 1_High | Next Rel | joji
| 12 |  | SystemC support - AT models (Orion) | 1_High | No | Sailesh | Not Started | Thelma | Customer request | Customer request | No | Yes | Yes | Yes
| 13 |  | Machine learning based build - Gemini | 1_High | Yes | Sailesh | Not Started | Isabelle | Internal | Internal | No | Yes | Yes | Yes |  |  | Waiting for spec
| 14 |  | Machine learning based build - Orion | 1_High | Yes | Sailesh | Not Started | Isabelle | Internal | Internal | Yes | Yes | No | No |  |  | Waiting for resource
| 15 |  | Snowflakes support | 1_High | No | eric | Not Started | Quennie | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  | Release
| 16 |  | CCC Pre-loader | 1_High | No | JJ | Not Started | Ingrid | Customer request | Customer request | No | No | Yes | Yes |  |  | Release
| 17 |  | CHI Support - Xilinx | 1_High | No | Joe | Not Started | Xena | Customer request | Customer request | No | No | Yes | Yes |  |  | Release with Errata
| 18 |  | FPGA readiness - Qsys support | 1_High | No | Babu | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | Yes | Yes |  |  | Release as Alpha
| 19 |  | RAMs outside of the NoC | 1_High | No | Joe | Not Started | Xena | Customer request | Customer request | No | No | No | Yes |  |  | Release as Beta
| 20 |  | CHI Support - Gemini | 1_High | No | Joe | Not Started | Nella | Customer request | Customer request | No | No | Yes | Yes
| 21 |  | Integrating NoCs from different NocStudio releases | 1_High | No | Babu | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes
| 22 |  | NocStudio - RTL vs. Perf sim accuracy improvement (Inputs from Sarah) | 1_High | no | John | Not Started | Sarah | Eval request | Eval request | Yes | Yes | Yes | Yes
| 23 |  | NocStudio: Host Model import (IPXACT) | 1_High | No | Babu | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | Yes | Yes
| 24 |  | Max outstanding different from Reorder Buffer depth | 1_High | No | Babu | Not Started | Sarah | Customer request | Customer request | No | Yes | Yes | Yes
| 25 |  | SystemC support - AT models (Gemini) | 1_High | No | Sailesh | Not Started | Thelma | Customer request | Customer request | Yes | Yes | Yes | Yes
| 26 |  | SystemC support - Cache models for Pegasus & Directory | 1_High | no | Sailesh | Not Started | Thelma | Customer request | Customer request | No | Yes | Yes | Yes
| 27 |  | CSR Security Requirements Gemini | 1_High | No | joe
| 28 |  | Memory controller deadlock fix - HW | 1_High | yes | joji
| 29 |  | Memory controller deadlock fix - SW prop | 1_High | yes | Nishant
| 30 |  | Full traffic class control in NoCStudio | 1_High | no | Nishant |  | Thelma
| 31 |  | OCP sanity test bench support | 2_Mid | Next Rel | Will | Not Started | Isabelle | Customer request | Customer request | No | Yes | Yes | No
| 32 |  | 32 port router | 2_Mid | No | Babu | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes
| 33 |  | AHB bridge improvement (Area, AHB5) | 2_Mid | no | Bob | Not Started | Sarah | Customer request | Customer request | No | Yes | Yes | Yes
| 34 |  | OCP - Master and slave support | 2_Mid | no | Perry | Not Started | Isabelle | Customer request | Customer request | No | Yes | Yes | Yes
| 35 |  | Pegasus - AXI user bits transfer support | 2_Mid | No | Joe | Not Started | Sarah | Eval request | Eval request | No | No | No | Yes
| 36 |  | Pegasus - Read & invalidate | 2_Mid | No | Joe | Not Started | Sarah | Eval request | Eval request | No | No | No | Yes
| 37 |  | Pegasus - Write-through support | 2_Mid | No | Joe | Not Started | Sarah | Eval request | Eval request | No | No | No | Yes
| 38 |  | Reorder bridge | 2_Mid | No | Babu | Not Started | Sarah | Eval request | Eval request | No | Yes | Yes | Yes
| 39 |  | FuSa:Parity on registers (LLC, DVM) | 2_Mid | No | joe
| 40 |  | Bridge Latency Reduction (Rresp bypass width conv) | 2_Mid | Next Rel
| 41 |  | NocStudio: DDR & Agent modeling | 2_Mid | Yes | John | Not Started | Isabelle | Customer request | Customer request | Yes | Yes | Yes | Yes
| 42 |  | NocStudio: Hierarchical NoCs | 2_Mid | Next Rel
| 43 |  | NocStudio: Incremental NoC construction / freezing | 2_Mid | Next Rel
| 44 |  | NocStudio: Sideband wire reduction | 2_Mid | Next Rel
| 45 |  | Page Locality Enhancement | 2_Mid | Next Rel | joji
| 46 |  | Regbus Clock Gating (ring master/slave, CSR) | 2_Mid | Next Rel
| 47 |  | SIB Multiple bridges in same location | 2_Mid | Next Rel
| 48 |  | Split size enhancement | 2_Mid | No | joji
| 49 |  | T&D: debug fencing | 2_Mid | Next Rel
| 50 |  | T&D: segregate regbus address space | 2_Mid | Next Rel
| 51 |  | T&D: trace transport across NoC | 2_Mid | Next Rel
| 52 |  | Virtual AXI: Adding VCs on transmit side | 2_Mid | Next Rel | joji
| 53 |  | Width Conversion info returned from Slave Bridge (PPA) | 2_Mid | Next Rel | joji
| 54 |  | Clock gating bugs in NSIP | 2_Mid | No | joji
| 55 |  | Low power support for NOC middle hops | 2_Mid | No | jim
| 56 |  | SRAMs of different physical dimesions instantiating same module | 2_Mid | No | eric
| 57 |  | ECC checking for directory control buffer (ASIL) | 2_Mid | Next Rel
| 58 |  | Constant parameter arrays - parity (ASIL) | 2_Mid | Next Rel
| 59 |  | Flop structure parity - All FIFOs, non FIFOs in Bridges (ASIL) | 2_Mid | No | joji
| 60 |  | Flop structure parity - non FIFOs in CCC & LLC (ASIL) | 2_Mid | no | joe
| 61 |  | End to End ECC Data (ASIL) | 2_Mid | No | joe
| 62 |  | Interface Parity including the R5/R7 (ASIL) - NS implementation | 2_Mid | No | joji
| 63 |  | CCC – Snoop Queue parity protection (ASIL) | 2_Mid | Next Rel
| 64 |  | LLC – SPRT storage parity protection (ASIL) | 2_Mid | Next Rel
| 65 |  | DMA Engine | 3_Low | Next Rel
| 66 |  | Prefetcher Support in LLC | 3_Low | No | joe
| 67 |  | UPF Support | 3_Low | Next Rel
| 68 |  | FuSa - Interface parity for Tunner | 2_Mid | No | joji
| 69 |  | FuSa - Packet checksum | Dropped | no | joji | Not Started | Ingrid | Customer request | Customer request | Yes | Yes | Yes | Yes
| 70 |  | Tcl interface to NoCStudio | 1_High | Yes | eric
| 71 |  | ROB (Reorder Bridge) for Orion (Non LP) | 0_Customer Commit | Yes | Kiran |  | winnie
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
90
90
| 95 |  | Regfile support for LLC, CCC,IOCB | 0_Customer Commit | yes | Jim

## FeatureList-Owners
2 | S.No | Aha No | name | priority_level |  | release_owner | workflow_status | Arch Owner | SW Owner | SW Verif Owner | HW Owner | HW Verif Owner | Priority Level | Yes | Status
| 1 |  | FuSa - Interface parity check | 0_Customer Commit | Yes | joji | Not Started | Joe | Nishant | Nishant | Joe | JJ | 0_Customer Commit | No | Not Started
| 2 |  | FuSa: ECC on RAM Index | 0_Customer Commit | No | joe |  | Joe | Nishant | Nishant | Joe | JJ | 1_High | No | In Implementation
| 3 |  | Isabelle: Perf counters/register updates | 0_Customer Commit | Yes | joji | Not Started | Bob |  |  |  |  | 2_Mid | No | Partial Support
| 4 |  | Trace & Debug thelma release | 0_Customer Commit | Yes | Jim | Not Started | Perry | Eric | Eric | Perry | Kiran | 3_Low | No | Nearly Done
| 5 |  | LLC: Byte Enable Storage Support (caching partial lines) | 0_Customer Commit | No | joe | [6 empty] | N/A | No | Debugging
| 6 |  | Inode Stamping support | 0_Customer Commit | Yes | eric | [6 empty] | 16.09 release |  | Done
| 7 |  | 512bit IOCB support (remove Wack) | 0_Customer Commit | yes | Joe | [7 empty] | Maybe | SW Done; Waiting for HW
| 8 |  | Non-coherent traffic going through CCC | 0_Customer Commit | Yes | joe | Not Started | [5 empty] | N/A |  | HW Done; Waiting for SW
| 10 |  | Regfile support for reorder buffers - 2 port regfile | 0_Customer Commit | Yes | joji | Not Started | [7 empty] | HW, SW Done; Waiting for Verif
| 13 |  | Machine learning based build - Gemini | 1_High | Yes | Sailesh | Not Started | [7 empty] | Waiting for spec
| 14 |  | Machine learning based build - Orion | 1_High | Yes | Sailesh | Not Started | [7 empty] | Waiting for resource
| 15 |  | Snowflakes support | 1_High | No | eric | Not Started | [7 empty] | Release
| 16 |  | CCC Pre-loader | 1_High | No | JJ | Not Started | [7 empty] | Release
| 17 |  | CHI Support - Xilinx | 1_High | No | Joe | Not Started | [7 empty] | Release with Errata
| 18 |  | FPGA readiness - Qsys support | 1_High | No | Babu | Not Started | [7 empty] | Release as Alpha
| 19 |  | RAMs outside of the NoC | 1_High | No | Joe | Not Started | [7 empty] | Release as Beta
| 20 |  | CHI Support - Gemini | 1_High | No | Joe | Not Started
| 21 |  | Integrating NoCs from different NocStudio releases | 1_High | No | Babu | Not Started
| 22 |  | NocStudio - RTL vs. Perf sim accuracy improvement (Inputs from Sarah) | 1_High | no | John | Not Started
| 23 |  | NocStudio: Host Model import (IPXACT) | 1_High | No | Babu | Not Started
| 24 |  | Max outstanding different from Reorder Buffer depth | 1_High | No | Babu | Not Started
| 25 |  | SystemC support - AT models (Gemini) | 1_High | No | Sailesh | Not Started
| 26 |  | SystemC support - Cache models for Pegasus & Directory | 1_High | no | Sailesh | Not Started
| 27 |  | CSR Security Requirements Gemini | 1_High | No | joe
| 28 |  | Memory controller deadlock fix - HW | 1_High | yes | joji
| 29 |  | Memory controller deadlock fix - SW prop | 1_High | yes | Nishant
| 30 |  | Full traffic class control in NoCStudio | 1_High | no | Nishant
| 31 |  | OCP sanity test bench support | 2_Mid | Next Rel | Will | Not Started
| 32 |  | 32 port router | 2_Mid | No | Babu | Not Started
| 34 |  | OCP - Master and slave support | 2_Mid | no | Perry | Not Started
| 35 |  | Pegasus - AXI user bits transfer support | 2_Mid | No | Joe | Not Started
| 36 |  | Pegasus - Read & invalidate | 2_Mid | No | Joe | Not Started
| 37 |  | Pegasus - Write-through support | 2_Mid | No | Joe | Not Started
| 38 |  | Reorder bridge | 2_Mid | No | Babu | Not Started
| 39 |  | FuSa:Parity on registers (LLC, DVM) | 2_Mid | No | joe
| 40 |  | Bridge Latency Reduction (Rresp bypass width conv) | 2_Mid | Next Rel
| 41 |  | NocStudio: DDR & Agent modeling | 2_Mid | Yes | John | Not Started
| 42 |  | NocStudio: Hierarchical NoCs | 2_Mid | Next Rel
| 43 |  | NocStudio: Incremental NoC construction / freezing | 2_Mid | Next Rel
| 44 |  | NocStudio: Sideband wire reduction | 2_Mid | Next Rel
| 45 |  | Page Locality Enhancement | 2_Mid | Next Rel | joji
| 46 |  | Regbus Clock Gating (ring master/slave, CSR) | 2_Mid | Next Rel
| 47 |  | SIB Multiple bridges in same location | 2_Mid | Next Rel
| 48 |  | Split size enhancement | 2_Mid | No | joji
| 49 |  | T&D: debug fencing | 2_Mid | Next Rel
| 50 |  | T&D: segregate regbus address space | 2_Mid | Next Rel
| 51 |  | T&D: trace transport across NoC | 2_Mid | Next Rel
| 52 |  | Virtual AXI: Adding VCs on transmit side | 2_Mid | Next Rel | joji
| 53 |  | Width Conversion info returned from Slave Bridge (PPA) | 2_Mid | Next Rel | joji
| 54 |  | Clock gating bugs in NSIP | 2_Mid | No | joji
| 55 |  | Low power support for NOC middle hops | 2_Mid | No | jim
| 56 |  | SRAMs of different physical dimesions instantiating same module | 2_Mid | No | eric
| 57 |  | ECC checking for directory control buffer (ASIL) | 2_Mid | Next Rel
| 59 |  | Flop structure parity - All FIFOs, non FIFOs in Bridges (ASIL) | 2_Mid | No | joji
| 60 |  | Flop structure parity - non FIFOs in CCC & LLC (ASIL) | 2_Mid | no | joe
| 61 |  | End to End ECC Data (ASIL) | 2_Mid | No | joe
| 62 |  | Interface Parity including the R5/R7 (ASIL) - NS implementation | 2_Mid | No | joji
| 63 |  | CCC – Snoop Queue parity protection (ASIL) | 2_Mid | Next Rel
| 64 |  | LLC – SPRT storage parity protection (ASIL) | 2_Mid | Next Rel
| 65 |  | DMA Engine | 3_Low | Next Rel
| 66 |  | Prefetcher Support in LLC | 3_Low | No | joe
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 67 |  | UPF Support | 3_Low | Next Rel
| 69 |  | FuSa - Packet checksum | Dropped | no | joji | Not Started
| 70 |  | Tcl interface to NoCStudio | 1_High | Yes | eric
| 71 |  | ROB (Reorder Bridge) for Orion (Non LP) | 0_Customer Commit | Yes | Kiran
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
90
90
| 95 |  | Regfile support for LLC, CCC,IOCB | 0_Customer Commit | yes | Jim

## Analysis
Project Status |  | Architecture Owners |  | SW Owners |  | SW Verif Owners |  | HW Owners |  | HW Verif Owners
Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No | Row Labels | Count of S.No
Not Started | 28 | Bob | 1 | Eric | 1 | Eric | 1 | Joe | 2 | JJ | 2
(blank) | 59 | Joe | 2 | Nishant | 2 | Nishant | 2 | Perry | 1 | Kiran | 1
Grand Total | 87 | Perry | 1 | (blank) | 87 | (blank) | 87 | (blank) | 87 | (blank) | 87
|  | (blank) | 86 | Grand Total | 90 | Grand Total | 90 | Grand Total | 90 | Grand Total | 90
|  | Grand Total | 90