## data
Aha ref # | feature description (from Aha or misc) | area | Status | owner | modules/tests | work duration orig (in weeks) | work left | Priority | Remarks
NA | Additional tests (From Nishant's document, cookbook, others) | sw verif | In Progress | InfoNam | C0/C1 | 0.8 | 0.04 | medium | add_ccc_group 1.1->1.7 setup_coherency 6.1, 6.2, 6.3 highlight_coherency 1.1, 1.2, 1.3, 2.1 unhighlight_coherency 1.1, 1.2, 1.3, 2.1 add_ccc.7.1, 7.2(low) bridge_prop.36.1, 38.1, 39.1 add_dvm.2.4 gen_ip.81.1, 81.2(low), 81.3
NA | Generate SDC file | sw verif | Done | Bhumesh | C0/C1 | 0.2 | 0 | medium | One output golden file test
NA | new property for the bridge AXI to ACE-lite bridge (was Aha - Specifying agents (Shapes, Sizes, etc), floorplan agents) | sw verif | In Progress | Bao | C0/C1 | 0.6 | 0 | medium | gen_ip.80.1
NA | Specifying BW (Coherent, Non-coherent),Latency requirements | sw verif | In Progress | Bao | C0/C1 | 0.4 | 0 | medium | ifce_prop.3.1 set_host_processing_latency.2.1 ifce_prop.6.1 latency.1.2, 2.2, 4.3, 5.2, 6.2, 7.2, 9.2, 11.2, 13.2, 14.2, 15.2, 16.3 we need to have a review to make sure that BW and latency is covered enough
NA | Specifying QoS requirements | sw verif | In Progress | Bao | C0/C1 | 0.4 | 0 | medium | analyze_traffic.1.2.3, add_traffic.7.1, 7.3 -> write new map.1.1.1, 1.1.2, 1.3, 1.4 new_mesh.2.1
STUDIO-7 | Support multiple clock domains | sw verif |  | Bao | perf sim CSV | 0.2 | 0 | low | clock_cross.4
STUDIO-1 | Support fast-tap for lower latency | sw verif |  | Sinh | Not needed | 0.6 | 0 | low | gen_ip.79.1, 79.2, bridge_prop.35.1 bridge_prop 37.1, 37.2, 37.3, 37.4, 37.5
NA | Support for last level cache (HW and SW) (add LLC; setup traffic; setup address range) | sw verif | In Progress | Sinh | C0/C1 | 2.8 | 0 | medium | add_llc.1.1 -> 1.4 add_traffic_c.6.1, 6.2, 6.3, 1.1 -> 1.9, 2.1, 2.2, 2.3, 2.4.*, 2.8.*, 2.11, 2.12, 2.13 add_range 1.13, 7, 8.1, 8.2, 8.3, 9.1 setup_coherency 1.4, 1.5, 1.6, 5.1 csv_property_test add_llc_group.1.1 -> 1.7
NA | Support for last level cache (HW and SW) gen_rtl | sw verif | In Progress | Bao | C0/C1 | 1.2 | 0 | medium | llc_props 1->3
NA | Generate IPXACT File | sw verif | Done | Bhumesh | C0 | 0.2 | 0 | low | One output golden file test
NA | Synthesis (def file) | sw verif | Done | Bhumesh | C0/C1 | 0.2 | 0 | medium | One output golden file test
NA | tunnel (nice to have) | sw verif | Done | Bao | C0/C1 | 0.2 | 0 | medium | tunnel.7.1
NA | unified address table format | sw verif | In Progress | Sinh | C0/C1 | 0.4 | 0 | medium | add_range10.1
8.2
NA | Auto output registering and pipelining needs to be done in systematic way. OAMBA-3 | sw verif | Done | Anup/Bhumeshwar | perf sim CSV | 0.4 | 0 | medium | SW Dev is in progress. Need brainstorming. Anup and Bhumesh to come up with effort estimate.
Note on D18: Author: The output registering task has undergone more changes. Waiting for SW dev to get finished.

## Work Per Feature
Row Labels | Sum of work duration orig (in weeks) | Sum of work left
Additional tests (From Nishant's document, cookbook, others) | 0.8 | 0.04
Generate IPXACT File | 0.2 | 0
Generate SDC file | 0.2 | 0
new property for the bridge AXI to ACE-lite bridge (was Aha - Specifying agents (Shapes, Sizes, etc), floorplan agents) | 0.6 | 0
Specifying BW (Coherent, Non-coherent),Latency requirements | 0.4 | 0
Specifying QoS requirements | 0.4 | 0
Support fast-tap for lower latency | 0.6 | 0
Support for last level cache (HW and SW) (add LLC; setup traffic; setup address range) | 2.8 | 0
Support for last level cache (HW and SW) gen_rtl | 1.2 | 0
Support multiple clock domains | 0.2 | 0
Synthesis (def file) | 0.2 | 0
tunnel (nice to have) | 0.2 | 0
unified address table format | 0.4 | 0
Grand Total | 8.2 | 0.04

## Work Per Person
Row Labels | Sum of work duration orig (in weeks) | Sum of work left
Bao | 3 | 0
Bhumesh | 0.6 | 0
InfoNam | 0.8 | 0.04
Sinh | 3.8 | 0
Grand Total | 8.2 | 0.04